## CASH FLOW
Row Labels | Sum of PAYMENT REQ. MAY | Sum of PAYMENT REQ. | Sum of PAYMENT REQ. JULY | Sum of PAYMENT REQ. AUG | Sum of PAYMENT REQ. SEPT | Sum of PAYMENT REQ. OCT | Sum of PAYMENT REQ. NOV | Sum of PAYMENT REQ. DEC | Sum of PAYMENT REQ. JAN
2012-APL-SPARES
2207-JTL-6HI CRM | [5 empty] | 11352600
2221-TPI REVAMP |  |  |  |  | 1174879
2231-SHYAM-6HI CRM | 1250000 |  | 11842440 | 19569032 | 3672763
2239-SHYAM-TRIMMING | 2154759 | 192700.9 | 7525915.94 | 3642945.52
2301-CIM-6HI CRM |  |  | 3218767 | 1488865 | 843907
2302-CIM-PICKLING
2304-CIM-ARP
2305-APL-CGL | 687576.8 | 11143914.18 | 19936192 | 32584722 | 38941171
2310-SURYA-4HI CRM
2401-AART-TRIMMER
2402-SURYA-REWINDING
2403-GOPANI-4HI CRM | 623677 |  | 4253610 | 4786009 | 16176562 | 3688857
2404-GOPANI-4HI SPM | 6294146 | 10917812.62 | 17027256.74 | 8720472.91 | 2637411 | 4892793
2405-JSPL-TRIMMING | 3407123 |  | 13585458 | 1549040 | 6492065 | 1731869
2406-JSPL-TRIMMING
2407-APL-PICKLING | 12527581.26 | 6288782.68 | 5289749 | 1434688 | 15180692 | 1780000
2409-PROMPT MILL
2411-SENMEN-SPARES
2412-HI TECH-SPARE
2414-UTTAM-6HI CRM | 5822066 | 18015427 | 30273726 | 21234588.12 | 55149268 | 27980241 | 49426020
2415-UTTAM-TRIMMING
2420-INDIA STEEL-CCL | 2630802 | 5699200 | 15664705 | 46468900 | 25733214 | 22680000 | 14745065 | 9000000 | 11092000
2421-APL-CGL | 13647457.5 | 10278339.84 | 23868260.9 | 22918786.74 | 76140772.82 | 25547916.82 | 20613100
2422-AECPL-CGL | 4179293 | 23970086.02 | 19953319.98 | 23894992.49 | 63193038.74 | 1797413.76
2424-MMI-6HI CRM |  | 3950320 | 200246 | 6962000 | 29337280 | 12001200
2425-MMI-6HI CRM | 2669009 | 3599843 | 22917433 | 22811352.78 | 16572649.42 | 88894619 | 24624600
2426-VIKAS-PICKLING | 1122300 | 3669500 | 800000 | 18483100 | 3750000 | 959528.41 | 9053234.8 | 26300000 | 5800000
2427-PROMPT-6HI CRM |  | 11725702.8 | 687496.32 | 1226700 | 22316552.38 | 33403805.72 | 63848200 | 28848000
2428-BMWIL-CGL
2501-AL SHAKER-6HI CRM | 1665920 | 4689000 |  | 11370850 | 12078708 | 12021771 | 14794233.6 | 32455334 | 33327211
2502-AL SHAKER-PICKLING |  | 2040000 |  | 3460000
2503-AFRICAN STEEL-SPARE
2504-BMWIL-SPARES |  | 309520
2505-APL-TANDEM-CRM
2506-JSW-APL | 105000 | 24000000 | 10000000 | 6500000 | 8000000 | 1500000 | 1500000 | 1500000
2507-JSW-BAWAL-SPARE | [5 empty] | 2815008 | 1860030.6
2508-MMI-SPARE | 534557.88 | 3870345.76 | 2999836.3 | 926818 | 425219
2511-GAURANG-6HI
2516-APL-5 TANK PICKLING
2518-APL-SPM |  |  | 8170000 |  |  | 1300000 | 291000
2521-BMWIL-6HI CRM | 11527620 | 198082.8 | 687496.32 | 1226700 | 22316552.38 | 33403805.72 | 63848200 | 28848000
2522-APL-SPM |  |  | 150000 |  | 2098246 | 2329152.6 | 799212
2523-JSW BAWAL
2527-AECPL-GI/GL LINE
2535-JSW-JFE-POR SPARE
(blank)
Grand Total | 70848888.44 | 144558577.6 | 219051908.5 | 261260562.56 | 422230950.74 | 290080581.03 | 265402896 | 126951334 | 50219211

## Sheet2
DISP. MONTH | (Multiple Items)
Sum of BILLING VALUE (Rs.) | Column Labels
Row Labels | Apr | May | Jun | Jul | Aug | Sep | Grand Total
2404-GOPANI-4HI SPM | Column Labels Apr: 1000000 | 1000000
2414-UTTAM-6HI CRM | Column Labels Apr: 4100000 | 4100000
2421-APL-CGL | Column Labels Apr: 1500000 | 1500000
2425-MMI-6HI CRM | Column Labels Apr: 344000 | 344000
2427-PROMPT-6HI CRM | Column Labels Apr: 14600000; Column Labels May: 6400000 | 21000000
2428-BMWIL-CGL | 100900000 | 71400000 | 48600000 | 83800000 | 56000000 | 78000000 | 438700000
2501-AL SHAKER-6HI CRM | Column Labels Apr: 3736791.1037; Column Labels May: 19185399; Column Labels Jun: 8950000 | 31872190.1037
2502-AL SHAKER-PICKLING | Column Labels Apr: 17095410; Column Labels May: 15210000; Column Labels Jun: 10080000 | 42385410
2506-JSW-APL | Column Labels Apr: 19186000; Column Labels May: 3620000 | 22806000
2511-GAURANG-6HI | 18940000 | 91246166 | 23340000 | 39313300 |  |  | 172839466
2512-GAURANG-TRIMMING | Column Labels Aug: 3800000; Column Labels Sep: 3700000 | 7500000
2514-GAURANG-CGL |  | 45800000 | 161600000 | 67300000 | 87300000 | 153000000 | 515000000
2516-APL-5 TANK PICKLING |  | 73050000 | 25400000 | 44100000 | 23500000 | 19000000 | 185050000
2517-APL-6 STAND | Column Labels Aug: 90900000; Column Labels Sep: 446900000 | 537800000
2518-APL-SPM | 53200000 | 75300000 | 76600000 | 25700000 |  |  | 230800000
2519-APL-CGL | Column Labels Jul: 3800000; Column Labels Aug: 137700000; Column Labels Sep: 215600000 | 357100000
2520-APL-CCL | Column Labels Aug: 7600000; Column Labels Sep: 177600000 | 185200000
2521-BMWIL-6HI CRM | Column Labels Apr: 18262000; Column Labels May: 5774000 | 24036000
2522-APL-SPM | Column Labels Apr: 27120000 | 27120000
2527-AECPL-GI/GL LINE | Column Labels Apr: 127869500; Column Labels May: 71000000; Column Labels Jun: 11000000 | 209869500
2529-KHUSHBOO-CCL |  | 1800000 | 11800000 | 28100000 | 14900000 | 7000000 | 63600000
2533-BMWIL-4 TANK PICKLING |  | 7200000 | 38500000 | 71900000 | 32500000 | 5000000 | 155100000
2534-BMWIL-TRIMMING |  | 4100000 | 5200000 | 12300000 | 15900000 |  | 37500000
2540-AS PRECISION-ELECTRICAL | Column Labels May: 125100000 | 125100000
2544-APL-REWINDING |  | 1200000 | 1900000 | 2800000 | 10700000 |  | 16600000
25M006-BMWIL-MILL BEARING | Column Labels Sep: 26154450 | 26154450
2601-BMWIL - 6HI CRM |  |  | 110100000 | 29300000 | 167600000 | 33000000 | 340000000
2602-BMWIL-SLITTING |  | 16600000 | 10200000 | 5500000 | 25200000 |  | 57500000
2604-AL PROMPT-CGL | Column Labels Aug: 45100000; Column Labels Sep: 91200000 | 136300000
2606-SHYAM-SPARE | Column Labels Jun: 24800000 | 24800000
2607-JSW-SPARE | Column Labels Jul: 9500000 | 9500000
2608-BMWIL-CRM (SPARE) | Column Labels Jul: 37658824.5763 | 37658824.5763
2610-BMWIL-CGL (SPARE) | Column Labels Sep: 56180324.5763 | 56180324.5763
2611-APL-CGL | Column Labels Sep: 52800000 | 52800000
2612-BMWIL-SLITTING (SPARE) | Column Labels Aug: 1692774.5763 | 1692774.5763
2613-BMWIL-PICKLING (SPARE) | Column Labels Aug: 9767009.322 | 9767009.322
2614-BMWIL-TRIMMING (SPARE) | Column Labels Aug: 903719.4915 | 903719.4915
2615-BMWIL-CRM (SPARE) | Column Labels Sep: 26106134 | 26106134
Grand Total | 407853701.1037 | 633985565 | 568070000 | 461072124.5763 | 731063503.3898 | 1391240908.5763 | 4193285802.6461

## PROJECTS
PROJECT | BOI /MANF. | PM | ASSEMBLY | RISK FB/ PAYMENT/ RED FLAG | BILLING VALUE ($) | BILLING VALUE (Rs.) | DISP. STATUS | DISP. MONTH | WEEKLY DISPATCH | DRG. REQ. | PENDING BOI ORDERING. | VENDOR | REMARKS | PAYMENT REQ. FEB | NATURE OF PAYMENT (MAR) | PAYMENT REQ. MAR | CATEGORY | DISPATCH MONTH NAME
2605-PROMPT-CCL |  | ADITYA SHARMA | RECOILER ASSY#1 |  |  | 9000000 | Not Disp. | 2027-04-28 |  | TRUE | [6 empty] | CCL | Apr 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | EXIT PINCH CUM DEFLECTOR ROLL ASSY. |  |  | 1000000 | Not Disp. | 2027-04-28 |  | TRUE | [6 empty] | CCL | Apr 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | DOUBLE DECKER DEFLECTOR ROLL ASSY.#1 |  |  | 1000000 | Not Disp. | 2027-04-28 |  | TRUE | [6 empty] | CCL | Apr 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY. |  |  | 1000000 | Not Disp. | 2027-04-28 |  | TRUE | [6 empty] | CCL | Apr 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | SINGLE STEERING ROLL ASSY. |  |  | 1000000 | Not Disp. | 2027-04-28 |  | TRUE | [6 empty] | CCL | Apr 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | SINGLE STEERING ROLL ASSY.(BEFORE FINISH COATER) |  |  | 1000000 | Not Disp. | 2027-04-28 |  | TRUE | [6 empty] | CCL | Apr 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | PRIME SQUEEZE ROLL CUM STEERING ASSY. |  |  | 1000000 | Not Disp. | 2027-04-28 |  | TRUE | [6 empty] | CCL | Apr 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | FINISH SQUEEZE ROLL CUM STEERING ASSY. |  |  | 1000000 | Not Disp. | 2027-04-28 |  | TRUE | [6 empty] | CCL | Apr 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | SINGLE SQUEEZE ROLL ASSY. |  |  | 1000000 | Not Disp. | 2027-04-28 |  | TRUE | [6 empty] | CCL | Apr 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | DOUBLE SQUEEZE ROLL ASSY. |  |  | 1000000 | Not Disp. | 2027-04-28 |  | TRUE | [6 empty] | CCL | Apr 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSEMBLY |  |  | 1000000 | Not Disp. | 2027-04-28 |  | TRUE | [6 empty] | CCL | Apr 2027
2530-AL SHAKER-CGL |  | SAURABH | RECOILER ASSY |  |  | 9500000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | SEAM WELDER ASSY. |  |  | 12500000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | CGL | Mar 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | TENSION LEVELLER (TLL) |  |  | 15000000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | CGL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Stand #4, Work Roll, IMR Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5, Work Roll, IMR Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6 Entry; Deflector Roll (Stressometer Roll Existing) |  |  | 3000000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6, Entry, Snubber Roll #10 |  |  | 1000000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #6 - Mill Stand #6, Roll Coolant Headers, Entry Side (Selectospray) |  |  | 2500000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Housings |  |  | 17500000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Bed Plates |  |  | 3500000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #6 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #6 - Back Up Rolls Bearings |  |  | 6000000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - IMR Rolls Chocks |  |  | 2500000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #6 - IMR Rolls |  |  | 2000000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #6 - IMR Roll, Bearings |  |  | 1200000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #6 - Work Rolls |  |  | 2000000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #6 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #6 - Cobble guard |  |  | 3000000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #6 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Gear Reduction |  |  | 2500000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #6 - Gear Spindle |  |  | 8000000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #6 - Spindle Support |  |  | 1000000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6, Work Roll, IMR Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6 Exit, Snubber Roll #11 |  |  | 1000000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6 Exit, Tensiometer Roll |  |  | 2500000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6 Exit, Air Knife & Air Wiper |  |  | 1000000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6, Thickness Gauge Protection Housing |  |  | 7500000 | Not Disp. | 2027-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6, Delivery Deflector Roll (Stressometer Roll Existing) |  |  | 3000000 | Not Disp. | 2027-03-28 |  | FALSE | TRUE | [5 empty] | APL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | UNCOILER ASSY#1 |  |  | 7000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | UNCOILER ASSY#2 |  |  | 7000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | BELT WRAPPER ASSY. |  |  | 1500000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | SLEEVE LOADER ASSY. |  |  | 1000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | PASSING TABLE ASSY#1 |  |  | 500000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | PASSING TABLE ASSY#2 |  |  | 500000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | PASSING TABLE ASSY#3 |  |  | 500000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | PASSING TABLE ASSY#4 |  |  | 500000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | STITCHER ASSY. |  |  | 7000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#4 |  |  | 4000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#5 |  |  | 4000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#6 |  |  | 4000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | ENTRY ACCUMULATOR STRUCTURE |  |  | 4000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | ENTRY ACCUMULATOR COUNTER WEIGHT ASSEMBLY |  |  | 5000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI | ADITYA SHARMA | ENTRY ACCUMULATOR CHAIN |  |  | 4000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | EXIT ACCUMULATOR STRUCTURE |  |  | 7000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | EXIT ACCUMULATOR COUNTER WEIGHT ASSEMBLY |  |  | 5000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI | ADITYA SHARMA | EXIT ACCUMULATOR CHAIN |  |  | 3000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | DOUBLE DECKER SHEAR ASSY. |  |  | 1000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | EXIT SHEAR ASSY. |  |  | 1000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | DEGREASING TANK ASSY#1 |  |  | 6000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | DEGREASING TANK ASSY#2 |  |  | 6000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | BRUSHING TANK ASSY.#1 |  |  | 6000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | BRUSH ROLL CHOCK ASSEMBLY |  |  | 3000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | BRUSH ROLL ASSEMBLY |  |  | 1000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | BACKUP ROLL CHOCK ASSEMBLY |  |  | 9000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | DRIVE ASSEMBLY |  |  | 1000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | BRUSHING TANK ASSY #2 |  |  | 6000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | HOT RINSING TANK ASSY#1 |  |  | 6000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | HOT RINSING TANK ASSY#2 |  |  | 6000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | HOLDING TANK |  |  | 6000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | PRIME QUENCHING TANK ASSY. |  |  | 6000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | FINISH QUENCHING TANK PIPING ASSY. |  |  | 6000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI | ADITYA SHARMA | FUME EXHAUST DUCTING |  |  | 3000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | HOT AIR DRYER ASSEMBLY |  |  | 1500000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | CHEMICAL DRYER ASSEMBLY |  |  | 1500000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | COLD AIR DRYER ASSEMBLY |  |  | 1500000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | FINISH COATER 'A' ASSY. |  |  | 5000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | FINISH COATER 'B' ASSY. |  |  | 5000000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | COATER ROOM |  |  | 1500000 | Not Disp. | 2027-03-28 |  | TRUE | [6 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | FINSH OVEN |  |  | 5000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | CPC |  |  | 6000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | EPC |  |  | 1000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | HYDRAULIC POWERPACK |  |  | 9000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | RTO |  |  | 30000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | TENSION LEVELLER (TLL) |  |  | 14000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2605-PROMPT-CCL | BOI | ADITYA SHARMA | CHEMICAL HANDLING SYSTEM |  |  | 3000000 | Not Disp. | 2027-03-28 |  | TRUE | TRUE | [5 empty] | CCL | Mar 2027
2513-GAURANG-SLITTING |  | OM DEV | RECOILER MANDREL ASSY. |  |  | 2500000 | Not Disp. | 2027-02-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Feb 2027
2513-GAURANG-SLITTING | BOI-LL | OM DEV | SLITTER HEAD ASSY |  |  | 2000000 | Not Disp. | 2027-02-28 |  | TRUE | TRUE | [5 empty] | SLITTING | Feb 2027
2513-GAURANG-SLITTING | BOI-LL | OM DEV | HYD. POWER PACK & VALVE STAND |  |  | 3000000 | Not Disp. | 2027-02-28 |  | TRUE | TRUE | [5 empty] | SLITTING | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | PIT COVER@ RECOILER |  |  | 200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | UNCOILER ASSY#1 |  |  | 8000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | UNCOILER ASSY#2 |  |  | 8000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | RECOILER BELT WRAPPPER ASSY. |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | RECOILER SLEEVE LOADER ASSY. |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | BRIDLE ROLL ASSY.#6 |  |  | 4500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | BRIDLE ROLL ASSY.#7 |  |  | 4500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | BRIDLE ROLL ASSY.#8 |  |  | 4500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | BRIDLE ROLL ASSY.#9 |  |  | 4500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | BRIDLE ROLL ASSY.#10 |  |  | 4500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | LOGO MARKER ASSY |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | EPC SENSOR ASSY. |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | CPC SENSOR ASSY. |  |  | 7000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | STRIP HEATER COOLING PENDANTS |  |  | 1500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | HYDRAULIC POWERPACK |  |  | 9000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | Static Section Assembly |  |  | 3200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | JCF Assembly |  |  | 4600000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Ducting Assembly |  |  | 700000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL |  | SAURABH | Calm Zone Assembly |  |  | 3800000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Pot cellar Ventilation Supply Ducting |  |  | 400000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Pot cellar Ventilation Exhaust Ducting |  |  | 400000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Moving Pendant assembly |  |  | 2000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Moving Trolley |  |  | 3000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Up Pass Pendant-1 |  |  | 1200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Cooling pendant assembly-Slot |  |  | 0 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Up Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Up Pass Pendant-3 |  |  | 1200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Down Pass Pendant-1 |  |  | 1200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Down Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Non-Ox Burners |  |  | 2000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Radiant Tube Burner With Recuperator |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Post Combustion Burner |  |  | 2000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Ignition Cable |  |  | 200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Ratio Regulators |  |  | 200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | UV Sensors |  |  | 200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | UV Flame Switches |  |  | 200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Ignition Transformers |  |  | 500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | JCF Heat Exchanger |  |  | 2000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Flow Switchs |  |  | 200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Premelt and Main Pot |  |  | 0 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Thermocouple |  |  | 200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Temperature Transmitters |  |  | 600000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Compensating Cable |  |  | 200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | IR Pyrometers |  |  | 400000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Pressure Transmitters |  |  | 600000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Solenoid Shut-Off Valves |  |  | 400000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | H2 analyzer |  |  | 500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Dew Point Analyzer |  |  | 500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | O2 Analyzer |  |  | 500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Electric Heater |  |  | 3000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Glow Heater |  |  | 100000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Pressure Gauges |  |  | 100000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Orifice Plates |  |  | 1200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Rotameters |  |  | 100000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Pneumatic Shut-Off Valves |  |  | 1200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Hot Air Control Valve |  |  | 1400000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Adjustable Gas control valves |  |  | 400000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Fan |  |  | 1500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Radiant Tubes |  |  | 1500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Air knife Blower |  |  | 6000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Recuperator For Non-OX Furnace |  |  | 3000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Gearmotor |  |  | 500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | HNX Gas Station & Heater |  |  | 1500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | JCF Fan |  |  | 5300000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Furnace Bellows |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Hearth Roll Bearing |  |  | 500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Butterfly Valve |  |  | 700000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Ball Valve |  |  | 700000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Gate Valve |  |  | 700000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Globe Valve |  |  | 700000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Flow Control Valve |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Check Valve |  |  | 700000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Main gas station |  |  | 1200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | Air knife ,Zinc Pump,Drosser |  |  | 10600000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | Pot Equipment |  |  | 38000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Propeller Shaft |  |  | 500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Couplings |  |  | 500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Entry Accumulator |  |  | 30000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Stand #1, Work Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Stand #2, Work Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Stand #3, Work Roll, IMR Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Stand #4 Exit, Snubber Roll #7 |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Stand #4 & #5, Interstrand Tensiometer Roll |  |  | 2500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Stand #4 Exit, Air Wiper |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5 Entry; Deflector Roll Assembly with Encoder |  |  | 3000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5, Entry, Snubber Roll #8 |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Mill Stand #5, Roll Coolant Headers, Entry Side (Selectospray) |  |  | 2500000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Housings |  |  | 17500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Bed Plates |  |  | 3500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Back Up Rolls Bearings |  |  | 6000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - IMR Rolls Chocks |  |  | 2500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - IMR Rolls |  |  | 2000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - IMR Roll, Bearings |  |  | 1200000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Work Rolls |  |  | 2000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Cobble guard |  |  | 3000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Gear Reduction |  |  | 2500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Gear Spindle |  |  | 8000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Spindle Support |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5 Exit, Snubber Roll #9 |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5 & #6, Interstrand Tensiometer Roll |  |  | 2500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5 Exit, Air Wiper |  |  | 1000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5, Thickness Gauge Protection Housing |  |  | 7500000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Delivery Flying Shearing Machine |  |  | 22500000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND |  | MAYANK | Delivery Carousel type Tension Reel, Pusher plate & OBBS |  |  | 20000000 | Not Disp. | 2027-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Cellar Ventilation System |  |  | 7500000 | Not Disp. | 2027-02-28 |  | FALSE | TRUE | [5 empty] | APL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | PEELER TABLE ASSY.#1 |  |  | 500000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | PEELER TABLE ASSY.#2 |  |  | 500000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | SCRAP DOWN TABLE ASSY#1 |  |  | 500000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | SCRAP DOWN TABLE ASSY#2 |  |  | 500000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | SCRAP TROLLEY ASSY. |  |  | 500000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | EXIT THREADING TABLE ASSY. |  |  | 500000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#1 |  |  | 4000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#2 |  |  | 4000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#3 |  |  | 4000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | ENTRY ACCUMULATOR FIXED FRAME |  |  | 7000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | ENTRY ACCUMULATOR MOVING FRAME |  |  | 5000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | ENTRY ACCUMULATOR TOP FRAME |  |  | 7000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | EXIT ACCUMULATOR FIXED FRAME |  |  | 5000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | EXIT ACCUMULATOR MOVING FRAME |  |  | 7000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | EXIT ACCUMULATOR TOP FRAME |  |  | 5000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | ENTRY PINCH ROLL ASSY.#1 |  |  | 800000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | ENTRY PINCH ROLL ASSY.#4 |  |  | 800000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | DEBURRING ROLL ASSY. |  |  | 1000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | EXIT PINCH ROLL ASSY. |  |  | 1000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | CHEMICAL COATER ASSY. |  |  | 5000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | PRIME COATER ASSY. |  |  | 5000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL | BOI-LL | ADITYA SHARMA | PRIME OVEN |  |  | 5000000 | Not Disp. | 2027-02-28 |  | TRUE | TRUE | [5 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | OVEN STRUCTURE |  |  | 4000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | CHEMICAL COATER STRUCTURE |  |  | 3000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL | BOI | ADITYA SHARMA | FOUNDATION BOLT |  |  | 1500000 | Not Disp. | 2027-02-28 |  | TRUE | TRUE | [5 empty] | CCL | Feb 2027
2605-PROMPT-CCL | BOI | ADITYA SHARMA | TAPER PLATE |  |  | 500000 | Not Disp. | 2027-02-28 |  | TRUE | TRUE | [5 empty] | CCL | Feb 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | ELECTRICAL |  |  | 50000000 | Not Disp. | 2027-02-28 |  | TRUE | [6 empty] | CCL | Feb 2027
2605-PROMPT-CCL | BOI | ADITYA SHARMA | PULPIT |  |  | 1000000 | Not Disp. | 2027-02-28 |  | TRUE | TRUE | [5 empty] | CCL | Feb 2027
2510-GAURANG-PICKLING |  | KUSH | RECOILER ASSY. |  |  | 5500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jan 2027
2510-GAURANG-PICKLING | BOI-LL | KUSH | EPC |  |  | 4000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Jan 2027
2510-GAURANG-PICKLING | BOI-LL | KUSH | HYDRAULIC POWER PACK & VALVE STAND |  |  | 7500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | UNCOILER MANDREL ASSY. |  |  | 2000000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | PASSING TABLE ASSY. |  |  | 100000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | PINCH CUM DEFLECTOR ROLL ASSY |  |  | 300000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | DEBURRING ROLL ASSY. |  |  | 100000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | EXIT PINCH ROLL |  |  | 200000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING | BOI-LL | OM DEV | ENTRY SHEAR ASSY. |  |  | 500000 | Not Disp. | 2027-01-28 |  | TRUE | TRUE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING | BOI-LL | OM DEV | EXIT SHEAR ASSY. |  |  | 500000 | Not Disp. | 2027-01-28 |  | TRUE | TRUE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | INLINE SEPARATOR ASSY. |  |  | 500000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | OVER ARM SEPERATOR ASSY. |  |  | 500000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | SIDE GUIDE ASSY. |  |  | 250000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | SCRAP WINDER ASSY. |  |  | 200000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | SCRAP OSCILLATOR |  |  | 250000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | PRESSURE PAD ASSY.(EXIT) |  |  | 500000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2513-GAURANG-SLITTING |  | OM DEV | SUPPORT ROL |  |  | 500000 | Not Disp. | 2027-01-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | PASSING TABLE ASSY#6 (COOLING AFTER GALVANIZING) |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | PASSING TABLE ASSY#7 (STRIP HEATER ASSY.) |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | HOZ. INSPECTION TABLE (BEFORE EXIT PINCH ROLL ASSY.#1) |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | ENTRY SCRAP DOWN TABLE ASSY#1 |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | ENTRY SCRAP DOWN TABLE ASSY#2 |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | ENTRY SCRAP TRAY ASSY. |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | EXIT SCRAP DOWN TABLE ASSY. |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | SCRAP TROLLEY ASSY. (ENTRY & EXIT SECTION) |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | EXIT THREADING TABLE ASSY. |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | BRIDLE ROLL ASSY.#1 |  |  | 4500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | BRIDLE ROLL ASSY.#2 |  |  | 4500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | BRIDLE ROLL ASSY.#3 |  |  | 4500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | BRIDLE ROLL ASSY.#4 |  |  | 4500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | BRIDLE ROLL ASSY.#5 |  |  | 4500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | EXIT ACCUMULATOR ASSY. |  |  | 27500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | SINGLE STEERING ROLL ASSY. |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | DOUBLE STEERING ROLL ASSY. @ CAG |  |  | 2000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#1,2,3 |  |  | 1500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#4 |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | DEBURRING ROLL ASSY. |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | EXIT PINCH ROLL ASSY. |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | EXIT PINCH CUM DEFLECTOR ROLL ASSY. |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#1 (AFTER BRIDLE ROLL ASSY.#01) |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#2 (BEFORE & AFTER ENTRY ACC ASSY.) |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#3 (BEFORE BRIDLE ROLL ASY.#03) |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#4 (BEFORE COATING THK GAUGE) |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#5 (AFTER COATING THK GAUGE) |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#6 (AFTER BRIDLE ROLL ASSY.#08) |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#7 (CHEMICAL COATER) |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#8 (BEFORE BRIDLE ROLL ASY.#09) |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#9 (BEFORE LOGO MARKER) |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | SUPPORT ROLL ASSY. (ENTRY ACCUMULATOR ROLL ASSY.) |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | SINGLE SQUEEZE ROLL ASSY. |  |  | 2500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | VERTICAL SQUEEZE ROLL ASSY.@CAG |  |  | 3500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | BRUSHING ROLL ASSY.#01 |  |  | 700000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | BRUSHING ROLL ASSY.#02 |  |  | 700000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | DEGREASING TANK ASSY. |  |  | 4500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | BRUSHING TANK ASSY. |  |  | 4500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | HOT WATER RINSING TANK ASSY. |  |  | 4500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | QUENCHING TANK ASSY. |  |  | 4500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | WATER SPRAY UNIT |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | TENSIOMETER ASSY.#1 BEFORE FURNACE ENTRY |  |  | 700000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | TENSIOMETER ASSY.#2 AFTER CAG |  |  | 700000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | TURN UP ROLL ASSY. (@CAG & STRIP HEATER) |  |  | 700000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | TURN DOWN ROLL ASSY. (@CAG & STRIP HEATER) |  |  | 700000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | SKIN PASS MILL |  |  | 40000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | VERTICAL CHEMICAL COATER ASSY. |  |  | 5500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | HOT AIR DRYER ASSY.#1 @ CLEANING SECTION |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | COLD AIR DRYER @ CAG |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | HOT AIR DRYER ASSY.#2 @ SPM |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | LOGO DRYER @ LOGO MARKER |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | CAG STRUCTURE |  |  | 4000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | COATER STRUCTURE |  |  | 5000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#01 |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#02 |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#03 |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | DOUBLE DECKER ENTRY SHEAR ASSY. |  |  | 1500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | DELIVERY SHEAR ASSY. |  |  | 1500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI-LL | SAURABH | COATING THK GAUGE ASSY. |  |  | 8000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | STRIP INDUCTION HEATER ASSY. |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | FOUNDATION BOLT |  |  | 1500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | TAPER PLATE |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | PULPIT |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | Furnace Structure-Staircases |  |  | 1500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | Furnace Structure-Handrails |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | Furnace Structure-Chequered plates |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | CAG Structure-Staircases |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | CAG Structure-Handrails |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | CAG Structure-Chequered plates |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Threading Needle Assembly |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Furnace Exhaust Ducting |  |  | 1500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Furnace Gas and Combustion Air Piping |  |  | 1900000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Furnace Dilution Air Piping |  |  | 500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Furnace Interconnecting Piping |  |  | 2500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | Entry Seal Assembly |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | Throat Assembly |  |  | 3500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | RTF Assembly |  |  | 5900000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL |  | SAURABH | SF Assembly |  |  | 5100000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Heat Exchanger |  |  | 2000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2530-AL SHAKER-CGL | BOI | SAURABH | Down Chute |  |  | 1500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Stand #4, Work Roll, IMR Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5, Work Roll, IMR Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6 Entry; Deflector Roll (Stressometer Roll Existing) |  |  | 3000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6, Entry, Snubber Roll #10 |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6, Roll Coolant Headers, Entry Side (Selectospray) |  |  | 2500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Housings |  |  | 17500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Bed Plates |  |  | 3500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Back Up Rolls Bearings |  |  | 6000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - IMR Rolls Chocks |  |  | 2500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - IMR Rolls |  |  | 2000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - IMR Roll, Bearings |  |  | 1200000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Work Rolls |  |  | 2000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Cobble guard |  |  | 3000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Gear Reduction |  |  | 2500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Gear Spindle |  |  | 8000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Spindle Support |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6, Work Roll, IMR Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6 Exit, Snubber Roll #11 |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6 Exit, Tensiometer Roll |  |  | 2500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6 Exit, Air Knife & Air Wiper |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6, Thickness Gauge Protection Housing |  |  | 7500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2517-APL-6 STAND |  | MAYANK | Mill Stand #6 - Mill Stand #6, Delivery Deflector Roll (Stressometer Roll Existing) |  |  | 3000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Stand #4 Entry; Deflector Roll Assembly with Encoder |  |  | 3000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Stand #4, Entry, Snubber Roll #6 |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Mill Stand #4, Roll Coolant Headers, Entry Side |  |  | 2500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Housings |  |  | 17500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Bed Plates |  |  | 3500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Back Up Rolls Bearings |  |  | 6000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - IMR Rolls Chocks |  |  | 2500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - IMR Rolls |  |  | 2000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - IMR Roll, Bearings |  |  | 1200000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Work Rolls |  |  | 2000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Cobble guard |  |  | 3000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Gear Reduction |  |  | 2500000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND |  | MAYANK | Mill Stand #4 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Gear Spindle |  |  | 8000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Spindle Support |  |  | 1000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Motors |  |  | 110000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Hydraulic System |  |  | 60000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI-LL | MAYANK | Pneumatic System |  |  |  | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | APL | Jan 2027
2537-APL-6 STAND | BOI | MAYANK | PipeS & Fittings |  |  | 15000000 | Not Disp. | 2027-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2027
2611-APL-CGL | BOI | SAURABH | POT CELLAR VENTILATION |  |  | 3000000 | Not Disp. | 2027-01-28 |  | FALSE | [6 empty] | CGL | Jan 2027
2611-APL-CGL | BOI-LL | SAURABH | TENSION LEVELLER (TLL) |  |  | 14000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2611-APL-CGL |  | SAURABH | Calm Zone Assembly |  |  | 3800000 | Not Disp. | 2027-01-28 |  | FALSE | [6 empty] | CGL | Jan 2027
2611-APL-CGL | BOI-LL | SAURABH | Air knife ,Zinc Pump,Drosser |  |  | 10600000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2611-APL-CGL | BOI-LL | SAURABH | Pot Equipment |  |  | 55000000 | Not Disp. | 2027-01-28 |  | FALSE | TRUE | [5 empty] | CGL | Jan 2027
2605-PROMPT-CCL | BOI | ADITYA SHARMA | UNCOILER COIL CAR ASSY. |  |  | 3000000 | Not Disp. | 2027-01-28 |  | TRUE | TRUE | [5 empty] | CCL | Jan 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | UNCOILER DRAG CHAIN ASSY. |  |  | 500000 | Not Disp. | 2027-01-28 |  | TRUE | [6 empty] | CCL | Jan 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | UNCOILER COIL SADDLE ASSY. |  |  | 500000 | Not Disp. | 2027-01-28 |  | TRUE | [6 empty] | CCL | Jan 2027
2605-PROMPT-CCL | BOI | ADITYA SHARMA | RECOILER COIL CAR ASSY. |  |  | 1500000 | Not Disp. | 2027-01-28 |  | TRUE | TRUE | [5 empty] | CCL | Jan 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | RECOILER DRAG CHAIN ASSY. |  |  | 300000 | Not Disp. | 2027-01-28 |  | TRUE | [6 empty] | CCL | Jan 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | RECOILER COIL SADDLE ASSY. |  |  | 300000 | Not Disp. | 2027-01-28 |  | TRUE | [6 empty] | CCL | Jan 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | UNCOILER #1 OBBS ASSY |  |  | 500000 | Not Disp. | 2027-01-28 |  | TRUE | [6 empty] | CCL | Jan 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | UNCOILER #2 OBBS ASSY |  |  | 500000 | Not Disp. | 2027-01-28 |  | TRUE | [6 empty] | CCL | Jan 2027
2605-PROMPT-CCL |  | ADITYA SHARMA | RECOILER OBBS ASSY |  |  | 500000 | Not Disp. | 2027-01-28 |  | TRUE | [6 empty] | CCL | Jan 2027
2605-PROMPT-CCL | BOI | ADITYA SHARMA | PIPES & FITTINGS |  |  | 3000000 | Not Disp. | 2027-01-28 |  | TRUE | TRUE | [5 empty] | CCL | Jan 2027
2510-GAURANG-PICKLING |  | KUSH | STEP TYPE UNCOILER ASSY. |  |  | 4000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | HOLD DOWN ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | PASSING TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | PASSING TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | PASSING TABLE ASSY.#3 |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | PASSING TABLE ASSY.#4 |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | PASSING TABLE ASSY.#5 |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | PASSING TABLE ASSY.#6 |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | PASSING TABLE ASSY.#7 |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | PASSING TABLE ASSY.#8 |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | PASSING TABLE ASSY.#9 |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | PASSING TABLE ASSY.#10 |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING | BOI-LL | KUSH | ENTRY SHEAR |  |  | 1000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING | BOI-LL | KUSH | EXIT SHEAR |  |  | 1000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | DOUBLE SQUEEZE ROLL ASSY. |  |  | 2000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | PINCH CUM LEVELLER ROLL ASSY. WITH FRAME |  |  | 800000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | BURR MASHER ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | TENSIONER ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING | BOI | KUSH | OIL SPRAYING ASSY. |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING | BOI | KUSH | AIR WIPER ASSY. |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | SUPPORT ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING | STRUCTURE | KUSH | STRUCTURE |  |  | 1000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2510-GAURANG-PICKLING | BOI | KUSH | HYDRAULIC & PNEUETIC FITTINGS |  |  | 1500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2026
2603-BMWIL-TRIMMING | BOI | KUNAL | UNCOILER-COIL CAR ASSEMBLY. |  |  | 750000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | UNCOILER-DRAG CHAIN ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | UNCOILER-COIL SADDLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | UNCOILER-PIT COVER |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING | BOI | KUNAL | RECOILER-COIL CAR ASSEMBLY. |  |  | 750000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | RECOILER-DRAG CHAIN ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | RECOILER-COIL SADDLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | RECOILER-PIT COVER |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | UNCOILER ASSEMBLY. |  |  | 3500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | ENTRY OBBS ASSEMBLY. |  |  | 250000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | RECOILER ASSEMBLY. |  |  | 4500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | OBBS ASSEMBLY. |  |  | 250000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | PINCH CUM DEFLECTOR ROLL ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | DEBURRING ROLL ASSEMBLY. |  |  | 1200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | EXIT PINCH CUM DEFLECTOR ROLL ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING | BOI-LL | KUNAL | SHEAR ASSY. |  |  | 900000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | SIDE GUIDE ASSEMBLY. |  |  | 1400000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | TENSIONER ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING | BOI-LL | KUNAL | TRIMMER HEAD ASSEMBLY. |  |  | 2500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | SCRAP BAILER ASSEMBLY. |  |  | 700000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | PEELER TABLE ASSEMBLY. |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | SCRAP DOWN TABLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE & SUIT ASSEMBLY. |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | THREADING TABLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | SCRAP TROLLEY ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#1 |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#2 |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#3 |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#4 |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#5 |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#6 |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING | BOI-LL | KUNAL | CPC |  |  | 700000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING | BOI-LL | KUNAL | EPC |  |  | 700000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING | BOI | KUNAL | FOUNDATION BOLTS |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING | BOI | KUNAL | TAPER (LEVELLING) PLATE |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING | BOI | KUNAL | INTERCONNECTING PIPING |  |  | 1000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING | BOI-LL | KUNAL | HYDRAULIC SYSTEM |  |  | 3500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2603-BMWIL-TRIMMING | ELECTRICAL | KUNAL | ELECTRICAL |  |  | 4000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2026
2513-GAURANG-SLITTING |  | OM DEV | ENTRY OBBS ASSY |  |  | 100000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2513-GAURANG-SLITTING |  | OM DEV | EXIT OBBS ASSY |  |  | 100000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2513-GAURANG-SLITTING |  | OM DEV | HOLD DOWN ROLL ASSY. |  |  | 200000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2513-GAURANG-SLITTING |  | OM DEV | PEELER TABLE ASSY. |  |  | 100000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2513-GAURANG-SLITTING |  | OM DEV | THREADING TABLE ASSY. |  |  | 100000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2513-GAURANG-SLITTING |  | OM DEV | LOOPER TABLE #1 |  |  | 100000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2513-GAURANG-SLITTING |  | OM DEV | LOOPER TABLE #2 |  |  | 100000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2513-GAURANG-SLITTING |  | OM DEV | LOOPER TABLE #3 |  |  | 100000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2513-GAURANG-SLITTING | BOI | OM DEV | FOUNDATION BOLTS |  |  | 500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2513-GAURANG-SLITTING | BOI | OM DEV | TAPER & FLAT PLATES |  |  | 500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2513-GAURANG-SLITTING | BOI | OM DEV | HYDRAULIC PIPE & FITTINGS |  |  | 500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2513-GAURANG-SLITTING | ELECTRICAL | OM DEV | ELECTRICAL |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | UNCOILER OBBS ASSY. #1 |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | UNCOILER OBBS ASSY. #2 |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | RECOILER EXIT OBBS ASSY. |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | PEELER TABLE ASSY.#1 |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | PEELER TABLE ASSY.#2 |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | PASSING TABLE ASSY#1 (D.D. SHEAR & PINCH ROLL#1) |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | PASSING TABLE ASSY#2 (PINCH ROLL#2 & D.D. SHEAR) |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | PASSING TABLE ASSY#3 (PINCH ROLL#3 & PINCH ROLL#4) |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | PASSING TABLE ASSY#4 (PINCH ROLL#4 & SEAM WELDER) |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | PASSING TABLE ASSY#5 (BEFORE ENTRY FURNACE) |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | ENTRY ACCUMULATOR ASSY. |  |  | 27500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL | ELECTRICAL | SAURABH | ELECTRICAL |  |  | 40000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | Furnace Structure - Columns |  |  | 10000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | Furnace Structure-Beams |  |  | 5000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | Furnace Structure-Bracings |  |  | 2500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | CAG Structure - Columns |  |  | 2500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | CAG Structure-Beams |  |  | 1500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL | STRUCTURE | SAURABH | CAG Structure-Bracings |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | Tunnel Assembly |  |  | 7000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | DFF Assembly |  |  | 7700000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2530-AL SHAKER-CGL |  | SAURABH | HBR Assembly |  |  | 10000000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Horizontal Accumulator |  |  | 30000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Stand #1, Work Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Stand #2, Work Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Stand #3, Work Roll, IMR Roll & Backup Roll Change Trolley |  |  | 5000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Stand #4 Exit, Snubber Roll #7 |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Stand #4 & #5, Interstrand Tensiometer Roll |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Mill Stand #4 Exit, Air Wiper |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5 Entry; Deflector Roll Assembly with Encoder |  |  | 3000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5, Entry, Snubber Roll #8 |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Mill Stand #5, Roll Coolant Headers, Entry Side (Selectospray) |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Housings |  |  | 17500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Bed Plates |  |  | 3500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Back Up Rolls Bearings |  |  | 6000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - IMR Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - IMR Rolls |  |  | 2000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - IMR Roll, Bearings |  |  | 1200000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Work Rolls |  |  | 2000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Cobble guard |  |  | 3000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Gear Reduction |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #5 - Gear Spindle |  |  | 8000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Spindle Support |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5 Exit, Snubber Roll #9 |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5 & #6, Interstrand Tensiometer Roll |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5 Exit, Air Wiper |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #5 - Mill Stand #5, Thickness Gauge Protection Housing |  |  | 7500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Delivery Flying Shearing Machine |  |  | 22500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND |  | MAYANK | Delivery Carousel type Tension Reel, Pusher plate & OBBS |  |  | 20000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Cellar Ventilation System |  |  | 7500000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 Entry; Deflector Roll Assembly with Encoder |  |  | 3000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1, Air Wiper, Entry Side |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1, Pressure Pad with Side Guide, Entry Side |  |  | 1600000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1, Roll Coolant Headers, Entry Side |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Stand #1-Mill Housings |  |  | 17500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Stand #1- Bed Plates |  |  | 3500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Gear Reduction |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Gear Spindle |  |  | 8000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Spindle Support |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Stand #1 Exit, Snubber Roll #1 |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Stand #1 & #2, Interstrand Tensiometer Roll |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Mill Stand #1 Exit, Air Wiper |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Stand #2 Entry; Deflector Roll Assembly with Encoder |  |  | 3000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Stand #2 Entry, Snubber Roll #2 |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Mill Stand #2, Roll Coolant Headers, Entry Side |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Housings |  |  | 17500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Bed Plates |  |  | 3500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Gear Reduction |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Gear Spindle |  |  | 8000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Spindle Support |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Stand #2 Exit, Snubber Roll #3 |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Stand #2 & #3, Interstrand Tensiometer Roll |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Mill Stand #2 Exit, Air Wiper |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Stand #3 Entry; Deflector Roll Assembly with Encoder |  |  | 3000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Stand #3, Entry, Snubber Roll #4 |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Mill Stand #3, Roll Coolant Headers, Entry Side |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Housings |  |  | 17500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Bed Plates |  |  | 3500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2026-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Back Up Rolls Bearings |  |  | 6000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - IMR Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - IMR Rolls |  |  | 2000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - IMR Roll, Bearings |  |  | 1200000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Work Rolls |  |  | 2000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Cobble guard |  |  | 3000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Gear Reduction |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Gear Spindle |  |  | 8000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Mill Stand #3 - Spindle Support |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Mill Stand #3 Exit, Snubber Roll #5 |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Mill Stand #3 & #4, Interstrand Tensiometer Roll |  |  | 2500000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Mill Stand #3 Exit, Air Wiper |  |  | 1000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND |  | MAYANK | Belt Wrapper |  |  | 5500000 | Not Disp. | 2026-12-28 |  | TRUE | FALSE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Gear Box Lubrication System |  |  | 5000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Air-Oil Lubrication System |  |  | 30000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Roll Coolant System |  |  | 47500000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | COOLANT SYSTEM |  |  |  |  | APL | Dec 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Fume Exhaust System |  |  | 20000000 | Not Disp. | 2026-12-28 |  | TRUE | TRUE | [5 empty] | APL | Dec 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | POT CELLAR VENTILATION |  |  | 3000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | TENSION LEVELLER (TLL) |  |  | 16000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | CGL | Dec 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | Calm Zone Assembly |  |  | 3800000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | Air knife ,Zinc Pump,Drosser |  |  | 21200000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | CGL | Dec 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | Pot Equipment |  |  | 90000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | CGL | Dec 2026
2611-APL-CGL |  | SAURABH | RECOILER ASSY. |  |  | 8500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI-LL | SAURABH | EPC SENSOR ASSY.@ RECOILER |  |  | 8000000 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | CGL | Dec 2026
2611-APL-CGL | BOI-LL | SAURABH | CPC SENSOR ASSY.@ STEERING ASSY. |  |  | 0 | Not Disp. | 2026-12-28 |  | FALSE | TRUE | [5 empty] | CGL | Dec 2026
2611-APL-CGL |  | SAURABH | BASE FRAME CPC SENSOR ASSY. |  |  | 0 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL |  | SAURABH | SKIN PASS MILL |  |  | 35000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Furnace Exhaust Ducting |  |  | 1500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Furnace Gas and Combustion Air Piping |  |  | 1900000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Furnace Dilution Air Piping |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Furnace Interconnecting Piping |  |  | 2500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL |  | SAURABH | Throat Assembly |  |  | 3500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL |  | SAURABH | SF Assembly |  |  | 5100000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL |  | SAURABH | Static Section Assembly |  |  | 3200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL |  | SAURABH | JCF Assembly |  |  | 4600000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Ducting Assembly |  |  | 700000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Heat Exchanger |  |  | 2000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Down Chute |  |  | 1500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Pot cellar Ventilation Supply Ducting |  |  | 400000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Pot cellar Ventilation Exhaust Ducting |  |  | 400000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Moving Pendant assembly |  |  | 2000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Moving Trolley |  |  | 3000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Up Pass Pendant-1 (Future) |  |  | 1200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Cooling pendant assembly-Slot (Future) |  |  | 0 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Up Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Up Pass Pendant-3 |  |  | 1200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Down Pass Pendant-1 |  |  | 1200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Down Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Non-Ox Burners |  |  | 2000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Radiant Tube Burner With Recuperator |  |  | 1000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Post Combustion Burner |  |  | 2000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Ignition Cable |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Ratio Regulators |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | UV Sensors |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | UV Flame Switches |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Ignition Transformers |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | JCF Heat Exchanger |  |  | 2000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Flow Switchs |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Thermocouple |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Temperature Transmitters |  |  | 600000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Compensating Cable |  |  | 200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | IR Pyrometers |  |  | 400000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Pressure Transmitters |  |  | 600000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Solenoid Shut-Off Valves |  |  | 400000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | H2 analyzer |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Dew Point Analyzer |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | O2 Analyzer |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Electric Heater |  |  | 3000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Glow Heater |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Pressure Gauges |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Orifice Plates |  |  | 1200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Rotameters |  |  | 100000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Pneumatic Shut-Off Valves |  |  | 1200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Hot Air Control Valve |  |  | 1400000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Adjustable Gas control valves |  |  | 400000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Fan |  |  | 1500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Radiant Tubes |  |  | 1500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Air knife Blower |  |  | 6000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Recuperator For Non-OX Furnace |  |  | 3000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Gearmotor |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | HNX Gas Station & Heater |  |  | 1500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | JCF Fan |  |  | 5300000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Furnace Bellows |  |  | 1000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Hearth Roll Bearing |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Butterfly Valve |  |  | 700000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Ball Valve |  |  | 700000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Gate Valve |  |  | 700000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Globe Valve |  |  | 700000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Flow Control Valve |  |  | 1000000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Check Valve |  |  | 700000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Main gas station |  |  | 1200000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Propeller Shaft |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2611-APL-CGL | BOI | SAURABH | Couplings |  |  | 500000 | Not Disp. | 2026-12-28 |  | FALSE | [6 empty] | CGL | Dec 2026
2510-GAURANG-PICKLING |  | KUSH | O.B.B.S ASSY. |  |  | 250000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING |  | KUSH | PEELER TABLE ASSY. |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING |  | KUSH | EXIT THREADING TABLE |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING |  | KUSH | EXIT PINCH CUM DEFLECTOR ROLL ASSY. |  |  | 1000000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING |  | KUSH | SINGLE SQUEEZE ROLL ASSY. |  |  | 4000000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING |  | KUSH | ENTRY SIDE GUIDE ASSY. WITH FRAME |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING |  | KUSH | EXIT SIDE GUIDE ASSY. WITH FRAME |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING | BOI-LL | KUSH | HOT AIR DRYER ASSY |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING | BOI | KUSH | FOUNDATION BOLTS |  |  | 1000000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING | BOI | KUSH | TAPER (LEVELLING) PLATE |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING | ELECTRICAL | KUSH | ELECTRICAL |  |  | 7000000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING | BOI-LL | KUSH | PRE WASH TANK |  |  | 2500000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING | BOI-LL | KUSH | PICKLING TANK 1,2 & 3 |  |  | 7500000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING | BOI-LL | KUSH | ACID RECIRCULATION SYSTEM |  |  | 7500000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING | BOI-LL | KUSH | FIVE STAGE RINSING TANK WITH RECIRCULATION SYSTEM |  |  | 3000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING | BOI-LL | KUSH | FUME EXHAUST AND SCRUBBING SYSTEM FOR ACID |  |  | 5000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Nov 2026
2510-GAURANG-PICKLING | BOI-LL | KUSH | FUME EXHAUST AND SCRUBBING SYSTEM FOR RINSING |  |  | 2500000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Nov 2026
2519-APL-CGL |  | ADITYA SHARMA | RECOILER ASSY |  |  | 9500000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | SEAM WELDER ASSY. |  |  | 12500000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | CGL | Nov 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | TENSION LEVELLER (TLL) |  |  | 15000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | CGL | Nov 2026
2512-GAURANG-TRIMMING |  | KUNAL | RECOILER ASSY. |  |  | 2500000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Nov 2026
2512-GAURANG-TRIMMING | BOI-LL | KUNAL | HYD. POWER PACK & VALVE STAND |  |  | 3000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | TRIMMING | Nov 2026
2513-GAURANG-SLITTING | BOI | OM DEV | UNCOILER-COIL CAR ASSY. |  |  | 500000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Nov 2026
2513-GAURANG-SLITTING |  | OM DEV | UNCOILER-DRAG CHAIN ASSY. |  |  | 50000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Nov 2026
2513-GAURANG-SLITTING |  | OM DEV | UNCOILER-SADDLE ASSY. |  |  | 50000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Nov 2026
2513-GAURANG-SLITTING | BOI | OM DEV | RECOILER-COIL CAR ASSY. |  |  | 500000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Nov 2026
2513-GAURANG-SLITTING |  | OM DEV | RECOILER-DRAG CHAIN ASSY. |  |  | 50000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Nov 2026
2513-GAURANG-SLITTING |  | OM DEV | RECOILER-SADDLE ASSY. |  |  | 50000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Nov 2026
2520-APL-CCL |  | SAURABH | RECOILER ASSY#1 |  |  | 9500000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | CCL | Nov 2026
2520-APL-CCL | BOI-LL | SAURABH | STITCHER ASSY. |  |  | 10000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | CCL | Nov 2026
2530-AL SHAKER-CGL | BOI | SAURABH | COIL CAR ASSY. @ UNCOILER |  |  | 2000000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2026
2530-AL SHAKER-CGL |  | SAURABH | DRAG CHAIN ASSY. @ UNCOILER |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2026
2530-AL SHAKER-CGL |  | SAURABH | COIL SADDLE ASSY. @ UNCOILER |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2026
2530-AL SHAKER-CGL | BOI | SAURABH | COIL CAR ASSY. @ RECOILER |  |  | 1000000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2026
2530-AL SHAKER-CGL |  | SAURABH | DRAG CHAIN ASSY. @ RECOILER |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2026
2530-AL SHAKER-CGL |  | SAURABH | COIL SADDLE ASSY. @ RECOILER |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Stand #4 Entry; Deflector Roll Assembly with Encoder |  |  | 3000000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Stand #4, Entry, Snubber Roll #6 |  |  | 1000000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Mill Stand #4, Roll Coolant Headers, Entry Side |  |  | 2500000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Housings |  |  | 17500000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Bed Plates |  |  | 3500000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Back Up Rolls Bearings |  |  | 6000000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - IMR Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - IMR Rolls |  |  | 2000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - IMR Roll, Bearings |  |  | 1200000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Work Rolls |  |  | 2000000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Cobble guard |  |  | 3000000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Gear Reduction |  |  | 2500000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #4 - Gear Spindle |  |  | 8000000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #4 - Spindle Support |  |  | 1000000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Motors |  |  | 110000000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Hydraulic System |  |  | 60000000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Pneumatic System |  |  |  | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2517-APL-6 STAND | BOI | MAYANK | PipeS & Fittings |  |  | 15000000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Laser Welder |  |  | 220000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND |  | MAYANK | Tension Bridle Unit #1 |  |  | 6000000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND |  | MAYANK | Steering Unit #1 |  |  | 2000000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND |  | MAYANK | Steering Unit #2 |  |  | 2000000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND |  | MAYANK | Tension Bridle #2 |  |  | 6000000 | Not Disp. | 2026-11-28 |  | TRUE | TRUE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Back Up Rolls Bearings |  |  | 10500000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Work Rolls |  |  | 2000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND |  | MAYANK | Delivery Threading Table |  |  | 1000000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND | BOI | MAYANK | Delivery Coil Car & Coil Saddles |  |  | 2000000 | Not Disp. | 2026-11-28 |  | TRUE | FALSE | [5 empty] | APL | Nov 2026
2537-APL-6 STAND | ELECTRICAL | MAYANK | Electrical |  |  | 180000000 | Not Disp. | 2026-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | RECOILER ASSY. |  |  | 12000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#7 |  |  | 5000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#8 |  |  | 5000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#9 |  |  | 5000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | COATING THK GAUGE WITH SUPPORT ROLLS ASSY. |  |  | 6000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | EPC SENSOR ASSY.@ RECOILER |  |  | 8000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | CPC SENSOR ASSY.@ STEERING ASSY. |  |  | 0 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | BASE FRAME CPC SENSOR ASSY. |  |  | 0 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | HYDRAULIC SYSTEM-POWER PACK |  |  | 7500000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | HYDRAULIC SYSTEM-VALVE STAND |  |  | 7500000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | SKIN PASS MILL |  |  | 45000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Furnace Exhaust Ducting |  |  | 1500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Furnace Gas and Combustion Air Piping |  |  | 1900000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Furnace Dilution Air Piping |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Furnace Interconnecting Piping |  |  | 2500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | Throat Assembly |  |  | 3500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | SF Assembly |  |  | 5100000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | Static Section Assembly |  |  | 3200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | JCF Assembly |  |  | 9000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Ducting Assembly |  |  | 700000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Heat Exchanger |  |  | 2000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Down Chute |  |  | 1500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Pot cellar Ventilation Supply Ducting |  |  | 400000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Pot cellar Ventilation Exhaust Ducting |  |  | 400000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Moving Pendant assembly |  |  | 2000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Moving Trolley |  |  | 3000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Up Pass Pendant-1 (Future) |  |  | 1200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Cooling pendant assembly-Slot (Future) |  |  | 0 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Up Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Up Pass Pendant-3 |  |  | 1200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Down Pass Pendant-1 |  |  | 1200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Down Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Non-Ox Burners |  |  | 2000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Radiant Tube Burner With Recuperator |  |  | 1000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Post Combustion Burner |  |  | 2000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Ignition Cable |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Ratio Regulators |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | UV Sensors |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | UV Flame Switches |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Ignition Transformers |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | JCF Heat Exchanger |  |  | 2000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Flow Switchs |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Thermocouple |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Temperature Transmitters |  |  | 600000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Compensating Cable |  |  | 200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | IR Pyrometers |  |  | 400000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Pressure Transmitters |  |  | 600000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Solenoid Shut-Off Valves |  |  | 400000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | H2 analyzer |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Dew Point Analyzer |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | O2 Analyzer |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Electric Heater |  |  | 3000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Glow Heater |  |  | 100000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Pressure Gauges |  |  | 100000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Orifice Plates |  |  | 1200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Rotameters |  |  | 100000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Pneumatic Shut-Off Valves |  |  | 1200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Hot Air Control Valve |  |  | 1400000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Adjustable Gas control valves |  |  | 400000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Fan |  |  | 1500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Radiant Tubes |  |  | 1500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Air knife Blower |  |  | 6000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Recuperator For Non-OX Furnace |  |  | 3000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Gearmotor |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | HNX Gas Station & Heater |  |  | 1500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | JCF Fan |  |  | 5300000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Furnace Bellows |  |  | 1000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Hearth Roll Bearing |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Butterfly Valve |  |  | 700000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Ball Valve |  |  | 700000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Gate Valve |  |  | 700000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Globe Valve |  |  | 700000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Flow Control Valve |  |  | 1000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Check Valve |  |  | 700000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Main gas station |  |  | 1200000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Propeller Shaft |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Couplings |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | UNCOILER ASSY.#1 |  |  | 7000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | UNCOILER ASSY.#2 |  |  | 7000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#7 |  |  | 3500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#8 |  |  | 3500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#9 |  |  | 3500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | SUPPORT ROLL ASSY. |  |  | 3500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | TENSIOMETER ASSY.#1 BEFORE FURNACE |  |  | 1000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL | BOI | SAURABH | WATER QUENCHING TANK ASSY. |  |  | 2500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL | BOI | SAURABH | WATER SPRAY UNIT |  |  | 1500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | VERTICAL SQUEEZE ROLL ASSY.@CAG |  |  | 1000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL | BOI-LL | SAURABH | COATING THK GAUGE WITH SUPPORT ROLLS ASSY. |  |  | 6000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | VERTICAL CHEMICAL COATER ASSY. |  |  | 8000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | INDUCTION TYPE STRIP HEATER ASSY. |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL | STRUCTURE | SAURABH | COATER & STRIP HEATER STRUCTURE |  |  | 1000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL | BOI-LL | SAURABH | SEAM WELDER ASSY. |  |  | 11000000 | Not Disp. | 2026-11-28 |  | FALSE | TRUE | [5 empty] | CGL | Nov 2026
2611-APL-CGL | ELECTRICAL | SAURABH | ELECTRICAL |  |  | 40000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL | BOI | SAURABH | PULPIT |  |  | 500000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL | BOI | SAURABH | Threading Needle Assembly |  |  | 1000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | DFF Assembly |  |  | 5000000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2611-APL-CGL |  | SAURABH | RTF Assembly |  |  | 5900000 | Not Disp. | 2026-11-28 |  | FALSE | [6 empty] | CGL | Nov 2026
2510-GAURANG-PICKLING | BOI | KUSH | ENTRY COIL CAR ASSY. |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Oct 2026
2510-GAURANG-PICKLING |  | KUSH | ENTRY DRAG CHAIN ASSY. |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Oct 2026
2510-GAURANG-PICKLING |  | KUSH | ENTRY COIL SADDLE |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Oct 2026
2510-GAURANG-PICKLING | BOI | KUSH | EXIT COIL CAR ASSY. |  |  | 750000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Oct 2026
2510-GAURANG-PICKLING |  | KUSH | EXIT DRAG CHAIN ASSY |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Oct 2026
2510-GAURANG-PICKLING |  | KUSH | EXIT COIL SADDLE |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | PIT COVER@ RECOILER |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | UNCOILER ASSY#1 |  |  | 8000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | UNCOILER ASSY#2 |  |  | 8000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | RECOILER BELT WRAPPPER ASSY. |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | RECOILER SLEEVE LOADER ASSY. |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#6 |  |  | 5500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#7 |  |  | 5500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#8 |  |  | 5500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#9 |  |  | 5500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#10 |  |  | 5500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | LOGO MARKER ASSY |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | EPC SENSOR ASSY. |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | CPC SENSOR ASSY. |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | STRIP HEATER COOLING PENDANTS |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | HYDRAULIC POWERPACK |  |  | 9000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | Static Section Assembly |  |  | 3200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | JCF Assembly |  |  | 4600000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Ducting Assembly |  |  | 700000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL |  | ADITYA SHARMA | Calm Zone Assembly |  |  | 3800000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Pot cellar Ventilation Supply Ducting |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Pot cellar Ventilation Exhaust Ducting |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Moving Pendant assembly |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Moving Trolley |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Up Pass Pendant-1 |  |  | 1200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Cooling pendant assembly-Slot |  |  | 0 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Up Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Up Pass Pendant-3 |  |  | 1200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Down Pass Pendant-1 |  |  | 1200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Down Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Non-Ox Burners |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Radiant Tube Burner With Recuperator |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Post Combustion Burner |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Ignition Cable |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Ratio Regulators |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | UV Sensors |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | UV Flame Switches |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Ignition Transformers |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | JCF Heat Exchanger |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Flow Switchs |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | Premelt and Main Pot |  |  | 0 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Thermocouple |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Temperature Transmitters |  |  | 600000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Compensating Cable |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | IR Pyrometers |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Pressure Transmitters |  |  | 600000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Solenoid Shut-Off Valves |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | H2 analyzer |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Dew Point Analyzer |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | O2 Analyzer |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Electric Heater |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Glow Heater |  |  | 100000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Pressure Gauges |  |  | 100000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Orifice Plates |  |  | 1200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Rotameters |  |  | 100000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Pneumatic Shut-Off Valves |  |  | 1200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Hot Air Control Valve |  |  | 1400000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Adjustable Gas control valves |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Fan |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Radiant Tubes |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Air knife Blower |  |  | 6000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Recuperator For Non-OX Furnace |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Gearmotor |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | HNX Gas Station & Heater |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | JCF Fan |  |  | 5300000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Furnace Bellows |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Hearth Roll Bearing |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Butterfly Valve |  |  | 700000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Ball Valve |  |  | 700000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Gate Valve |  |  | 700000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Globe Valve |  |  | 700000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Flow Control Valve |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Check Valve |  |  | 700000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Main gas station |  |  | 1200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | Air knife ,Zinc Pump,Drosser |  |  | 10600000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | Pot Equipment |  |  | 68000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Propeller Shaft |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Couplings |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL CAR ASSY.#1 |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY DRAG CHAIN ASSY.#1 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL SADDLE#1 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL CAR ASSY.#2 |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY DRAG CHAIN ASSY.#2 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL SADDLE#2 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL CAR ASSY.#1 |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT DRAG CHAIN ASSY.#1 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL SADDLE #1 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL CAR ASSY.#2 |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT DRAG CHAIN ASSY.#2 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL SADDLE #2 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | STEP TYPE UNCOILER MANDREL ASSY.#1 |  |  | 6000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | STEP TYPE UNCOILER GEAR BOX ASSY.#1 |  |  |  | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | SNUBBER WITH BENDING ROLL ASSY.#1 |  |  |  | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | UNCOILER MANDREL ASSY.#2 |  |  | 6000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | UNCOILER GEAR BOX ASSY.#2 |  |  |  | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | SNUBBER WITH BENDING ROLL ASSY.#2 |  |  |  | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | O.B.B.S ASSY. FOR UNCOILER#2 |  |  | 600000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | RECOILER MANDREL ASSY.#1 |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | RECOILER GEAR BOX ASSY.#1 |  |  |  | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PUSHER PLATE ASSY.#1 |  |  |  | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | O.B.B.S ASSY.#1 |  |  | 600000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | HOLD DOWN ROLL ASSY.#1 |  |  | 600000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | RECOILER MANDREL ASSY.#2 |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | RECOILER GEAR BOX ASSY.#2 |  |  |  | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PUSHER PLATE ASSY.#2 |  |  |  | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | O.B.B.S ASSY.#2 |  |  | 600000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | HOLD DOWN ROLL ASSY.#2 |  |  | 600000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PEELER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PEELER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT SCRAP DOWN TABLE WITH HYDRAULIC CYLINDER |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT THREADING TABLE#1 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT THREADING TABLE#2 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | SCRAP TROLLEY 3 Nos |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY LOOPER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY LOOPER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT LOOPER TABLE ASSY.#3 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT LOOPER TABLE ASSY.#4 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#1 WITH ROLLERS |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#2 WITH ROLLERS |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#3 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#4 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#5 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#6 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#7 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#8 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#9 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#10 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#11 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#12 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#13 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#14 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#15 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#16 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#17 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#18 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#19 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#20 WITH ROLLERS |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | ENTRY SHEAR 2 Nos |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | EXIT SHEAR |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PINCH CUM LEVELLER ROLL ASSY.#1 WITH BASE FRAME |  |  | 4000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PINCH CUM LEVELLER ROLL ASSY.#2 WITH BASE FRAME |  |  | 4000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY SIDE GUIDE ASSY.#1 WITH BASE FRAME |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY SIDE GUIDE ASSY.#2 WITH BASE FRAME |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT SIDE GUIDE ASSY.#3 WITH BASE FRAME |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#1 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#2 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#3 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#4 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH ROLL ASSY.#5 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH ROLL ASSY.#6 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH CUM DEF. ROLL ASSY.#1 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH CUM DEF. ROLL ASSY.#2 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | STITCHER ASSY. |  |  | 6000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | BURR MASHER ROLL ASSY. WITH BASE FRAME |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | SINGLE SQUEEZE ROLL ASSY. 13 Nos WITH BASE FRAME |  |  | 11000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | DOUBLE SQUEEZE ROLL ASSY. 2 Nos WITH BASE FRAME |  |  | 4500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | AIR WIPER ASSY. |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | HOT AIR DRYER ASSY. |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | SUPPORT ROLL ASSY. -2 Nos |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | TENSIONER ROLL ASSY. WITH BASE FRAME |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI | ADITYA SAINI | OIL SPRAYING ASSY. |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | EPC |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | STRUCTURE | ADITYA SAINI | STRUCTURE |  |  | 10000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI | ADITYA SAINI | FOUNDATION BOLTS |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI | ADITYA SAINI | TAPER (LEVELLING) PLATE |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | ELECTRICAL | ADITYA SAINI | ELECTRICAL |  |  | 10000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | PRE WASH TANK |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | PICKLING TANK 1, 2, 3, 4 & 5 |  |  | 15000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | ACID RECIRCULATION SYSTEM |  |  | 18000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | SIX STAGE RINSING TANK WITH RECIRCULATION SYSTEM |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | FUME EXHAUST AND SCRUBBING SYSTEM FOR ACID |  |  | 7500000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | FUME EXHAUST AND SCRUBBING SYSTEM FOR RINSING |  |  | 7500000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | HYDRAULIC POWER PACK & VALVE STAND |  |  | 9000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI | ADITYA SAINI | HYDRAULIC & PNEUMATIC FITTINGS |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | ACID PROOF FLOOR LINNING |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI | ADITYA SAINI | PRESSURE REDUCING STATION |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI | ADITYA SAINI | CONDENSATE RECOVERY SYSTEM |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2538-APL-5 TANK PICKLING | BOI | ADITYA SAINI | SAFETY SHOWERS (3 NOS.) |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | UNCOILER ASSY. |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | PASSING TABLE ASSY.#1 |  |  | 100000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | PASSING TABLE ASSY.#2 |  |  | 100000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | PASSING TABLE ASSY.#3 |  |  | 100000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | PASSING TABLE ASSY.#4 |  |  | 100000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | PASSING TABLE ASSY.#5 |  |  | 100000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | PASSING TABLE ASSY.#6 |  |  | 100000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | PINCH CUM DEFLECTOR ROLL ASSY |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | DEBURRING ROLL ASSY. |  |  | 250000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING | BOI-LL | KUNAL | EPC & CPC |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING | BOI-LL | KUNAL | ENTRY SHEAR ASSY. |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING | BOI-LL | KUNAL | EXIT SHEAR ASSY. |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | SIDE GUIDE ASSY. |  |  | 250000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | TENSIONER ASSY. |  |  | 250000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING |  | KUNAL | SCRAP BAILER ASSY. |  |  | 250000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING | BOI | KUNAL | FOUNDATION BOLTS |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2512-GAURANG-TRIMMING | BOI | KUNAL | TAPER & FLAT PLATES |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2026
2520-APL-CCL |  | SAURABH | UNCOILER ASSY#1 |  |  | 8000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | UNCOILER ASSY#2 |  |  | 8000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | BELT WRAPPER ASSY. |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | SLEEVE LOADER ASSY. |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | PASSING TABLE ASSY#1 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | PASSING TABLE ASSY#2 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | PASSING TABLE ASSY#3 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | PASSING TABLE ASSY#4 |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | BRIDLE ROLL ASSY.#4 |  |  | 6000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | BRIDLE ROLL ASSY.#5 |  |  | 6000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | BRIDLE ROLL ASSY.#6 |  |  | 6000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | STRUCTURE | SAURABH | ENTRY ACCUMULATOR STRUCTURE |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | ENTRY ACCUMULATOR COUNTER WEIGHT ASSEMBLY |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI | SAURABH | ENTRY ACCUMULATOR CHAIN |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | STRUCTURE | SAURABH | EXIT ACCUMULATOR STRUCTURE |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | EXIT ACCUMULATOR COUNTER WEIGHT ASSEMBLY |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI | SAURABH | EXIT ACCUMULATOR CHAIN |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI-LL | SAURABH | DOUBLE DECKER SHEAR ASSY. |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI-LL | SAURABH | EXIT SHEAR ASSY. |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | EXIT PINCH CUM DEFLECTOR ROLL ASSY. |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | DOUBLE DECKER DEFLECTOR ROLL ASSY.#1 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | DEFLECTOR ROLL ASSY. |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | SINGLE STEERING ROLL ASSY. |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | SINGLE STEERING ROLL ASSY.(BEFORE FINISH COATER) |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | PRIME SQUEEZE ROLL CUM STEERING ASSY. |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | FINISH SQUEEZE ROLL CUM STEERING ASSY. |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | SINGLE SQUEEZE ROLL ASSY. |  |  | 3500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | DOUBLE SQUEEZE ROLL ASSY. |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | DEGREASING TANK ASSY#1 |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | DEGREASING TANK ASSY#2 |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | BRUSHING TANK ASSY.#1 |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | BRUSH ROLL CHOCK ASSEMBLY |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | BRUSH ROLL ASSEMBLY |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | BACKUP ROLL CHOCK ASSEMBLY |  |  | 9000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | DRIVE ASSEMBLY |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | BRUSHING TANK ASSY #2 |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | HOT RINSING TANK ASSY#1 |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | HOT RINSING TANK ASSY#2 |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI-LL | SAURABH | HOLDING TANK |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI-LL | SAURABH | PRIME QUENCHING TANK ASSY. |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | DEFLECTOR ROLL ASSEMBLY |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | FINISH QUENCHING TANK PIPING ASSY. |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | FUME EXHAUST DUCTING |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI-LL | SAURABH | HOT AIR DRYER ASSEMBLY |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI-LL | SAURABH | CHEMICAL DRYER ASSEMBLY |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI-LL | SAURABH | COLD AIR DRYER ASSEMBLY |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | FINISH COATER 'A' ASSY. |  |  | 8000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | FINISH COATER 'B' ASSY. |  |  | 8000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL |  | SAURABH | COATER ROOM |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI-LL | SAURABH | FINSH OVEN |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI-LL | SAURABH | CPC |  |  | 6000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI-LL | SAURABH | EPC |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CCL | Oct 2026
2520-APL-CCL | BOI-LL | SAURABH | HYDRAULIC POWERPACK |  |  | 9000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CCL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 Entry; Deflector Roll Assembly with Encoder |  |  | 3000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1, Air Wiper, Entry Side |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1, Pressure Pad with Side Guide, Entry Side |  |  | 1600000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1, Roll Coolant Headers, Entry Side |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Stand #1-Mill Housings |  |  | 17500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Stand #1- Bed Plates |  |  | 3500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Gear Reduction |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Gear Spindle |  |  | 8000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Spindle Support |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Stand #1 Exit, Snubber Roll #1 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #1 - Mill Stand #1 & #2, Interstrand Tensiometer Roll |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Mill Stand #1 Exit, Air Wiper |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Stand #2 Entry; Deflector Roll Assembly with Encoder |  |  | 3000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Stand #2 Entry, Snubber Roll #2 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Mill Stand #2, Roll Coolant Headers, Entry Side |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Housings |  |  | 17500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Bed Plates |  |  | 3500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Gear Reduction |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Gear Spindle |  |  | 8000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Spindle Support |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Stand #2 Exit, Snubber Roll #3 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #2 - Mill Stand #2 & #3, Interstrand Tensiometer Roll |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Mill Stand #2 Exit, Air Wiper |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Stand #3 Entry; Deflector Roll Assembly with Encoder |  |  | 3000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Stand #3, Entry, Snubber Roll #4 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Mill Stand #3, Roll Coolant Headers, Entry Side |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Housings |  |  | 17500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Bed Plates |  |  | 3500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Hydraulic Roll Force Cylinders |  |  | 5500000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Back Up Rolls Chocks |  |  | 7500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Back Up Rolls Bearings |  |  | 6000000 | Not Disp. | 2026-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - IMR Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - IMR Rolls |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - IMR Roll, Bearings |  |  | 1200000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Work Rolls Chocks |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Work Rolls |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mae-West Blocks |  |  | 6000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Pass Line Adjustment Mechanism |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Access Doors |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Cobble guard |  |  | 3000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Backup Roll Wipers |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Gear Reduction |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Main Mill Gear Box cum Pinion Stand |  |  | 7200000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Gear Spindle |  |  | 8000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Spindle Support |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Stand #3 Exit, Snubber Roll #5 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Mill Stand #3 - Mill Stand #3 & #4, Interstrand Tensiometer Roll |  |  | 2500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #3 - Mill Stand #3 Exit, Air Wiper |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND |  | MAYANK | Belt Wrapper |  |  | 5500000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Gear Box Lubrication System |  |  | 5000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Air-Oil Lubrication System |  |  | 30000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Roll Coolant System |  |  | 47500000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | COOLANT SYSTEM |  |  |  |  | APL | Oct 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Fume Exhaust System |  |  | 20000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND |  | MAYANK | Uncoiler #1 with Hold Down Roll & Snubber Roll |  |  | 20000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND | BOI | MAYANK | Entry Coil Car & Coil Storage Saddle #1 |  |  | 2000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND |  | MAYANK | Uncoiler Threading Table #1 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND |  | MAYANK | Entry Pinch Roll #1 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND |  | MAYANK | Uncoiler #2 with Hold Down Roll & Snubber Roll |  |  | 20000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND | BOI | MAYANK | Entry Coil Car & Coil Storage Saddle #2 |  |  | 2000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND |  | MAYANK | Uncoiler Threading Table #2 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND |  | MAYANK | Entry Pinch Roll #2 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND |  | MAYANK | Entry Pinch Roll #3 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Entry Double Decker Shear (for Top & Bottom Cut) with Scrap Bin |  |  | 2000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND |  | MAYANK | Entry Pinch Roll #4 (Common Pinch Roll) |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND |  | MAYANK | Entry Pinch Roll #5 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | TRUE | FALSE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Back Up Rolls Bearings |  |  | 10500000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Work Rolls |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | APL | Oct 2026
2537-APL-6 STAND | BOI | MAYANK | Foundation Bolt & Taper Plate |  |  | 10000000 | Not Disp. | 2026-10-28 |  | TRUE | TRUE | [5 empty] | APL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | UNCOILER ASSY.#1 |  |  | 9000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | UNCOILER ASSY.#2 |  |  | 9000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#4 |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#5 |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#6 |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | SINGLE STEERING ROLL ASSY. |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | DOUBLE STEERING ROLL ASSY. @ CAG |  |  | 3000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | SUPPORT ROLL ASSY. |  |  | 3500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | TENSIOMETER ASSY.#1 BEFORE FURNACE |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | AIR WIPPING EQUIPMENT |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | TURN UP ROLL ASSY. @CAG |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | TURN DOWN ROLL ASSY. @CAG |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | WATER QUENCHING TANK ASSY. |  |  | 2500000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | WATER SPRAY UNIT |  |  | 1500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | SINGLE SQUEEZE ROLL ASSY.@SPM |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | VERTICAL SQUEEZE ROLL ASSY.@CAG |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | COLD AIR DRYER @ CAG |  |  | 700000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | AIR DRYER @ SPM |  |  | 700000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | LOGO DRYER @ LOGO MARKER |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | VERTICAL CHEMICAL COATER ASSY. |  |  | 8000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | INDUCTION TYPE STRIP HEATER ASSY. |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | AIR COOLER@ STRIP HEATER |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | STRUCTURE | ADITYA SHARMA | COATER & STRIP HEATER STRUCTURE |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | CHILL ROLL ASSY. #1 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | CHILL ROLL ASSY. #2 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | LOGO MARKER ASSY |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | WELD HOLE DETECTOR ASSY.#01 (AFTER STEERING ASSY#02) |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | WELD HOLE DETECTOR ASSY.#02 (AFTER CAG) |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | WELD HOLE DETECTOR ASSY.#03 (AFTER EXIT ACC ASSY.) |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | SEAM WELDER ASSY. |  |  | 11000000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | ELECTRICAL | ADITYA SHARMA | ELECTRICAL |  |  | 80000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | PULPIT |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | Threading Needle Assembly |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | DFF Assembly |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | RTF Assembly |  |  | 5900000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | RECOILER BELT WRAPPPER ASSY. |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | RECOILER SLEEVE LOADER ASSY. |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | PEELER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | PEELER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | PASSING TABLE ASSY#1 (D.D. SHEAR & PINCH ROLL#1) |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | PASSING TABLE ASSY#2 (D.D. SHEAR & PINCH ROLL#3) |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | ENTRY SCRAP DOWN TABLE ASSY#1 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | ENTRY SCRAP DOWN TABLE ASSY#2 |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | ENTRY SCRAP TRAY ASSY. |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | ENTRY& EXIT SCRAP CAR ASSY. |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | PASSING TABLE ASSY#3 (BEFORE PINCH ROLL#4) |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | PASSING TABLE ASSY#4 (PINCH ROLL#4 & SEAM WELDER) |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | PASSING TABLE ASSY#5 (SEAM WELDER & PINCH ROLL#5) |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | PASSING TABLE ASSY#6 (PINCH ROLL#5 & STRIP CLAMP#1) |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | PASSING TABLE ASSY#7 (BEFORE FURNACE) |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | PASSING TABLE ASSY#7 (TURNUP & DOWN ASSY. ) |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | INSPECTION TABLE ASSY. |  |  | 200000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#4 |  |  | 3500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#5 |  |  | 3500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#6 |  |  | 3500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR TOP FRAME |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR COUNTER WEIGHT ASSEMBLY |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | EXIT ACCUMULATOR TOP FRAME |  |  | 5000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | EXIT ACCUMULATOR COUNTER WEIGHT ASSEMBLY |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | TENSIOMETER ASSY.#2 BEFORE TLL |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL | BOI | SAURABH | AIR WIPPING EQUIPMENT |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | TURN UP ROLL ASSY. @CAG |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | TURN DOWN ROLL ASSY. @CAG |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | SINGLE SQUEEZE ROLL ASSY.@SPM |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL | BOI | SAURABH | COLD AIR DRYER @ CAG |  |  | 700000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL | BOI | SAURABH | AIR DRYER @ SPM |  |  | 700000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL | BOI | SAURABH | LOGO DRYER @ LOGO MARKER |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | AIR COOLER@ STRIP HEATER |  |  | 500000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | CHILL ROLL ASSY. #1 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | CHILL ROLL ASSY. #2 |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL | BOI | SAURABH | LOGO MARKER ASSY |  |  | 2000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#01 (AFTER STEERING ASSY#02) |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#02 (AFTER CAG) |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#03 (AFTER EXIT ACC ASSY.) |  |  | 400000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL | BOI-LL | SAURABH | HYDRAULIC SYSTEM-POWER PACK |  |  | 7500000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2611-APL-CGL | BOI-LL | SAURABH | HYDRAULIC SYSTEM-VALVE STAND |  |  | 7500000 | Not Disp. | 2026-10-28 |  | FALSE | TRUE | [5 empty] | CGL | Oct 2026
2611-APL-CGL | BOI | SAURABH | HYDRAULIC PIPES & FITTINGS |  |  | 4000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | Entry Seal Assembly |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | Tunnel Assembly |  |  | 7000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL |  | SAURABH | HBR Assembly |  |  | 10000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2611-APL-CGL | BOI | SAURABH | HBR Gearbox |  |  | 1000000 | Not Disp. | 2026-10-28 |  | FALSE | [6 empty] | CGL | Oct 2026
2428-BMWIL-CGL | BOI-LL | TRIPURARI | Air knife |  |  | 11100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2428-BMWIL-CGL | BOI-LL | TRIPURARI | Pot |  |  | 51900000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2428-BMWIL-CGL | BOI-LL | TRIPURARI | Pot Equipment |  |  | 15000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | SAURABH | POT CELLAR VENTILATION |  |  | 3000000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | SAURABH | TENSION LEVELLER (TLL) |  |  | 14000000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL | BOI-LL | SAURABH | HYDRAULIC SYSTEM-POWER PACK |  |  | 7500000 | Not Disp. | 2026-09-28 |  | TRUE | TRUE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL | BOI-LL | SAURABH | HYDRAULIC SYSTEM-VALVE STAND |  |  | 7500000 | Not Disp. | 2026-09-28 |  | TRUE | TRUE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | SAURABH | EDGE WIPER ASSY.@SPM |  |  | 500000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL | BOI-LL | MAYANK | TOP BACKUP ROLL ASSY. |  |  | 1100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL | BOI-LL | MAYANK | BOTTOM BACKUP ROLL ASSY. |  |  | 1100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | BUP CHOCKS-4 NOS |  |  | 1500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL | BOI-LL | MAYANK | BUP BEARINGS |  |  | 3500000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL | BOI-LL | MAYANK | TOP WORK ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL | BOI-LL | MAYANK | BOTTOM WORK ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | WR CHOCKS-4 NOS |  |  | 1200000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL | BOI-LL | MAYANK | WR BEARINGS |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | MAEWEST BLOCK ASSY. |  |  | 2000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | TAPER WEDGE ASSY. |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | TOP SEPRATOR ASSY. |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | BACKUP WIPER ASSY. |  |  | 300000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | WORK ROLL INSIDE TRACK |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | BACK UP INSIDE TRACK |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | WORK ROLL CHANGING TROLLY |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | BACK-UP ROLL CHANGING TROLLY ASSY |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | ROLL FORCE CLY. ASSY. |  |  | 1500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | BACK UP STOOL ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | ROLL COOLANT HEADER ASSY |  |  | 100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | MILL DRIVE ARRANGEMENT |  |  | 2000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | SPINDLE SUPPORT ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | DEFLECTOR ROLL ASSY. |  |  | 3000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | ANTI-CRIMP ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | ANTI-CROSS ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | MILL HOUSING ASSY |  |  | 5000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | BED PLATE ASSY |  |  | 3000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | HOOD & PLATFORM |  |  | 2000000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | MAYANK | SQUEEZE ROLL ASSY FOR SPM |  |  | 1000000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | SAURABH | Static Section Assembly |  |  | 3200000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL |  | SAURABH | Calm Zone Assembly |  |  | 3800000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL | BOI-LL | SAURABH | Air knife ,Zinc Pump,Drosser |  |  | 10600000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2514-GAURANG-CGL | BOI-LL | SAURABH | Pot Equipment |  |  | 68000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | UNCOILER MANDREL ASSY.#2 |  |  | 6000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | UNCOILER GEAR BOX ASSY.#2 |  |  |  | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | APL | Sep 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | SNUBBER WITH BENDING ROLL ASSY.#2 |  |  |  | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | APL | Sep 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | RECOILER MANDREL ASSY.#2 |  |  | 7000000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | APL | Sep 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | RECOILER GEAR BOX ASSY.#2 |  |  |  | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | APL | Sep 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PUSHER PLATE ASSY.#2 |  |  |  | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | APL | Sep 2026
2516-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | STITCHER ASSY. |  |  | 6000000 | Not Disp. | 2026-09-28 |  | TRUE | TRUE | [5 empty] | APL | Sep 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | STITCHER ASSY. |  |  | 5000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Sep 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | STITCHER ASSY. |  |  | 4000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | EXIT HORIZONTAL ACCUMULATOR ASSY. |  |  | 3000000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CCL | Sep 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | COATER ROOM |  |  |  | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CCL | Sep 2026
2601-BMWIL - 6HI CRM | UNIT-2 | MAYANK | TOP PLATFORM |  | 5000 | 1200000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CRM | Sep 2026
2601-BMWIL - 6HI CRM | UNIT-2 | MAYANK | HOOD ASSY |  | 8000 | 1000000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | CRM | Sep 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | CPC |  | 2000 | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE |  |  |  | LC | 806270 | CRM | Sep 2026
2601-BMWIL - 6HI CRM | BOI | MAYANK | MISC |  |  | 3400000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CRM | Sep 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | HT MOTORS (PINION, POR, ETR & DTR) |  | 280000 | 26400000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CRM | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#6 (COOLING AFTER GALVANIZING) |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#7 (STRIP HEATER ASSY.) |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | HOZ. INSPECTION TABLE (BEFORE EXIT PINCH ROLL ASSY.#1) |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | ENTRY SCRAP DOWN TABLE ASSY#1 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | ENTRY SCRAP DOWN TABLE ASSY#2 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | ENTRY SCRAP TRAY ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | EXIT SCRAP DOWN TABLE ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | SCRAP TROLLEY ASSY. (ENTRY & EXIT SECTION) |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | EXIT THREADING TABLE ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#1 |  |  | 5500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#2 (TOP & BOTTOM SNUBBER ROLL) |  |  | 6000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#3 |  |  | 5500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#4 |  |  | 5500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#5 |  |  | 5500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | EXIT ACCUMULATOR ASSY. |  |  | 30000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | SINGLE STEERING ROLL ASSY. |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | DOUBLE STEERING ROLL ASSY. @ CAG |  |  | 2000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | ENTRY PINCH ROLL ASSY.#1,2,3 |  |  | 1500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | ENTRY PINCH ROLL ASSY.#4 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | DEBURRING ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | EXIT PINCH ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | EXIT PINCH CUM DEFLECTOR ROLL ASSY. |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#1 (AFTER BRIDLE ROLL ASSY.#01) |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#2 (BEFORE & AFTER ENTRY ACC ASSY.) |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#3 (BEFORE BRIDLE ROLL ASY.#03) |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#4 (BEFORE COATING THK GAUGE) |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#5 (AFTER COATING THK GAUGE) |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#6 (AFTER BRIDLE ROLL ASSY.#08) |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#7 (CHEMICAL COATER) |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#8 (BEFORE BRIDLE ROLL ASY.#09) |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#9 (BEFORE LOGO MARKER) |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | SUPPORT ROLL ASSY. (ENTRY ACCUMULATOR ROLL ASSY.) |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | SINGLE SQUEEZE ROLL ASSY. |  |  | 2500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | VERTICAL SQUEEZE ROLL ASSY.@CAG |  |  | 3500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | BRUSHING ROLL ASSY.#01 |  |  | 700000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | BRUSHING ROLL ASSY.#02 |  |  | 700000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | DEGREASING TANK ASSY. |  |  | 4500000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | BRUSHING TANK ASSY. |  |  | 4500000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | HOT WATER RINSING TANK ASSY. |  |  | 4500000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | QUENCHING TANK ASSY. |  |  | 4500000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | WATER SPRAY UNIT |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | TENSIOMETER ASSY.#1 BEFORE FURNACE ENTRY |  |  | 700000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | TENSIOMETER ASSY.#2 AFTER CAG |  |  | 700000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | TURN UP ROLL ASSY. (@CAG & STRIP HEATER) |  |  | 700000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | TURN DOWN ROLL ASSY. (@CAG & STRIP HEATER) |  |  | 700000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | SKIN PASS MILL |  |  | 40000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | VERTICAL CHEMICAL COATER ASSY. |  |  | 5500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | HOT AIR DRYER ASSY.#1 @ CLEANING SECTION |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | COLD AIR DRYER @ CAG |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | HOT AIR DRYER ASSY.#2 @ SPM |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | LOGO DRYER @ LOGO MARKER |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | CAG STRUCTURE |  |  | 4000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | COATER STRUCTURE |  |  | 5000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | WELD HOLE DETECTOR ASSY.#01 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | WELD HOLE DETECTOR ASSY.#02 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | WELD HOLE DETECTOR ASSY.#03 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | DOUBLE DECKER ENTRY SHEAR ASSY. |  |  | 1500000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | DELIVERY SHEAR ASSY. |  |  | 1500000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI-LL | ADITYA SHARMA | COATING THK GAUGE ASSY. |  |  | 8000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | STRIP INDUCTION HEATER ASSY. |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | FOUNDATION BOLT |  |  | 1500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | TAPER PLATE |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | PULPIT |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | Furnace Structure-Staircases |  |  | 1500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | Furnace Structure-Handrails |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | Furnace Structure-Chequered plates |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | CAG Structure-Staircases |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | CAG Structure-Handrails |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | CAG Structure-Chequered plates |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Threading Needle Assembly |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Furnace Exhaust Ducting |  |  | 1500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Furnace Gas and Combustion Air Piping |  |  | 1900000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Furnace Dilution Air Piping |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Furnace Interconnecting Piping |  |  | 2500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | Entry Seal Assembly |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | Throat Assembly |  |  | 3500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | RTF Assembly |  |  | 5900000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL |  | ADITYA SHARMA | SF Assembly |  |  | 5100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Heat Exchanger |  |  | 2000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2519-APL-CGL | BOI | ADITYA SHARMA | Down Chute |  |  | 1500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2026
2512-GAURANG-TRIMMING |  | KUNAL | UNCOILER OBBS ASSY |  |  | 100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Sep 2026
2512-GAURANG-TRIMMING |  | KUNAL | EXIT OBBS ASSY |  |  | 100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Sep 2026
2512-GAURANG-TRIMMING |  | KUNAL | PEELER TABLE ASSY. |  |  | 100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Sep 2026
2512-GAURANG-TRIMMING |  | KUNAL | SCRAP DOWN TABLE ASSY. |  |  | 100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Sep 2026
2512-GAURANG-TRIMMING |  | KUNAL | PASSING TABLE & SCRAP SUIT |  |  | 100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Sep 2026
2512-GAURANG-TRIMMING |  | KUNAL | THREADING TABLE ASSY. |  |  | 100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Sep 2026
2512-GAURANG-TRIMMING |  | KUNAL | SCRAP TROLLEY ASSY. |  |  | 100000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Sep 2026
2512-GAURANG-TRIMMING | BOI | KUNAL | HYDRAULIC PIPE & FITTINGS |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Sep 2026
2512-GAURANG-TRIMMING | ELECTRICAL | KUNAL | ELECTRICAL |  |  | 2500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Sep 2026
2520-APL-CCL |  | SAURABH | PEELER TABLE ASSY.#1 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | PEELER TABLE ASSY.#2 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | SCRAP DOWN TABLE ASSY#1 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | SCRAP DOWN TABLE ASSY#2 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | SCRAP TROLLEY ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | EXIT THREADING TABLE ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | BRIDLE ROLL ASSY.#1 |  |  | 6000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | BRIDLE ROLL ASSY.#2 |  |  | 6000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | BRIDLE ROLL ASSY.#3 |  |  | 6000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | ENTRY ACCUMULATOR FIXED FRAME |  |  | 8000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | ENTRY ACCUMULATOR MOVING FRAME |  |  | 5000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | ENTRY ACCUMULATOR TOP FRAME |  |  | 8000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | EXIT ACCUMULATOR FIXED FRAME |  |  | 8000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | EXIT ACCUMULATOR MOVING FRAME |  |  | 5000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | EXIT ACCUMULATOR TOP FRAME |  |  | 8000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | ENTRY PINCH ROLL ASSY.#1 |  |  | 800000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | ENTRY PINCH ROLL ASSY.#4 |  |  | 800000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | DEBURRING ROLL ASSY. |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | EXIT PINCH ROLL ASSY. |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | CHEMICAL COATER ASSY. |  |  | 8000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL |  | SAURABH | PRIME COATER ASSY. |  |  | 8000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL | BOI-LL | SAURABH | PRIME OVEN |  |  | 5000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CCL | Sep 2026
2520-APL-CCL | STRUCTURE | SAURABH | OVEN STRUCTURE |  |  | 4000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL | STRUCTURE | SAURABH | CHEMICAL COATER STRUCTURE |  |  | 3000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL | BOI | SAURABH | FOUNDATION BOLT |  |  | 1500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL | BOI | SAURABH | TAPER PLATE |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL | BOI-LL | SAURABH | RTO |  |  | 40000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL | ELECTRICAL | SAURABH | ELECTRICAL |  |  | 40000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2520-APL-CCL | BOI | SAURABH | PULPIT |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Laser Welder |  |  | 220000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2026
2517-APL-6 STAND |  | MAYANK | Tension Bridle Unit #1 |  |  | 6000000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | APL | Sep 2026
2517-APL-6 STAND |  | MAYANK | Steering Unit #1 |  |  | 2000000 | Not Disp. | 2026-09-28 |  | TRUE | TRUE | [5 empty] | APL | Sep 2026
2517-APL-6 STAND |  | MAYANK | Steering Unit #2 |  |  | 2000000 | Not Disp. | 2026-09-28 |  | TRUE | TRUE | [5 empty] | APL | Sep 2026
2517-APL-6 STAND |  | MAYANK | Tension Bridle #2 |  |  | 6000000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | APL | Sep 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Back Up Rolls Bearings |  |  | 10500000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Work Rolls |  |  | 2000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #2 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2026
2517-APL-6 STAND |  | MAYANK | Delivery Threading Table |  |  | 1000000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | APL | Sep 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Delivery Coil Car & Coil Saddles |  |  | 2000000 | Not Disp. | 2026-09-28 |  | TRUE | FALSE | [5 empty] | APL | Sep 2026
2517-APL-6 STAND | ELECTRICAL | MAYANK | Electrical |  |  | 180000000 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2026
2615-BMWIL-CRM (SPARE) |  |  | SPARE |  |  | 26106134 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | SPARE | Sep 2026
2610-BMWIL-CGL (SPARE) |  |  | SPARE |  |  | 56180324.5763 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | SPARE | Sep 2026
25M006-BMWIL-MILL BEARING |  |  | SPARE |  |  | 26154450 | Not Disp. | 2026-09-28 |  | FALSE | FALSE | [5 empty] | MILL BEARING | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | UNCOILER OBBS ASSY.#1 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | UNCOILER OBBS ASSY.#2 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | RECOILER EXIT OBBS ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | RECOILER BELT WRAPPPER ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | RECOILER SLEEVE LOADER ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | PEELER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | PEELER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#1 (D.D. SHEAR & PINCH ROLL#1) |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#2 (D.D. SHEAR & PINCH ROLL#3) |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY SCRAP DOWN TABLE ASSY#1 |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY SCRAP DOWN TABLE ASSY#2 |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY SCRAP TRAY ASSY. |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY& EXIT SCRAP CAR ASSY. |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#3 (BEFORE PINCH ROLL#4) |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#4 (PINCH ROLL#4 & SEAM WELDER) |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#5 (SEAM WELDER & PINCH ROLL#5) |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#6 (PINCH ROLL#5 & STRIP CLAMP#1) |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#7 (BEFORE FURNACE) |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#7 (TURNUP & DOWN ASSY. ) |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | INSPECTION TABLE ASSY. |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | EXIT THREADING TABLE ASSY. |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#1 |  |  | 5000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#2 |  |  | 5000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#3 |  |  | 5000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY ACCUMULATOR TOP FRAME |  |  | 8000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY ACCUMULATOR COUNTER WEIGHT ASSEMBLY |  |  | 5000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | ENTRY ACCUMULATOR CHAIN |  |  | 3000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | EXIT ACCUMULATOR TOP FRAME |  |  | 8000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | EXIT ACCUMULATOR COUNTER WEIGHT ASSEMBLY |  |  | 5000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY PINCH ROLL ASSY.#1 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY PINCH ROLL ASSY.#2 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY PINCH ROLL ASSY.#3 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY PINCH ROLL ASSY.#4 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY PINCH ROLL ASSY.#5 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | EXIT PINCH ROLL ASSY. #1 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | EXIT PINCH ROLL ASSY. #2 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#1 (AFTER BRIDLE ROLL ASSY.#1) |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#2&3 (BEFORE & AFTER ENTRY ACC ASSY.) |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#4 (BEFORE COATING THICKNESS GAUGE) |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#5 (AFTER BRIDLE ROLL ASY.#07) |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#6&7 (BEFORE CHEMICAL COATER) |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#8 (BEFORE BRIDLE ROLL ASY.#08) |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#9 (BEFORE LOGO MARKER) |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | TENSIOMETER ASSY.#2 BEFORE TLL |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | DOUBLE DECKER ENTRY SHEAR ASSY. |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL | BOI-LL | ADITYA SHARMA | DELIVERY SHEAR ASSY. |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | STRIP CLAMP ASSY.#01 BEFORE BRIDLE ASSY#1 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | STRIP CLAMP ASSY.#02 AFTER BRIDLE ASSY#2 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | STRIP CLAMP ASSY.#03 @ CAG |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | HYDRAULIC PIPES & FITTINGS |  |  | 4000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | Entry Seal Assembly |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | Tunnel Assembly |  |  | 7000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | HBR Assembly |  |  | 20000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | HBR Gearbox |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL | BOI | SAURABH | COIL CAR ASSY. @ UNCOILER |  |  | 2000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | DRAG CHAIN ASSY. @ UNCOILER |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | COIL SADDLE ASSY. @ UNCOILER |  |  | 400000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL | BOI | SAURABH | COIL CAR ASSY. @ RECOILER |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | DRAG CHAIN ASSY. @ RECOILER |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | COIL SADDLE ASSY. @ RECOILER |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | UNCOILER OBBS ASSY.#1 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | UNCOILER OBBS ASSY.#2 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | RECOILER EXIT OBBS ASSY. |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | EXIT THREADING TABLE ASSY. |  |  | 200000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#1 |  |  | 3500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#2 |  |  | 3500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#3 |  |  | 3500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL | STRUCTURE | SAURABH | ENTRY ACCUMULATOR STRUCTURE |  |  | 2000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR FIXED FRAME |  |  | 4000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR MOVING FRAME |  |  | 3000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL | BOI | SAURABH | ENTRY ACCUMULATOR CHAIN |  |  | 2000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL | STRUCTURE | SAURABH | EXIT ACCUMULATOR STRUCTURE |  |  | 2000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | EXIT ACCUMULATOR FIXED FRAME |  |  | 4000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | EXIT ACCUMULATOR MOVING FRAME |  |  | 3000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL | BOI | SAURABH | EXIT ACCUMULATOR CHAIN |  |  | 2000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | SINGLE STEERING ROLL ASSY. |  |  | 2000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | DOUBLE STEERING ROLL ASSY. @ CAG |  |  | 3000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#1 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#2 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#3 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#4 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#5 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | EXIT PINCH ROLL ASSY. #1 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | EXIT PINCH ROLL ASSY. #2 |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#1 (AFTER BRIDLE ROLL ASSY.#1) |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#2&3 (BEFORE & AFTER ENTRY ACC ASSY.) |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#4 (BEFORE COATING THICKNESS GAUGE) |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#5 (AFTER BRIDLE ROLL ASY.#07) |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#6&7 (BEFORE CHEMICAL COATER) |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#8 (BEFORE BRIDLE ROLL ASY.#08) |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#9 (BEFORE LOGO MARKER) |  |  | 250000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL | BOI-LL | SAURABH | DOUBLE DECKER ENTRY SHEAR ASSY. |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2611-APL-CGL | BOI-LL | SAURABH | DELIVERY SHEAR ASSY. |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | TRUE | [5 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | STRIP CLAMP ASSY.#01 BEFORE BRIDLE ASSY#1 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | STRIP CLAMP ASSY.#02 AFTER BRIDLE ASSY#2 |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL |  | SAURABH | STRIP CLAMP ASSY.#03 @ CAG |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL | BOI | SAURABH | FOUNDATION BOLT |  |  | 1000000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2611-APL-CGL | BOI | SAURABH | TAPER PLATE |  |  | 500000 | Not Disp. | 2026-09-28 |  | FALSE | [6 empty] | CGL | Sep 2026
2428-BMWIL-CGL | BOI-LL | TRIPURARI | TENSION LEVELLER (TLL) |  |  | 16600000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | EDGE WIPER ASSY.@SPM |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | TOP BACKUP ROLL ASSY. |  |  | 1100000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | BOTTOM BACKUP ROLL ASSY. |  |  | 1100000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | BUP CHOCKS-4 NOS |  |  | 1500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | BOI-LL | TRIPURARI | BUP BEARINGS |  |  | 3500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | TOP WORK ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | BOTTOM WORK ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | WR CHOCKS-4 NOS |  |  | 1200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | BOI-LL | TRIPURARI | WR BEARINGS |  |  | 1000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | MAEWEST BLOCK ASSY. |  |  | 2000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | TAPER WEDGE ASSY. |  |  | 1000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | TOP SEPRATOR ASSY. |  |  | 200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | BACKUP WIPER ASSY. |  |  | 300000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | WORK ROLL INSIDE TRACK |  |  | 200000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | BACK UP INSIDE TRACK |  |  | 200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | WORK ROLL CHANGING TROLLY |  |  | 500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | BACK-UP ROLL CHANGING TROLLY ASSY |  |  | 500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | ROLL FORCE CLY. ASSY. |  |  | 1500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | BACK UP STOOL ASSY. |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | ROLL COOLANT HEADER ASSY |  |  | 100000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | MILL DRIVE ARRANGEMENT |  |  | 2000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | SPINDLE SUPPORT ASSY. |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | DEFLECTOR ROLL ASSY. |  |  | 3000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | ANTI-CRIMP ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | ANTI-CROSS ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | MILL HOUSING ASSY |  |  | 5000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | BED PLATE ASSY |  |  | 3000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-1 | TRIPURARI | HOOD & PLATFORM |  |  | 2000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | SQUEEZE ROLL ASSY FOR SPM |  |  | 1000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | Static Section Assembly |  |  | 2000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | Calm Zone Assembly |  |  | 2000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI-LL | SAURABH | EPC SENSOR ASSY.@ RECOILER |  |  | 8000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI-LL | SAURABH | CPC SENSOR ASSY.@ STEERING ASSY. |  |  | 0 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL |  | SAURABH | BASE FRAME CPC SENSOR ASSY. |  |  | 0 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Furnace Exhaust Ducting |  |  | 1500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Furnace Gas and Combustion Air Piping |  |  | 1900000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Furnace Dilution Air Piping |  |  | 500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Furnace Interconnecting Piping |  |  | 2500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL |  | SAURABH | RTF Assembly |  |  | 5900000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL |  | SAURABH | JCF Assembly |  |  | 4600000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Ducting Assembly |  |  | 700000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Heat Exchanger |  |  | 2000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Down Chute |  |  | 1500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Pot cellar Ventilation Supply Ducting |  |  | 400000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Pot cellar Ventilation Exhaust Ducting |  |  | 400000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Moving Pendant assembly |  |  | 2000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Moving Trolley |  |  | 3000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Up Pass Pendant-1 (Future) |  |  | 1200000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Cooling pendant assembly-Slot (Future) |  |  | 0 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Up Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Up Pass Pendant-3 |  |  | 1200000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Down Pass Pendant-1 |  |  | 1200000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Down Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Non-Ox Burners |  |  | 2000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Radiant Tube Burner With Recuperator |  |  | 1000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Post Combustion Burner |  |  | 2000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Ignition Cable |  |  | 200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Ratio Regulators |  |  | 200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | UV Sensors |  |  | 200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | UV Flame Switches |  |  | 200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Ignition Transformers |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | JCF Heat Exchanger |  |  | 2000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Flow Switchs |  |  | 200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Thermocouple |  |  | 200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Temperature Transmitters |  |  | 600000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Compensating Cable |  |  | 200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | IR Pyrometers |  |  | 400000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Pressure Transmitters |  |  | 600000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Solenoid Shut-Off Valves |  |  | 400000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | H2 analyzer |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Dew Point Analyzer |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | O2 Analyzer |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Electric Heater |  |  | 3000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Glow Heater |  |  | 100000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Pressure Gauges |  |  | 100000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Orifice Plates |  |  | 1200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Rotameters |  |  | 100000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Pneumatic Shut-Off Valves |  |  | 1200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Hot Air Control Valve |  |  | 1400000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Adjustable Gas control valves |  |  | 400000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Fan |  |  | 1500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Radiant Tubes |  |  | 1500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Air knife Blower |  |  | 6000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Recuperator For Non-OX Furnace |  |  | 3000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | HNX Gas Station & Heater |  |  | 1500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | JCF Fan |  |  | 5300000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Furnace Bellows |  |  | 1000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Butterfly Valve |  |  | 700000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Ball Valve |  |  | 700000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Gate Valve |  |  | 700000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Globe Valve |  |  | 700000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Flow Control Valve |  |  | 1000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Check Valve |  |  | 700000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Main gas station |  |  | 1200000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Propeller Shaft |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2514-GAURANG-CGL | BOI | SAURABH | Couplings |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | STEP TYPE UNCOILER MANDREL ASSY.#1 |  |  | 6000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | STEP TYPE UNCOILER GEAR BOX ASSY.#1 |  |  |  | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | SNUBBER WITH BENDING ROLL ASSY.#1 |  |  |  | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | RECOILER MANDREL ASSY.#1 |  |  | 7000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | APL | Aug 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | RECOILER GEAR BOX ASSY.#1 |  |  |  | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PUSHER PLATE ASSY.#1 |  |  |  | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | BURR MASHER ROLL ASSY. WITH BASE FRAME |  |  | 1500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2516-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | HYDRAULIC POWER PACK & VALVE STAND |  |  | 9000000 | Not Disp. | 2026-08-28 |  | FALSE | TRUE | [5 empty] | APL | Aug 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | UNCOILER MANDREL ASSY.#1 |  |  | 5000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | STEP TYPE UNCOILER GEAR BOX ASSY.#1 |  |  |  | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | SNUBBER WITH BENDING ROLL ASSY.#1 |  |  |  | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | UNCOILER MANDREL ASSY.#2 |  |  | 5000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | UNCOILER GEAR BOX ASSY.#2 |  |  |  | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | SNUBBER WITH BENDING ROLL ASSY.#2 |  |  |  | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | RECOILER MANDREL ASSY. |  |  | 7000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | RECOILER GEAR BOX ASSY. |  |  |  | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PUSHER PLATE ASSY. |  |  |  | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | FUME EXHAUST AND SCRUBBING SYSTEM FOR ACID |  |  | 7500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | FUME EXHAUST AND SCRUBBING SYSTEM FOR RINSING |  |  | 7500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | BOI | ADITYA SAINI | WATER WASHER STANDS(3 NOS.) |  |  | 500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Aug 2026
2533-BMWIL-4 TANK PICKLING | BOI | ADITYA SAINI | MISC |  |  |  | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Aug 2026
2602-BMWIL-SLITTING |  | OM DEV | RECOILER-TURN STYLE |  |  | 2000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Aug 2026
2602-BMWIL-SLITTING |  | OM DEV | STEP TYPE UNCOILER ASSEMBLY. |  |  | 7500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Aug 2026
2602-BMWIL-SLITTING |  | OM DEV | RECOILER ASSEMBLY. |  |  | 8500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Aug 2026
2602-BMWIL-SLITTING | BOI-LL | OM DEV | SLITTER HEAD ASSEMBLY. WITH TOOLING |  |  | 3000000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | SLITTING | Aug 2026
2602-BMWIL-SLITTING | BOI-LL | OM DEV | HYDRAULIC SYSTEM-POWERPACK |  |  | 4000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | SLITTING | Aug 2026
2602-BMWIL-SLITTING |  | OM DEV | MISC. |  |  | 200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | SLITTING | Aug 2026
2534-BMWIL-TRIMMING |  | KUNAL | UNCOILER ASSEMBLY. |  |  | 5500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | Aug 2026
2534-BMWIL-TRIMMING |  | KUNAL | RECOILER ASSEMBLY. |  |  | 6500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | Aug 2026
2534-BMWIL-TRIMMING | BOI-LL | KUNAL | TRIMMER HEAD ASSEMBLY. |  |  | 2500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2026
2534-BMWIL-TRIMMING | BOI-LL | KUNAL | CPC |  |  | 700000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2026
2534-BMWIL-TRIMMING | BOI-LL | KUNAL | EPC |  |  | 700000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | UNCOILER ASSY#1 WITH SNUBBER ROLE |  |  | 2000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CCL | Aug 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | UNCOILER ASSY#2 WITH SNUBBER ROLE |  |  | 2000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CCL | Aug 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | RECOILER ASSY. WITH PUSHER PLATE |  |  | 2500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CCL | Aug 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | ENTRY HORIZONTAL ACCUMULATOR ASSY. |  |  | 3000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CCL | Aug 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | EXIT PINCH CUM DEFLECTOR ROLL ASSY. |  |  | 800000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CCL | Aug 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | DOUBLE DECKER DEFLECTOR ROLL ASSY.#1 |  |  | 800000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CCL | Aug 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | CPC SENSOR ASSY.#1, |  |  | 200000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CCL | Aug 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | CPC SENSOR ASSY.#2 |  |  | 200000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CCL | Aug 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | CPC SENSOR ASSY.#3 |  |  | 200000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CCL | Aug 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | EPC SENSOR ASSY. |  |  | 200000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CCL | Aug 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | HYDRAULIC POWER PACK & VALVE STAND |  |  | 3000000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CCL | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-3 | MAYANK | POR ASSEMBLY WITH SNUBBER |  | 74079.4244 | 7000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | ETR ASSEMBLY WITH PUSHER PLATE |  | 160000 | 12500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | DTR ASSEMBLY WITH PUSHER PLATE |  | 136835.9386 | 12500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | BACKUP CHOCKS - 4 NOS |  | 57938.5023 | 6000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | IMR CHOCKS - 4 NOS |  | 16514.6114 | 1600000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | WORK ROLL CHOCKS - 4 NOS |  | 15594.6477 | 1600000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI | MAYANK | ROLL FORCE CLY ASSY |  | 40000 | 9900000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-3 | MAYANK | QWRC TROLLEY ASSY WITH SAFETY CAGE |  | 40000 | 8000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | IMR SHIFTING ALONG WITH SPINDLE SUPPORT |  | 40000 | 2000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | MILL HOUSING WITH WORK ROLL CLAMP, BACKUP CLAMP & LINERS |  | 220000 | 25000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | BED PLATE ASSY. |  | 50000 | 1500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | SHUTTER ASSY |  | 2000 | 700000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | TOP SEPARATOR ASSY. |  | 5000 | 100000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | TAPER WEDGE ASSY |  | 35000 | 1500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | MAEWEST BLOCK ASSY. |  | 120000 | 3000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | WORK ROLL INSIDE TRACK |  | 2000 | 100000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | BACKUP INSIDE TRACK |  | 2000 | 200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | BACKUP OUTSIDE TRACK |  | 2000 | 100000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | ENTRY MILL TABLE WITH DEFLECTOR CUM TURN DOWN ROLL ASSEMBLY |  | 50000 | 1400000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | EXIT MILL TABLE WITH DEFLECTOR CUM TURN DOWN ROLL ASSEMBLY |  | 50000 | 1400000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | ENTRY C FRAME |  | 2053.2426 | 200000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | EXIT C FRAME |  | 2053.2426 | 200000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | ROLL COOLANT HEADER ASSY |  | 20000 | 1700000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | ENTRY & EXIT AIR WIPER ASSY |  | 10000 | 900000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | BACKUP ROLL WIPER ASSY |  | 10000 | 900000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | COBBLE GUARD ASSY |  | 30000 | 2600000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | PRESSURE PAD WITH SIDE GUIDE |  | 50000 | 2200000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | ENTRY & EXIT AIR KNIFE ASSY |  | 10000 | 1000000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | ENTRY PASSING TABLE @ MILL STAND |  | 5000 | 500000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | EXIT PASSING TABLE @ MILL STAND |  | 3000 | 500000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | INTERCONNECTING PIPING |  | 8000 | 700000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | DISTRIBUTION HEADER |  | 5000 | 500000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | DELIVERY SHEAR ASSY |  | 6875 | 600000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | UNIT-3 | MAYANK | ELECTROMAGNETIC BRAKE FOR ETR & DTR WITH BASE FRAME |  | 20000 | 6200000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE |  |  | 1400626 |  |  | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI | MAYANK | GEARED SPINDLE (1 WORKING SET+1 SPARE) |  | 120000 | 10300000 | Not Disp. | 2026-08-28 |  | FALSE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | CELLAR VENTILATION SYSTEM |  | 5000 | 600000 | Not Disp. | 2026-08-28 |  | FALSE | TRUE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | HYDRAULIC POWER PACK & VALVE TABLE ASSY |  | 190000 | 15000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | THICKNESS GAUGE |  | 100000 | 13200000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | BACKUP ROLLS - 2 NOS |  | 104000 | 9000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE |  |  | 8307416 |  |  | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | IMR ROLLS - 2 NOS |  | 17000 | 1500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | WORK ROLLS - 2 NOS |  | 10000 | 1000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2026
2601-BMWIL - 6HI CRM | BOI | MAYANK | FUME EXHAUST AND CELLER VENTILATION DUCTING MATERIAL ONLY |  | 5000 | 2200000 | Not Disp. | 2026-08-28 |  | FALSE | TRUE | [5 empty] | CRM | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | UNCOILER OBBS ASSY. #1 |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | UNCOILER OBBS ASSY. #2 |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | RECOILER EXIT OBBS ASSY. |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | PEELER TABLE ASSY.#1 |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | PEELER TABLE ASSY.#2 |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#1 (D.D. SHEAR & PINCH ROLL#1) |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#2 (PINCH ROLL#2 & D.D. SHEAR) |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#3 (PINCH ROLL#3 & PINCH ROLL#4) |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#4 (PINCH ROLL#4 & SEAM WELDER) |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | PASSING TABLE ASSY#5 (BEFORE ENTRY FURNACE) |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | ENTRY ACCUMULATOR ASSY. |  |  | 30000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL | ELECTRICAL | ADITYA SHARMA | ELECTRICAL |  |  | 50000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | Furnace Structure - Columns |  |  | 10000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | Furnace Structure-Beams |  |  | 5000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | Furnace Structure-Bracings |  |  | 2500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | CAG Structure - Columns |  |  | 2500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | CAG Structure-Beams |  |  | 1500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL | STRUCTURE | ADITYA SHARMA | CAG Structure-Bracings |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | Tunnel Assembly |  |  | 7000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | DFF Assembly |  |  | 7700000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2519-APL-CGL |  | ADITYA SHARMA | HBR Assembly |  |  | 16000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2026
2512-GAURANG-TRIMMING | BOI | KUNAL | UNCOILER-COIL CAR ASSY. |  |  | 1000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2026
2512-GAURANG-TRIMMING |  | KUNAL | UNCOILER-DRAG CHAIN ASSY. |  |  | 50000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2026
2512-GAURANG-TRIMMING |  | KUNAL | UNCOILER-SADDLE ASSY. |  |  | 50000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2026
2512-GAURANG-TRIMMING |  | KUNAL | UNCOILER-PIT COVER |  |  | 50000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2026
2512-GAURANG-TRIMMING | BOI | KUNAL | RECOILER-COIL CAR ASSY. |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2026
2512-GAURANG-TRIMMING |  | KUNAL | RECOILER-DRAG CHAIN ASSY. |  |  | 50000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2026
2512-GAURANG-TRIMMING |  | KUNAL | RECOILER-SADDLE ASSY. |  |  | 50000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2026
2512-GAURANG-TRIMMING |  | KUNAL | RECOILER-PIT COVER |  |  | 50000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2026
2512-GAURANG-TRIMMING | BOI-LL | KUNAL | TRIMMER HEAD ASSY. |  |  | 2000000 | Not Disp. | 2026-08-28 |  | FALSE | TRUE | [5 empty] | TRIMMING | Aug 2026
2520-APL-CCL | BOI | SAURABH | UNCOILER COIL CAR ASSY. |  |  | 3000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2026
2520-APL-CCL |  | SAURABH | UNCOILER DRAG CHAIN ASSY. |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2026
2520-APL-CCL |  | SAURABH | UNCOILER COIL SADDLE ASSY. |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2026
2520-APL-CCL | BOI | SAURABH | RECOILER COIL CAR ASSY. |  |  | 1500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2026
2520-APL-CCL |  | SAURABH | RECOILER DRAG CHAIN ASSY. |  |  | 300000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2026
2520-APL-CCL |  | SAURABH | RECOILER COIL SADDLE ASSY. |  |  | 300000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2026
2520-APL-CCL |  | SAURABH | UNCOILER #1 OBBS ASSY |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2026
2520-APL-CCL |  | SAURABH | UNCOILER #2 OBBS ASSY |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2026
2520-APL-CCL |  | SAURABH | RECOILER OBBS ASSY |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2026
2544-APL-REWINDING |  | KUNAL | UNCOILER ASSEMBLY. |  |  | 2000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2544-APL-REWINDING |  | KUNAL | RECOILER ASSEMBLY. |  |  | 2500000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2544-APL-REWINDING | BOI-LL | KUNAL | EPC |  |  | 700000 | Not Disp. | 2026-08-28 |  | FALSE | TRUE | [5 empty] | APL | Aug 2026
2544-APL-REWINDING | BOI-LL | KUNAL | HYDRAULIC SYSTEM |  |  | 3500000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | APL | Aug 2026
2544-APL-REWINDING | ELECTRICAL | KUNAL | ELECTRICAL |  |  | 2000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND |  | MAYANK | Uncoiler #1 with Hold Down Roll & Snubber Roll |  |  | 20000000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND | BOI | MAYANK | Entry Coil Car & Coil Storage Saddle #1 |  |  | 2000000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND |  | MAYANK | Uncoiler Threading Table #1 |  |  | 1000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND |  | MAYANK | Entry Pinch Roll #1 |  |  | 1000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND |  | MAYANK | Uncoiler #2 with Hold Down Roll & Snubber Roll |  |  | 20000000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND | BOI | MAYANK | Entry Coil Car & Coil Storage Saddle #2 |  |  | 2000000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND |  | MAYANK | Uncoiler Threading Table #2 |  |  | 1000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND |  | MAYANK | Entry Pinch Roll #2 |  |  | 1000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND |  | MAYANK | Entry Pinch Roll #3 |  |  | 1000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Entry Double Decker Shear (for Top & Bottom Cut) with Scrap Bin |  |  | 2000000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND |  | MAYANK | Entry Pinch Roll #4 (Common Pinch Roll) |  |  | 1000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND |  | MAYANK | Entry Pinch Roll #5 |  |  | 1000000 | Not Disp. | 2026-08-28 |  | TRUE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Back Up Rolls |  |  | 14000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Back Up Rolls Bearings |  |  | 10500000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Work Rolls |  |  | 2000000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND | BOI-LL | MAYANK | Mill Stand #1 - Work Rolls Bearings |  |  | 1400000 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | APL | Aug 2026
2517-APL-6 STAND | BOI | MAYANK | Foundation Bolt & Taper Plate |  |  | 10000000 | Not Disp. | 2026-08-28 |  | TRUE | TRUE | [5 empty] | APL | Aug 2026
2612-BMWIL-SLITTING (SPARE) |  |  | SPARE |  |  | 1692774.5763 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | SPARE | Aug 2026
2613-BMWIL-PICKLING (SPARE) |  |  | SPARE |  |  | 9767009.322 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | SPARE | Aug 2026
2614-BMWIL-TRIMMING (SPARE) |  |  | SPARE |  |  | 903719.4915 | Not Disp. | 2026-08-28 |  | FALSE | FALSE | [5 empty] | SPARE | Aug 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | COIL CAR ASSY. @ UNCOILER |  |  | 2000000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | DRAG CHAIN ASSY. @ UNCOILER |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | COIL SADDLE ASSY. @ UNCOILER |  |  | 400000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | COIL CAR ASSY. @ RECOILER |  |  | 1000000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | DRAG CHAIN ASSY. @ RECOILER |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | COIL SADDLE ASSY. @ RECOILER |  |  | 200000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL | STRUCTURE | ADITYA SHARMA | ENTRY ACCUMULATOR STRUCTURE |  |  | 5000000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY ACCUMULATOR FIXED FRAME |  |  | 8000000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | ENTRY ACCUMULATOR MOVING FRAME |  |  | 5000000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL | STRUCTURE | ADITYA SHARMA | EXIT ACCUMULATOR STRUCTURE |  |  | 5000000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | EXIT ACCUMULATOR FIXED FRAME |  |  | 8000000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL |  | ADITYA SHARMA | EXIT ACCUMULATOR MOVING FRAME |  |  | 5000000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | EXIT ACCUMULATOR CHAIN |  |  | 3000000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | FOUNDATION BOLT |  |  | 1000000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2604-AL PROMPT-CGL | BOI | ADITYA SHARMA | TAPER PLATE |  |  | 500000 | Not Disp. | 2026-08-28 |  | FALSE | [6 empty] | CGL | Aug 2026
2518-APL-SPM | BOI-LL | MAYANK | THICKNESS GAUGE (IMS) |  |  | 7700000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | SPM | Jul 2026
2518-APL-SPM | BOI-LL | MAYANK | SPINDLE COUPLING (2 nos.) |  |  | 15500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | SPM | Jul 2026
2518-APL-SPM | UNIT-2 | MAYANK | TOP PLATFORM | FB |  | 1000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | SPM | Jul 2026
2518-APL-SPM | UNIT-2 | MAYANK | HOOD | FB |  | 1500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | SPM | Jul 2026
2428-BMWIL-CGL | BOI-LL | TRIPURARI | EPC SENSOR ASSY.@ |  |  | 8000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI-LL | TRIPURARI | CPC SENSOR ASSY.@ STEERING ASSY. |  |  |  | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Furnace Exhaust Ducting |  |  | 1500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Furnace Gas and Combustion Air Piping |  |  | 1900000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Furnace Dilution Air Piping |  |  | 500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Furnace Interconnecting Piping |  |  | 2500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | Throat Assembly |  |  | 2000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | JCF Assembly |  |  | 4000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | Ducting |  |  | 700000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | Heat Exchanger |  |  | 2000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | Down Chute |  |  | 1500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Pot cellar Ventilation Supply Ducting |  |  | 400000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Pot cellar Ventilation Exhaust Ducting |  |  | 400000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Moving Pendant assembly |  |  | 2000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Moving Trolley |  |  | 3000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Up Pass Pendant-1 (Future) |  |  | 1200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Cooling pendant assembly-Slot (Future) |  |  | 0 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Up Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Up Pass Pendant-3 |  |  | 1200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Down Pass Pendant-1 |  |  | 1200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Down Pass Pendant-2 |  |  | 1200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Cooling pendant assembly-Hole |  |  | 0 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Non-Ox Burners |  |  | 2000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Radiant Tube Burner With Recuperator |  |  | 1000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Post Combustion Burner |  |  | 2000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Ignition Cable |  |  | 200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Ratio Regulators |  |  | 200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | UV Sensors |  |  | 200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | UV Flame Switches |  |  | 200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Ignition Transformers |  |  | 500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | JCF Heat Exchanger |  |  | 2000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Flow Switchs |  |  | 200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Thermocouple |  |  | 200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Temperature Transmitters |  |  | 600000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Compensating Cable |  |  | 200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | IR Pyrometers |  |  | 400000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Pressure Transmitters |  |  | 600000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Solenoid Shut-Off Valves |  |  | 400000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | H2 analyzer |  |  | 500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Dew Point Analyzer |  |  | 500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | O2 Analyzer |  |  | 500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Electric Heater |  |  | 3000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Glow Heater |  |  | 100000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Pressure Gauges |  |  | 100000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Orifice Plates |  |  | 1200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Rotameters |  |  | 100000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Pneumatic Shut-Off Valves |  |  | 1200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Hot Air Control Valve |  |  | 1400000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Adjustable Gas control valves |  |  | 400000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Fan |  |  | 1500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Radiant Tubes |  |  | 1500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Air knife Blower |  |  | 6000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Recuperator For Non-OX Furnace |  |  | 3000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Gearmotor |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | HNX Gas Station & Heater |  |  | 1500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | JCF Fan |  |  | 5300000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Furnace Bellows |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Hearth Roll Bearing |  |  | 500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Butterfly Valve |  |  | 700000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Ball Valve |  |  | 700000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Gate Valve |  |  | 700000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Globe Valve |  |  | 700000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Flow Control Valve |  |  | 1000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Check Valve |  |  | 700000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Main gas station |  |  | 1200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Propeller Shaft |  |  | 500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Couplings |  |  | 500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2511-GAURANG-6HI | BOI-LL | MAYANK | AC MOTOR POR,MILL DRIVE,ETR,DTR |  |  | 32710000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2026
2511-GAURANG-6HI | BOI | MAYANK | Geared spindle |  |  | 6603300 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2026
2514-GAURANG-CGL |  | SAURABH | BRIDLE ROLL ASSY.#7 |  |  | 3500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL |  | SAURABH | BRIDLE ROLL ASSY.#8 |  |  | 3500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL |  | SAURABH | BRIDLE ROLL ASSY.#9 |  |  | 3500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL |  | SAURABH | SUPPORT ROLL ASSY. |  |  | 3500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL |  | SAURABH | TENSIOMETER ASSY.#1 BEFORE FURNACE |  |  | 1000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | BOI | SAURABH | WATER QUENCHING TANK ASSY. |  |  | 2500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | BOI | SAURABH | WATER SPRAY UNIT |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL |  | SAURABH | VERTICAL SQUEEZE ROLL ASSY.@CAG |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL |  | SAURABH | VERTICAL CHEMICAL COATER ASSY. |  |  | 8000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | BOI | SAURABH | INDUCTION TYPE STRIP HEATER ASSY. |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | COATER & STRIP HEATER STRUCTURE |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | BOI-LL | SAURABH | SEAM WELDER ASSY. |  |  | 11000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | BOI | SAURABH | PULPIT |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | Furnace Structure-Bracings |  |  | 2500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | Furnace Structure-Staircases |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | Furnace Structure-Handrails |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | Furnace Structure-Chequered plates |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | CAG Structure-Beams |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | CAG Structure-Bracings |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | CAG Structure-Staircases |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | CAG Structure-Handrails |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | CAG Structure-Chequered plates |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL | BOI | SAURABH | Threading Needle Assembly |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL |  | SAURABH | DFF Assembly |  |  | 7700000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL |  | SAURABH | Throat Assembly |  |  | 3500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2514-GAURANG-CGL |  | SAURABH | SF Assembly |  |  | 5100000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CGL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | HOLD DOWN ROLL ASSY.#2 |  |  | 600000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#6 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#7 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#8 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#9 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#10 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#11 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#12 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#13 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#14 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#15 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#16 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#17 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#18 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#19 |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#20 WITH ROLLERS |  |  | 200000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | ENTRY SHEAR 2 Nos |  |  | 2000000 | Not Disp. | 2026-07-28 |  | FALSE | TRUE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | EXIT SHEAR |  |  | 1000000 | Not Disp. | 2026-07-28 |  | FALSE | TRUE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PINCH CUM LEVELLER ROLL ASSY.#1 WITH BASE FRAME |  |  | 4000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PINCH CUM LEVELLER ROLL ASSY.#2 WITH BASE FRAME |  |  | 4000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY SIDE GUIDE ASSY.#1 WITH BASE FRAME |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY SIDE GUIDE ASSY.#2 WITH BASE FRAME |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT SIDE GUIDE ASSY.#3 WITH BASE FRAME |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#1 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#2 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#3 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#4 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH ROLL ASSY.#5 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH ROLL ASSY.#6 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH CUM DEF. ROLL ASSY.#1 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH CUM DEF. ROLL ASSY.#2 WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | TENSIONER ROLL ASSY. WITH BASE FRAME |  |  | 3000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | BOI | ADITYA SAINI | OIL SPRAYING ASSY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | EPC |  |  | 3000000 | Not Disp. | 2026-07-28 |  | TRUE | TRUE | [5 empty] | APL | Jul 2026
2516-APL-5 TANK PICKLING | STRUCTURE | ADITYA SAINI | STRUCTURE |  |  | 10000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | HOLD DOWN ROLL ASSY. |  |  | 400000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PINCH CUM LEVELLER ROLL ASSY.#1 WITH BASE FRAME |  |  | 2000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PINCH CUM LEVELLER ROLL ASSY.#2 WITH BASE FRAME |  |  | 2000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#1 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#2 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#3 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#4 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH ROLL ASSY.#5 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH ROLL ASSY.#6 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH ROLL ASSY.#7 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH ROLL ASSY.#8 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH CUM DEF. ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | BURR MASHER ROLL ASSY. WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | SINGLE SQUEEZE ROLL ASSY. WITH BASE FRAME |  |  | 5500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | DOUBLE SQUEEZE ROLL ASSY. WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | BOI | ADITYA SAINI | AIR WIPER ASSY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | HOT AIR DRYER ASSY. |  |  | 2000000 | Not Disp. | 2026-07-28 |  | TRUE | TRUE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | SUPPORT ROLL ASSY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | SLITTER HEAD ASSY. WITH BASE FRAME |  |  | 3000000 | Not Disp. | 2026-07-28 |  | TRUE | TRUE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | SCRAP OSCILLATOR ASSY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | SCRAP WINDER ASSY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | DEBURRING ROLL ASSY. WITH BASE FRAME |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | TENSIONER ROLL ASSY. WITH BASE FRAME |  |  | 2000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | BOI | ADITYA SAINI | OIL SPRAYING ASSY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | EPC |  |  | 3000000 | Not Disp. | 2026-07-28 |  | TRUE | TRUE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | STRUCTURE | ADITYA SAINI | STRUCTURE |  |  | 5000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | ACID RECIRCULATION SYSTEM |  |  | 18000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | FIVE STAGE RINSING TANK WITH RECIRCULATION SYSTEM |  |  | 5000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | HYDRAULIC POWER PACK & VALVE STAND |  |  | 7000000 | Not Disp. | 2026-07-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | ACID PROOF FLOOR LINNING |  |  | 2000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | BOI | ADITYA SAINI | PRESSURE REDUCING STATION |  |  | 2000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2533-BMWIL-4 TANK PICKLING | BOI | ADITYA SAINI | CONDENSATE RECOVERY SYSTEM |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jul 2026
2602-BMWIL-SLITTING |  | OM DEV | PINCH CUM LEVELLER ROLL ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jul 2026
2602-BMWIL-SLITTING |  | OM DEV | SCRAP OSCILLATOR |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jul 2026
2602-BMWIL-SLITTING | BOI-LL | OM DEV | HYDRAULIC SYSTEM-VALVE STAND |  |  | 3500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | SLITTING | Jul 2026
2534-BMWIL-TRIMMING |  | KUNAL | PINCH CUM DEFLECTOR ROLL ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | Jul 2026
2534-BMWIL-TRIMMING |  | KUNAL | DEBURRING ROLL ASSEMBLY. |  |  | 1200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2026
2534-BMWIL-TRIMMING |  | KUNAL | EXIT PINCH CUM DEFLECTOR ROLL ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | Jul 2026
2534-BMWIL-TRIMMING |  | KUNAL | SCRAP BAILER ASSEMBLY. |  |  | 700000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2026
2534-BMWIL-TRIMMING | BOI-LL | KUNAL | HYDRAULIC SYSTEM |  |  | 4000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2026
2534-BMWIL-TRIMMING | ELECTRICAL | KUNAL | ELECTRICAL |  |  | 4400000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | BRIDLE ROLL ASSY.#1 |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | BRIDLE ROLL ASSY.#2 |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | BRIDLE ROLL ASSY.#3 |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | BRIDLE ROLL ASSY.#4 |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | BRIDLE ROLL ASSY.#5 |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | DOUBLE DECKER SHEAR ASSY. |  |  | 500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | EXIT SHEAR ASSY. |  |  | 500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | ENTRY PINCH ROLL ASSY.#1 |  |  | 300000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | ENTRY PINCH ROLL ASSY.#2&3 |  |  | 300000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | ENTRY PINCH ROLL ASSY.#4 |  |  | 300000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | EXIT PINCH ROLL ASSY. |  |  | 300000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SINGLE SQUEEZE ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SINGLE SQUEEZE ROLL ASSY. |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | DEGREASING TANK ASSY |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | TRUE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | BRUSHING TANK ASSY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | TRUE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | HOT RINSING TANK ASSY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | TRUE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | PRIME QUENCHING TANK ASSY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | TRUE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | FINISH QUENCHING TANK ASSY. |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | TRUE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | BRUSHING ROLL ASSY.#1 |  |  | 300000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | BRUSHING ROLL ASSY.#2 |  |  | 300000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | AIR KNIFE ASSEMBLY |  |  | 300000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | CHEMICAL DRYER ASSEMBLY |  |  | 300000 | Not Disp. | 2026-07-28 |  | TRUE | TRUE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | AIR COOLING SECTION ASSEMBLY @ PRIME QUENCH TANK |  |  | 300000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | AIR COOLING SECTION ASSEMBLY @ FINISH QUENCH TANK |  |  | 300000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | CHEMICAL COATER ASSY. |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | PRIME COATER ASSY. |  |  | 1500000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | FINISH OVEN |  |  | 1000000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | STRUCTURE | TRIPURARI | OVEN STRUCTURE |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | STRUCTURE | TRIPURARI | CHEMICAL COATER STRUCTURE |  |  | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | BOI | TRIPURARI | PRINTER |  |  | 100000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | ELECTRICAL | TRIPURARI | ELECTRICAL |  |  | 3000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CCL | Jul 2026
2529-KHUSHBOO-CCL | BOI | TRIPURARI | PULPIT |  |  | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CCL | Jul 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | POR-OBBS ASSY |  | 4008.1653 | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CRM | Jul 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | ETR-OBBS ASSY |  | 3352.5102 | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CRM | Jul 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | DTR-OBBS ASSY |  | 3352.5102 | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CRM | Jul 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | THREE ROLL FEEDER ALONG WITH PASSING TABLE |  | 60000 | 1500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CRM | Jul 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | BACKUP STOOL |  | 1532.7256 | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CRM | Jul 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | BACKUP ROLL PULLING TROLLY |  | 4000 | 500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | CRM | Jul 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | PINION GEARBOX ASSEMBLY |  | 75000 | 4000000 | Not Disp. | 2026-07-28 |  | TRUE | TRUE | [5 empty] | CRM | Jul 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | Roll Coolant System |  | 128000 | 10700000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | COOLANT SYSTEM |  |  | LC | 7769700 | CRM | Jul 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | AIR OIL LUBRICATION SYSTEM ASSY |  | 44375 | 4000000 | Not Disp. | 2026-07-28 |  | FALSE | TRUE |  |  |  | PAYMENT | 3124000 | CRM | Jul 2026
2601-BMWIL - 6HI CRM | BOI | MAYANK | HYDRAULIC PIPES |  | 35000 | 2200000 | Not Disp. | 2026-07-28 |  | FALSE | TRUE | [5 empty] | CRM | Jul 2026
2601-BMWIL - 6HI CRM | BOI | MAYANK | HYDRAULIC FITTINGS |  | 35000 | 1700000 | Not Disp. | 2026-07-28 |  | FALSE | TRUE | [5 empty] | CRM | Jul 2026
2601-BMWIL - 6HI CRM | BOI | MAYANK | COOLANT PIPES & FITTINGS |  | 25000 | 2200000 | Not Disp. | 2026-07-28 |  | FALSE | TRUE | [5 empty] | CRM | Jul 2026
2601-BMWIL - 6HI CRM | BOI | MAYANK | PNEUMATIC PIPES & FITTINGS |  | 3750 | 500000 | Not Disp. | 2026-07-28 |  | FALSE | TRUE | [5 empty] | CRM | Jul 2026
2519-APL-CGL | BOI | ADITYA SHARMA | COIL CAR ASSY. @ UNCOILER |  |  | 2000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2519-APL-CGL |  | ADITYA SHARMA | DRAG CHAIN ASSY. @ UNCOILER |  |  | 200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2519-APL-CGL |  | ADITYA SHARMA | COIL SADDLE ASSY. @ UNCOILER |  |  | 200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2519-APL-CGL | BOI | ADITYA SHARMA | COIL CAR ASSY. @ RECOILER |  |  | 1000000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2519-APL-CGL |  | ADITYA SHARMA | DRAG CHAIN ASSY. @ RECOILER |  |  | 200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2519-APL-CGL |  | ADITYA SHARMA | COIL SADDLE ASSY. @ RECOILER |  |  | 200000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2026
2544-APL-REWINDING |  | KUNAL | PINCH ROLL ASSEMBLY. |  |  | 300000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | APL | Jul 2026
2544-APL-REWINDING | BOI-LL | KUNAL | ENTRY SHEAR ASSY. |  |  | 800000 | Not Disp. | 2026-07-28 |  | FALSE | TRUE | [5 empty] | APL | Jul 2026
2544-APL-REWINDING | BOI-LL | KUNAL | EXIT SHEAR ASSY. |  |  | 800000 | Not Disp. | 2026-07-28 |  | FALSE | TRUE | [5 empty] | APL | Jul 2026
2544-APL-REWINDING |  | KUNAL | SIDE GUIDE ASSEMBLY. |  |  | 300000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | APL | Jul 2026
2544-APL-REWINDING |  | KUNAL | PRESSURE PAD ASSEMBLY. |  |  | 300000 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | APL | Jul 2026
2544-APL-REWINDING |  | KUNAL | PASSING TABLE ASSEMBLY.#1 |  |  | 100000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2544-APL-REWINDING |  | KUNAL | PASSING TABLE ASSEMBLY.#2 |  |  | 100000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2544-APL-REWINDING |  | KUNAL | PASSING TABLE ASSEMBLY.#3 |  |  | 100000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | APL | Jul 2026
2607-JSW-SPARE |  |  | SPARE |  |  | 9500000 | Not Disp. | 2026-07-28 |  | TRUE | FALSE | [5 empty] | SPARE | Jul 2026
2608-BMWIL-CRM (SPARE) |  |  | SPARE |  |  | 37658824.5763 | Not Disp. | 2026-07-28 |  | FALSE | FALSE | [5 empty] | SPARE | Jul 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | EXIT PINCH CUM DEFLECTOR ROLL ASSY. |  | 15000 | 1350000 | Not Disp. | 2026-06-30 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | SIDE GUIDE ASSEMBLY | FB |  | 700000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | ENTRY DEFLECTOR ROLL WITH MILL TABLE | FB |  | 800000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | EXIT DEFLECTOR CUM TURN DOWN ROLL ASSEMBLY | FB |  | 800000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | C-FRAME (1 SET) | FB |  | 400000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | ANTI-CRIMP ROLL ASSEMBLY | FB |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | MILL HOUSING WITH LINERS |  |  | 35000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | BED PLATE |  |  | 4000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | TOP SEPARATOR | FB |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | TAPER WEDGE ASSEMBLY | FB |  | 3000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | TOP BACKUP CHOCK (WITHOUT CHOCK BEARING & ROLLS) |  |  | 3000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | BOTTOM BACKUP CHOCK (WITHOUT CHOCK BEARING & ROLLS) |  |  | 3000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | BACKUP CLAMP ASSEMBLY | FB |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | TOP WORK ROLL CHOCK (WITHOUR CHOCK BEARINGS & ROLLS) |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | BOTTOM WORK ROLL CHOCK (WITHOUT CHOCK BEARINGS & ROLLS) |  |  | 1200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | WORK ROLL CLAMP ASSEMBLY | FB |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | MAEWEST BLOCK ASSEMBLY |  |  | 4000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | BOI-LL | MAYANK | ROLL FORCE CYLINDER |  |  | 6000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | SPINDLE SUPPORT ASSEMBLY | FB |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | WORK ROLL INSIDE TRACK | FB |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-3 | MAYANK | QWRC ASSEMBLY WITH SAFETY CAGE | FB |  | 4000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | BACKUP INSIDE TRACK | FB |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | BACKUP OUTSIDE TRACK | FB |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | SHUTTER ASSEMBLY | FB |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | WINDOW EQUIPMENT (LECHLER) |  |  | 2500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2518-APL-SPM | UNIT-1 | MAYANK | MISC |  |  | 1200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPM | Jun 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | BRIDLE ROLL ASSY.#2 |  |  | 3100000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | BRIDLE ROLL ASSY.#5 (03 ROLLS) |  |  | 4500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | SUPPORT ROLL ASSY. |  |  | 1500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | TENSIOMETER ASSY.#1 BEFORE FURNACE |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | VERTICAL SQUEEZE ROLL ASSY.@CAG |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | BOI | TRIPURARI | INDUCTION TYPE STRIP HEATER ASSY. |  |  | 4000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | COATER & STRIP HEATER STRUCTURE |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | BOI-LL | TRIPURARI | SEAM WELDER ASSY. |  |  | 11000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | BOI | TRIPURARI | PULPIT |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | CAG Structure-Beams |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | CAG Structure-Bracings |  |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | CAG Structure-Staircases |  |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | CAG Structure-Handrails |  |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | CAG Structure-Chequered plates |  |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | BOI | TRIPURARI | Threading Needle Assembly |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | DFFAssembly With Refractory |  |  | 6000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | RTF Assembly |  |  | 6000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | SF Assembly |  |  | 5000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2511-GAURANG-6HI |  | MAYANK | QWRC TROLLEY ASSY | FB |  | 4200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2511-GAURANG-6HI | BOI | MAYANK | ROLL FORCE CLY ASSY |  |  | 4140000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2511-GAURANG-6HI | BOI-LL | MAYANK | CPC |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2511-GAURANG-6HI |  | MAYANK | SPARE-WORK ROLL CHOCKS-1set |  |  | 1600000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2511-GAURANG-6HI |  | MAYANK | SPARE-IMR ROLLS CHOCKS-1set |  |  | 1600000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2511-GAURANG-6HI |  | MAYANK | SPARE-WORK ROLL CHOCKS-3 set |  |  | 3200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2511-GAURANG-6HI |  | MAYANK | SPARE-IMR ROLLS CHOCKS-1 set |  |  | 1600000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2511-GAURANG-6HI |  | MAYANK | SPARE-BACKUP ROLL CHOCKS-1 set |  |  | 6000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | JCF Heat Exchanger |  |  | 2000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Air knife Blower |  |  | 9000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | UNCOILER MANDREL ASSY.#1 |  |  | 3000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | UNCOILER GEAR BOX ASSY.#1 |  |  | 5000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | UNCOILER SNUBBER ROLL ASSY.#1 |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | UNCOILER MANDREL ASSY.#2 |  |  | 3000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | UNCOILER GEAR BOX ASSY.#2 |  |  | 5000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | UNCOILER SNUBBER ROLL ASSY. #2 |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | RECOILER MANDREL ASSY. |  |  | 4000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | RECOILER GEAR BOX ASSY. |  |  | 6000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | RECOILER PUSHER PLATE ASSY. |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | RECOILER BELT WRAPPPER ASSY. |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | RECOILER SLEEVE LOADER ASSY. |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | PEELER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | PEELER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | PASSING TABLE ASSY#1 (D.D. SHEAR & PINCH ROLL#1) |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | PASSING TABLE ASSY#2 (D.D. SHEAR & PINCH ROLL#3) |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY SCRAP DOWN TABLE ASSY#1 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY SCRAP DOWN TABLE ASSY#2 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY SCRAP TRAY ASSY. |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY& EXIT SCRAP CAR ASSY. |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | PASSING TABLE ASSY#3 (BEFORE PINCH ROLL#4) |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | PASSING TABLE ASSY#4 (PINCH ROLL#4 & SEAM WELDER) |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | PASSING TABLE ASSY#5 (SEAM WELDER & PINCH ROLL#5) |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | PASSING TABLE ASSY#6 (PINCH ROLL#5 & STRIP CLAMP#1) |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | PASSING TABLE ASSY#7 (BEFORE FURNACE) |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | PASSING TABLE ASSY#7 (TURNUP & DOWN ASSY. ) |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | INSPECTION TABLE ASSY. |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | BRIDLE ROLL ASSY.#4 |  |  | 3500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | BRIDLE ROLL ASSY.#5 (03 ROLLS) |  |  | 4500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | BRIDLE ROLL ASSY.#6 |  |  | 3500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | ENTRY ACCUMULATOR STRUCTURE |  |  | 2000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY ACCUMULATOR TOP FRAME |  |  | 5000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY ACCUMULATOR COUNTER WEIGHT ASSEMBLY |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | EXIT ACCUMULATOR STRUCTURE |  |  | 2000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | EXIT ACCUMULATOR TOP FRAME |  |  | 5000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | EXIT ACCUMULATOR COUNTER WEIGHT ASSEMBLY |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | TENSIOMETER ASSY.#2 BEFORE TLL |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | BOI | SAURABH | AIR WIPPING EQUIPMENT |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | TURN UP ROLL ASSY. @CAG |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | TURN DOWN ROLL ASSY. @CAG |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | SINGLE SQUEEZE ROLL ASSY.@SPM |  |  | 2000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | BOI | SAURABH | COLD AIR DRYER @ CAG |  |  | 700000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | BOI | SAURABH | AIR DRYER @ SPM |  |  | 700000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | BOI | SAURABH | LOGO DRYER @ LOGO MARKER |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | BOI | SAURABH | AIR COOLER@ STRIP HEATER |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | CHILL ROLL ASSY. #1 |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | CHILL ROLL ASSY. #2 |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | BOI | SAURABH | LOGO MARKER ASSY |  |  | 2000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#01 (AFTER STEERING ASSY#02) |  |  | 400000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#02 (AFTER CAG) |  |  | 400000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#03 (AFTER EXIT ACC ASSY.) |  |  | 400000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | BOI | SAURABH | HYDRAULIC PIPES & FITTINGS |  |  | 4000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | ELECTRICAL | SAURABH | ELECTRICAL |  |  | 45000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | Furnace Structure - Columns |  |  | 10000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | Furnace Structure-Beams |  |  | 5000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL | STRUCTURE | SAURABH | CAG Structure - Columns |  |  | 1500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | Entry Seal Assembly |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | Tunnel Assembly |  |  | 7000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2514-GAURANG-CGL |  | SAURABH | HBR Assembly |  |  | 16000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CGL | Jun 2026
2501-AL SHAKER-6HI CRM | BOI-LL | MAYANK | THICKNESS GAUGE |  | 100000 | 8950000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | RECOILER-MANDREL, GEARBOX, PUSHER PLATE ASSY |  | 45000 | 4050000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | O.B.B.S ASSY. FOR UNCOILER#2 |  |  | 600000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | O.B.B.S ASSY.#1 |  |  | 600000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | HOLD DOWN ROLL ASSY.#1 |  |  | 600000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | O.B.B.S ASSY.#2 |  |  | 600000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PEELER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PEELER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT SCRAP DOWN TABLE WITH HYDRAULIC CYLINDER |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT THREADING TABLE#1 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT THREADING TABLE#2 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | SCRAP TROLLEY 3 Nos |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY LOOPER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY LOOPER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT LOOPER TABLE ASSY.#3 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT LOOPER TABLE ASSY.#4 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#1 WITH ROLLERS |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#2 WITH ROLLERS |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#3 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#4 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#5 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | SINGLE SQUEEZE ROLL ASSY. 13 Nos WITH BASE FRAME |  |  | 11000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | DOUBLE SQUEEZE ROLL ASSY. 2 Nos WITH BASE FRAME |  |  | 4500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | AIR WIPER ASSY. |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | HOT AIR DRYER ASSY. |  |  | 2000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | SUPPORT ROLL ASSY. -2 Nos |  |  | 1500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL CAR ASSY.#1 |  |  | 1500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL CAR ASSY.#2 |  |  | 1500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL CAR ASSY.#1 |  |  | 1500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | O.B.B.S ASSY. FOR UNCOILER#2 |  |  | 400000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | O.B.B.S ASSY. |  |  | 400000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PEELER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PEELER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY SCRAP DOWN TABLE WITH HYDRAULIC CYLINDER |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT SCRAP DOWN TABLE WITH HYDRAULIC CYLINDER |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT THREADING TABLE |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | SCRAP TROLLEY |  |  | 400000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY LOOPER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY LOOPER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT LOOPER TABLE ASSY.#3 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT LOOPER TABLE ASSY.#4 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#12 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#13 |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#14 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#15 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#16 |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#17 |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#18 |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#19 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#20 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#21 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#22 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#23 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#24 |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#25 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#26 |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | ENTRY SHEAR |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | EXIT SHEAR |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | TRUE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY SIDE GUIDE ASSY.#1 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY SIDE GUIDE ASSY.#2 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT SIDE GUIDE ASSY.#3 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT SIDE GUIDE ASSY.#4 WITH BASE FRAME |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | ELECTRICAL | ADITYA SAINI | ELECTRICAL |  |  | 8500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | PRE WASH TANK |  |  | 2500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | BOI-LL | ADITYA SAINI | PICKLING TANK 1, 2, 3 & 4 |  |  | 10000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2533-BMWIL-4 TANK PICKLING | BOI | ADITYA SAINI | HYDRAULIC & PNEUMATIC FITTINGS |  |  | 3000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2602-BMWIL-SLITTING | BOI-LL | OM DEV | ENTRY SHEAR ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | TRUE | [5 empty] | SLITTING | Jun 2026
2602-BMWIL-SLITTING | BOI-LL | OM DEV | EXIT SHEAR ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | TRUE | [5 empty] | SLITTING | Jun 2026
2602-BMWIL-SLITTING |  | OM DEV | PINCH ROLL ASSEMBLY.#1 |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jun 2026
2602-BMWIL-SLITTING |  | OM DEV | DEBURRING ROLL ASSEMBLY. |  |  | 1200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jun 2026
2602-BMWIL-SLITTING |  | OM DEV | ENTRY DEFLECTOR ROLL ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jun 2026
2602-BMWIL-SLITTING |  | OM DEV | EXIT DEFLECTOR ROLL ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jun 2026
2602-BMWIL-SLITTING |  | OM DEV | INLINE SEPARATOR ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jun 2026
2602-BMWIL-SLITTING |  | OM DEV | OVER ARM SEPERATOR ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jun 2026
2602-BMWIL-SLITTING |  | OM DEV | PRESSURE PAD ASSEMBLY.(EXIT) |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jun 2026
2602-BMWIL-SLITTING |  | OM DEV | SCRAP WINDER ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | SLITTING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | ENTRY OBBS ASSEMBLY. |  |  | 250000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | OBBS ASSEMBLY. |  |  | 250000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING | BOI-LL | KUNAL | ENTRY SHEAR ASSY. |  |  | 900000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | SIDE GUIDE ASSEMBLY. |  |  | 1500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | TENSIONER ASSEMBLY. |  |  | 1000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | PEELER TABLE ASSEMBLY. |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | SCRAP DOWN TABLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE & SUIT ASSEMBLY. |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | THREADING TABLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | SCRAP TROLLEY ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#1 |  |  | 100000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#2 |  |  | 100000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#3 |  |  | 100000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#4 |  |  | 100000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#5 |  |  | 100000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | Jun 2026
2534-BMWIL-TRIMMING |  | KUNAL | PASSING TABLE ASSEMBLY.#6 |  |  | 100000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | UNCOILER OBBS ASSY |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | PEELER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | PEELER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | PASSING TABLE ASSY#1 |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | PASSING TABLE ASSY#2 |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | PASSING TABLE ASSY#3 |  |  | 200000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | PASSING TABLE ASSY#4 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SCRAP DOWN TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | EXIT THREADING TABLE ASSY. |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | DEFLECTOR ROLL ASSY.#2 |  |  | 300000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | DEFLECTOR ROLL ASSY.#3 |  |  | 300000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | DEFLECTOR ROLL ASSY.#6 |  |  | 300000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | DEFLECTOR ROLL ASSY.#7 |  |  | 300000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | DEFLECTOR ROLL ASSY.#8 |  |  | 300000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | DEFLECTOR ROLL ASSY.#9 |  |  | 300000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SUPPORT ROLL ASSY.#1 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SUPPORT ROLL ASSY.#2 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SUPPORT ROLL ASSY.#3 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SUPPORT ROLL ASSY.#4 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SUPPORT ROLL ASSY.#5 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SUPPORT ROLL ASSY.#6 |  |  | 200000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SINGLE STEERING ROLL ASSY.#1 |  |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SINGLE STEERING ROLL ASSY.#2 (BEFORE FINISH COATER) |  |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | SINGLE STEERING ROLL ASSY.#3 |  |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | FINISH COATER 'A' ASSY. |  |  | 1500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | FINISH COATER 'B' ASSY. |  |  | 1500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL | BOI-LL | TRIPURARI | PRIME OVEN |  |  | 1000000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL | BOI | TRIPURARI | FOUNDATION BOLT |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL | BOI | TRIPURARI | TAPER PLATE |  |  | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CCL | Jun 2026
2529-KHUSHBOO-CCL | BOI | TRIPURARI | HYDRAULIC & PNEUETIC FITTINGS |  |  | 500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2026
2601-BMWIL - 6HI CRM | BOI | MAYANK | FOUNDATION BOLTS + TAPER PLATES SET |  | 22258.25 | 2000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | UNIT-2 | MAYANK | COOLANT TRAY |  | 10000 | 1500000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | COIL CAR @ POR, ETR & DTR |  | 99000 | 3000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | DRAG CHAIN @ POR, ETR & DTR |  | 7101.675 | 900000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | COIL SADDLE @ POR, ETR & DTR |  | 5578.783 | 900000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | PIT COVER @ POR, ETR & DTR |  | 7075.8563 | 900000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | MOTOR BASE FRAME (PINION, ETR & DTR) |  | 30000 | 3500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | PEELER TABLE ASSY |  | 2000 | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | CARRY OVER TABLE |  | 5421.1858 | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | TILTING TABLE ASSY. AT ETR |  | 3796.8443 | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | UNIT-1 | MAYANK | TILTINGTABLE ASSY. AT DTR |  | 3796.8443 | 500000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | ELECTRICAL | MAYANK | ELECTRICAL PACKAGE |  | 375000 | 80000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | BACKUP CHOCK BEARINGS - 4 NOS |  | 80000 | 7000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | IMR CHOCK BEARINGS - 4NOS |  | 12000 | 600000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | WORK ROLL CHOCK BEARINGS - 4 NOS |  | 8000 | 300000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | ENTRY SHEAR ASSY |  | 11875 | 1100000 | Not Disp. | 2026-06-28 |  | TRUE | TRUE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | FUME EXHAUST SYSTEM |  | 56386.25 | 5000000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2026
2601-BMWIL - 6HI CRM | BOI-LL | MAYANK | GEAR LUBRICATION SYSTEM ASSY |  | 15000 | 1400000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE |  |  |  | PAYMENT / LC | 961200 | CRM | Jun 2026
2606-SHYAM-SPARE |  |  | SPARE |  |  | 24800000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | SPARE | Jun 2026
2544-APL-REWINDING |  | KUNAL | ENTRY OBBS ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2544-APL-REWINDING |  | KUNAL | OBBS ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2544-APL-REWINDING |  | KUNAL | PEELER TABLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2544-APL-REWINDING |  | KUNAL | THREADING TABLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2544-APL-REWINDING | BOI | KUNAL | FOUNDATION BOLTS |  |  | 400000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2544-APL-REWINDING | BOI | KUNAL | TAPER (LEVELLING) PLATE |  |  | 400000 | Not Disp. | 2026-06-28 |  | TRUE | FALSE | [5 empty] | APL | Jun 2026
2544-APL-REWINDING | BOI | KUNAL | INTERCONNECTING PIPING |  |  | 700000 | Not Disp. | 2026-06-28 |  | FALSE | FALSE | [5 empty] | APL | Jun 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | UNCOILER-MANDREL, GEARBOX, SNUBBER ASSY (STEPPED CONE TYPE)#1 |  | 52000 | 4680000 | Not Disp. | 2026-06-25 |  | FALSE | FALSE | [5 empty] | PICKLING | Jun 2026
2518-APL-SPM | UNIT-3 | MAYANK | DRAG CHAIN @ UNCOILER | FB |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-3 | MAYANK | COIL SADDLE @ UNCOILER | FB |  | 300000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-3 | MAYANK | PIT COVER @ UNCOILER | FB |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | UNCOILER MANDREL ASSEMBLY |  |  | 7000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  | 1626984 |  |  | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | UNCOILER GEARBOX ASSEMBLY | FB |  | 8500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  | 6604066 |  |  | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | SNUBBER WITH BENDING ROLL ASSEMBLY | FB |  | 2000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | OBBS @ UNCOILER | FB |  | 300000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | PEELER TABLE | FB |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | SCRAP DOWN TABLE | FB |  | 300000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | EXIT THREADING TABLE | FB |  | 300000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | PINCH CUM LEVELER ASSEMBLY | FB |  | 3000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | BOI-LL | MAYANK | BACKUP ROLLS (2 NOS.) |  |  | 11500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | BOI-LL | MAYANK | WORK ROLLS (2 NOS.) |  |  | 3000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-2 | MAYANK | CATCHMENT TRAY | FB |  | 1500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | MILL DRIVE ASSEMBLY (WITHOUT MOTOR & SPINDLE COUPLING) |  |  | 9000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  | 2985120 |  |  | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | SCRAP TROLLEY | FB |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-3 | MAYANK | PIT COVER @ RECOILER | FB |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | RECOILER MANDREL ASSEMBLY |  |  | 6000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  | 1394087 |  |  | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | RECOILER GEARBOX ASSEMBLY |  |  | 9500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  | 6391440 |  |  | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | PUSHER PLATE ASSEMBLY | FB |  | 1500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | OBBS @ RECOILER | FB |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | UNIT-1 | MAYANK | HOLD DOWN ROLL ASSEMBLY | FB |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | BOI | MAYANK | CELLAR VENTILATION SYSTEM |  |  | 1700000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2518-APL-SPM | BOI | MAYANK | FOUNDATION BOLTS & TAPER PLATES |  |  | 5000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SPM | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | RECOILER EXIT OBBS ASSY. |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | RECOILER BELT WRAPPPER ASSY. |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | RECOILER SLEEVE LOADER ASSY. |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | PEELER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | PEELER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | PASSING TABLE ASSY#1 (D.D. SHEAR & PINCH ROLL#1) |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | PASSING TABLE ASSY#2 (D.D. SHEAR & PINCH ROLL#3) |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY SCRAP DOWN TABLE ASSY#1 |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY SCRAP DOWN TABLE ASSY#2 |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY SCRAP TRAY ASSY. |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | PASSING TABLE ASSY#3 (BEFORE PINCH ROLL#4) |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | PASSING TABLE ASSY#4 (PINCH ROLL#4 & SEAM WELDER) |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | PASSING TABLE ASSY#5 (SEAM WELDER & PINCH ROLL#5) |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | PASSING TABLE ASSY#6 (PINCH ROLL#5 & STRIP CLAMP#1) |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | PASSING TABLE ASSY#7 (BEFORE FURNACE) |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | PASSING TABLE ASSY#7 (TURNUP & DOWN ASSY. ) |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ROLLER TABLE ASSY. |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | DOUBLE STEERING ROLL ASSY. @ CAG |  |  | 3000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | TENSIOMETER ASSY.#2 BEFORE TLL |  |  | 1000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | BOI | TRIPURARI | AIR WIPPING EQUIPMENT |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | TURN UP ROLL ASSY. @CAG |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | TURN DOWN ROLL ASSY. @CAG |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | SINGLE SQUEEZE ROLL ASSY.@SPM |  |  | 2000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | BOI | TRIPURARI | COLD AIR DRYER @ CAG |  |  | 700000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | BOI | TRIPURARI | AIR DRYER @ SPM |  |  | 700000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | BOI | TRIPURARI | LOGO DRYER @ LOGO MARKER |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | VERTICAL CHEMICAL COATER ASSY. |  |  | 8000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | BOI | TRIPURARI | AIR COOLER@ STRIP HEATER |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | CHILL ROLL ASSY. #1 |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | CHILL ROLL ASSY. #2 |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | BOI | TRIPURARI | LOGO MARKER ASSY |  |  | 2000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | BASE FRAME CPC SENSOR ASSY. |  |  | 0 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | WELD HOLE DETECTOR ASSY.#01 (AFTER STEERING ASSY#02) |  |  | 400000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | WELD HOLE DETECTOR ASSY.#02 (AFTER CAG) |  |  | 400000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | WELD HOLE DETECTOR ASSY.#03 (AFTER EXIT ACC ASSY.) |  |  | 400000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | BOI-LL | TRIPURARI | HYDRAULIC SYSTEM-POWER PACK |  |  | 13500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | BOI | TRIPURARI | HYDRAULIC PIPES & FITTINGS |  |  | 4000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | Furnace Structure-Beams |  |  | 5000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | Furnace Structure-Bracings |  |  | 2500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | Furnace Structure-Staircases |  |  | 1500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | Furnace Structure-Handrails |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | Furnace Structure-Chequered plates |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | CAG Structure - Columns |  |  | 1500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | Entry Seal Assembly |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | Tunnel With Refractory |  |  | 4000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | HBR Assembly |  |  | 8000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2427-PROMPT-6HI CRM | UNIT-1 | MAYANK | ETR SAFETY CAGE |  |  |  | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2427-PROMPT-6HI CRM | UNIT-1 | MAYANK | DTR SAFETY CAGE |  |  |  | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2427-PROMPT-6HI CRM | UNIT-2 | MAYANK | TOP PLATFORM |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2427-PROMPT-6HI CRM | UNIT-2 | MAYANK | HOOD ASSY |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2427-PROMPT-6HI CRM | BOI | MAYANK | FUME EXHAUST & CELLAR VENTILATION DUCTING |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2427-PROMPT-6HI CRM | BOI-LL | MAYANK | CPC |  |  | 0 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  |  | LC | 806270 | CRM | May 2026
2427-PROMPT-6HI CRM | BOI | MAYANK | SPARE-Required Air Compressor in YD Scope |  |  | 5500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | QWRC SAFETY CAGE | FB |  |  | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | QWRC RAIL, CLAMP & BOLTS |  |  |  | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2521-BMWIL-6HI CRM | UNIT-2 | MAYANK | TOP PLATFORM | FB |  | 750000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2521-BMWIL-6HI CRM | UNIT-2 | MAYANK | HOOD ASSY | FB |  | 750000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | CELLAR VENTILATION SYSTEM WITH BLOWER ASSY |  |  | 700000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | FUME EXHAUST & CELLAR VENTILATION DUCTING |  |  | 2500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2521-BMWIL-6HI CRM | BOI-LL | MAYANK | CPC |  |  | 1074000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  |  | LC | 806270 | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | POR-COIL CAR |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | UNIT-3 | MAYANK | POR-COIL SADDLE | FB |  | 50000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | UNIT-3 | MAYANK | POR-COIL CAR PIT COVER | FB |  | 100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | ETR-COIL CAR |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | UNIT-3 | MAYANK | ETR-COIL SADDLE | FB |  | 50000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | UNIT-3 | MAYANK | ETR-COIL CAR PIT COVER | FB |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | DTR-COIL CAR |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | UNIT-3 | MAYANK | DTR-COIL SADDLE | FB |  | 50000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | UNIT-3 | MAYANK | DTR-COIL CAR PIT COVER | FB |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | POR-OBBS ASSY | FB |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | THREE ROLL FEEDER | FB |  | 2000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | PEELER TABLE ASSY | FB |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | CARRY OVER TABLE WITH ENTRY SHEAR | FB |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | ENTRY TILTING TABLE ASSY | FB |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | EXIT TILTING TABLE ASSY | FB |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | BACKUP STOOL ASSY. | FB |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | BACKUP ROLL PULLING TROLLY | FB |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | ETR-OBBS ASSY | FB |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | DTR-MANDREL ASSY,GEARBOX,PUSHER PLATE |  |  | 9000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | DTR-OBBS ASSY | FB |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI-LL | MAYANK | DELIVERY SHEAR ASSY |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI-LL | MAYANK | WORK ROLL - 2nos |  |  | 1220000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI-LL | MAYANK | BACK UP ROLL - 2nos |  |  | 10200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI-LL | MAYANK | IMR ROLL - 2nos |  |  | 1730000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | Back up roll chocks - 4 nos |  |  | 6000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | wr chocks - 4nos |  |  | 1600000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | Imr Chocks - 4 nos |  |  | 1600000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | IMR SHIFTING ASSY. | FB |  | 1800000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | SPINDLE SUPPORT ASSY | FB |  | 1500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | MILL HOUSING |  |  | 17500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | MAEWEST BLOCK ASSY. |  |  | 4500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | BED PLATE ASSY. |  |  | 2000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | ENTRY DEFLECTOR CUM TURN DOWN | FB |  | 800000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | ENTRY C FRAME | FB |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | DELIVERY DEFLECTOR CUM TURN DOWN | FB |  | 800000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | EXIT C FRAME | FB |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | PINION GEAR BOX |  |  | 4000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | TOP SEPARATOR ASSY. | FB |  | 100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | TOP PLATFORM | FB |  | 900000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | HOOD ASSY | FB |  | 900000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | FUME EXHAUST DUCT. |  |  | 2500000 | Not Disp. | 2026-05-28 |  | FALSE | TRUE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | SHUTTER ASSY | FB |  | 300000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | TAPER WEDGE ASSY | FB |  | 2582000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | ROLL COOLANT HEADER ASSY |  |  | 900000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | ENTRY AIR WIPER ASSY |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | BACKUP WIPER ASSY |  |  | 380000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | EXIT AIR WIPER ASSY |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | COBBLE GUARD ASSY |  |  | 1750000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | ENTRY SIDE GUIDE CUM PRESSURE PAD ASSY |  |  | 2380000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | ENTRY AIR KNIFE ASSY |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | EXIT AIR KNIFE ASSY |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | ENTRY PASSING TABLE @ MILL STAND |  |  | 187500 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | EXIT PASSING TABLE @ MILL STAND |  |  | 187500 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | INTER CONNECTING PIPING |  |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | DISTRIBUTION HEADERS |  |  | 615000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | CELLER VENTILATION SYSTEM WITH BLOWER ASSY |  |  | 860000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | CELLER VENTILATION DUCT |  |  | 600000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI | BOI | MAYANK | FOUNDATION BOLTS |  |  | 1404166 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | BACKUP INSIDE TRACK | FB |  | 100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | BACKUP OUTSIDE TRACK | FB |  | 100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2511-GAURANG-6HI |  | MAYANK | WORK ROLL & IMR INSIDE TRACK | FB |  | 100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#5 (PINCH ROLL#4 & SEAM WELDER) |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#6 (SEAM WELDER & PINCH ROLL#5) |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#7 (BEFORE ENTRY FURNACE) |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#8 (COOLING AFTER GALVANIZING) |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#9 (STRIP HEATER ASSY.) |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#10 (AFTER BRIDLE ASSY.#9) |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#11 (AFTER BRIDLE ASSY.#10) |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#12 (BEFORE EXIT SHEAR) |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | EXIT THREADING TABLE ASSY. |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | SUPPORT ROLL ASSY.-29 ASSY. |  |  | 1500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | SINGLE SQUEEZE ROLL ASSY.@ RINSE TANK-2 ASSY. |  |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | VERTICAL DOUBLE SQUEEZE ROLL ASSY.@CAG |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | VERTICAL DOUBLE SQUEEZE ROLL ASSY. @ CHROMATIC TANK |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI-LL | SAURABH | ECL TANK LOT 2 |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | TURN UP ROLL ASSY. @CAG |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | TURN DOWN ROLL ASSY. @CAG |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | MANUAL TINSEL SCRAPPER |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | CHILL ROLL ASSY. #1 |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | CHILL ROLL ASSY. #2 |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | STRIP INDUCTION HEATER ASSY. WITH DRYER |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | GA OF AIR COOLER |  |  | 4500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | LOGO MARKER ASSY-2 ASSY. |  |  | 2000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | HOT AIR DRYER ASSY.#1 @ CLEANING SECTION |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | COLD AIR DRYER @ CAG |  |  | 700000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | HOT AIR DRYER ASSY. @ CHROMATIC SECTION |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | LOGO DRYER @ LOGO MARKER |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#01 (BEFORE BRIDLE ROLL#3) |  |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#02 (AFTER CAG) |  |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | WELD HOLE DETECTOR ASSY.#03 (AFTER EXIT ACC ASSY.) |  |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI-LL | SAURABH | TENSION LEVELLER (TLL) |  |  | 15100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | SEMI AUTOMATIC STRIP STRAPPING MACHINE |  |  | 2000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | ECL TANK + HOLDING TANK + COMM SPARE |  |  | 15000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | THREADING NEEDLE ASSEMBLY |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | FURNACE EXHAUST DUCTING |  |  | 1500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | FURNACE GAS AND COMBUSTION AIR PIPING |  |  | 1900000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | FURNACE DILUTION AIR PIPING |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | FURNACE N2 & HNX PIPING |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | FURNACE INTERCONNECTING PIPING |  |  | 2500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ENTRY SEAL WITH REFRACTORY ASSY |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | TUNNEL -1 WITH EXHAUST CASING & REFRACTORY ASSY |  |  | 1300000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | TUNNEL -2 WITH REFRACTORY ASSY |  |  | 1300000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | TUNNEL -3 WITH MAIN DOOR & REFRACTORY ASSY |  |  | 1300000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DFF-1 WITH HEARTH ROLL & REF ASSEMBLY |  |  | 2500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DFF-2 WITH HEARTH ROLL & REF ASSEMBLY |  |  | 2500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | THROAT WITH HEARTH ROLL & REF ASSEMBLY |  |  | 2500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | RTF WITHOUT DOOR WITH HEARTH ROLL & REF ASSEMBLY 1, 2 |  |  | 4000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | RTF WITH DOOR WITH HEARTH ROLL & REF ASSEMBLY 1, 2 |  |  | 4000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | SF CASING WITH DOOR WITH HEARTH ROLL & REF ASSEMBLY |  |  | 2500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | SF CASING WITHOUT DOOR-1 WITH HEARTH ROLL & REF ASSEMBLY |  |  | 2500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | SF CASING WITHOUT DOOR-2 WITH HEARTH ROLL & REF ASSEMBLY |  |  | 4500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | STATIC SECTION WITH HEARTH ROLL & REF ASSEMBLY |  |  | 3000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | JCF WITH HEARTH ROLL & REF ASSEMBLY 1,2, 3 |  |  | 10500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | JCF DUCTING ASSEMBLY |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | HEAT EXCHANGER |  |  | 2000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | CALM ZONE ASSEMBLY |  |  | 3000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | DC |  |  | 1500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | POT CELLAR VENTILATION SUPPLY DUCTING |  |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | POT CELLAR VENTILATION EXHAUST DUCTING |  |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | ELECTRICAL | SAURABH | ELECTRICAL LOOSE SUPPLY |  |  | 2000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Flow Switchs |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Electric Heater |  |  | 3000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  |  | LC | 2546160 | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Glow Heater |  |  | 100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Pressure Gauges |  |  | 100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Orifice Plates |  |  | 1200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Rotameters |  |  | 100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  | 25724 |  |  | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Pneumatic Shut-Off Valves |  |  | 1200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Hot Air Control Valve |  |  | 1400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Adjustable Gas control valves |  |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Fan |  |  | 1500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Gearmotor |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | JCF Fan |  |  | 5300000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Propeller Shaft |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Couplings |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Furnace Bellows |  |  | 1500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Butterfly Valve |  |  | 700000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Ball Valve |  |  | 700000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Gate Valve |  |  | 700000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Globe Valve |  |  | 700000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Flow Control Valve |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Check Valve |  |  | 700000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Air knife ,Zinc Pump,Drosser |  |  | 10600000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  | 8517600 |  |  | CGL | May 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | INGOT FEEDING ARRANGEMENT |  |  | 1800000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | DRAG CHAIN ASSY. @ UNCOILER |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | COIL SADDLE ASSY. @ UNCOILER |  |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | DRAG CHAIN ASSY. @ RECOILER |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | COIL SADDLE ASSY. @ RECOILER |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | UNCOILER OBBS ASSY.#1 |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | UNCOILER OBBS ASSY.#2 |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | RECOILER EXIT OBBS ASSY. |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | EXIT THREADING TABLE ASSY. |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | BRIDLE ROLL ASSY.#1 |  |  | 3500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | BRIDLE ROLL ASSY.#2 |  |  | 3500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | BRIDLE ROLL ASSY.#3 |  |  | 3500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY ACCUMULATOR FIXED FRAME |  |  | 4000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY ACCUMULATOR MOVING FRAME |  |  | 3000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL | BOI | SAURABH | ENTRY ACCUMULATOR CHAIN |  |  | 2000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | EXIT ACCUMULATOR FIXED FRAME |  |  | 4000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | EXIT ACCUMULATOR MOVING FRAME |  |  | 3000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL | BOI | SAURABH | EXIT ACCUMULATOR CHAIN |  |  | 2000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | SINGLE STEERING ROLL ASSY. |  |  | 2000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | DOUBLE STEERING ROLL ASSY. @ CAG |  |  | 3000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#1 |  |  | 250000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#2 |  |  | 250000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#3 |  |  | 250000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#4 |  |  | 250000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#5 |  |  | 250000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | EXIT PINCH ROLL ASSY. #1 |  |  | 250000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | EXIT PINCH ROLL ASSY. #2 |  |  | 250000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#1 (AFTER BRIDLE ROLL ASSY.#1) |  |  | 250000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#2&3 (BEFORE & AFTER ENTRY ACC ASSY.) |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#4 (BEFORE COATING THICKNESS GAUGE) |  |  | 250000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#5 (AFTER BRIDLE ROLL ASY.#07) |  |  | 250000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#6&7 (BEFORE CHEMICAL COATER) |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#8 (BEFORE BRIDLE ROLL ASY.#08) |  |  | 250000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#9 (BEFORE LOGO MARKER) |  |  | 250000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL | BOI-LL | SAURABH | DOUBLE DECKER ENTRY SHEAR ASSY. |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL | BOI-LL | SAURABH | DELIVERY SHEAR ASSY. |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | STRIP CLAMP ASSY.#01 BEFORE BRIDLE ASSY#1 |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | STRIP CLAMP ASSY.#02 AFTER BRIDLE ASSY#2 |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL |  | SAURABH | STRIP CLAMP ASSY.#03 @ CAG |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL | BOI | SAURABH | FOUNDATION BOLT |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2514-GAURANG-CGL | BOI | SAURABH | TAPER PLATE |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2026
2501-AL SHAKER-6HI CRM | UNIT-2 | MAYANK | TOP PLATFORM | FB | 5000 | 447500 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2501-AL SHAKER-6HI CRM | UNIT-2 | MAYANK | HOOD ASSY | FB | 5362 | 479899 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2501-AL SHAKER-6HI CRM | UNIT-3 | MAYANK | QWRC TROLLEY ASSY WITH SAFETY CAGE | FB | 40000 | 3580000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | SPARE-BACKUP CHOCKS - 4 NOS |  | 20000 | 1790000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | SPARE-IMR CHOCKS - 4 NOS |  | 12000 | 1074000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | SPARE-WORK ROLL CHOCKS - 8 NOS |  | 16000 | 1432000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | CELLAR VENTILATION SYSTEM |  | 5000 | 447500 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | BACKUP ROLLS - 2 NOS |  | 104000 | 9308000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  | 8307416 |  |  | CRM | May 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | FUME EXHAUST AND CELLER VENTILATION DUCTING MATERIAL ONLY |  | 5000 | 447500 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2026
2501-AL SHAKER-6HI CRM | BOI-LL | MAYANK | CPC |  | 2000 | 179000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE |  |  |  | LC | 806270 | CRM | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | HOLD DOWN ROLL ASSY. |  | 2000 | 180000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | UNCOILER-MANDREL, GEARBOX, SNUBBER ASSY(OVERHANG TYPE) #2 |  | 40000 | 3600000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Hot Air Control Valve |  |  | 3620000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL CAR ASSY.#1 |  |  | 2000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY DRAG CHAIN ASSY.#1 |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL SADDLE#1 |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL CAR ASSY.#2 |  |  | 2000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY DRAG CHAIN ASSY.#2 |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL SADDLE#2 |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL CAR ASSY.#1 |  |  | 2000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT DRAG CHAIN ASSY.#1 |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL SADDLE #1 |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL CAR ASSY.#2 |  |  | 2000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT DRAG CHAIN ASSY.#2 |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL SADDLE #2 |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | BOI | ADITYA SAINI | FOUNDATION BOLTS |  |  | 1000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | BOI | ADITYA SAINI | TAPER (LEVELLING) PLATE |  |  | 1000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | ELECTRICAL | ADITYA SAINI | ELECTRICAL |  |  | 10000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | PRE WASH TANK |  |  | 3000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | PICKLING TANK 1, 2, 3, 4 & 5, SIX STAGE RINSING TANK, ACID PROOF LINING |  |  | 22000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | BOI-LL | ADITYA SAINI | ACID RECIRCULATION SYSTEM, FUME EXHAUST & SCRUBBING SYSTEM-Lot 2 |  |  | 11000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | BOI | ADITYA SAINI | HYDRAULIC & PNEUMATIC FITTINGS |  |  | 3000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | BOI | ADITYA SAINI | PRESSURE REDUCING STATION |  |  | 2000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | BOI | ADITYA SAINI | CONDENSATE RECOVERY SYSTEM |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2516-APL-5 TANK PICKLING | BOI | ADITYA SAINI | SAFETY SHOWERS (3 NOS.) |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY DRAG CHAIN ASSY.#1 |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL SADDLE#1 |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY DRAG CHAIN ASSY.#2 |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL SADDLE#2 |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT DRAG CHAIN ASSY.#1 |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL SADDLE#1 |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#3 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#4 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#5 |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#6 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#7 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#8 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#9 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#10 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLE ASSY.#11 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | BOI | ADITYA SAINI | FOUNDATION BOLTS |  |  | 1000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2533-BMWIL-4 TANK PICKLING | BOI | ADITYA SAINI | TAPER (LEVELLING) PLATE |  |  | 1000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | PICKLING | May 2026
2602-BMWIL-SLITTING | BOI | OM DEV | UNCOILER-COIL CAR |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | UNCOILER-DRAG CHAIN |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | UNCOILER-COIL SADDLE |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING | BOI | OM DEV | RECOILER-COIL CAR |  |  | 1000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | RECOILER-DRAG CHAIN |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | RECOILER OBBS. |  |  | 300000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | ENTRY SIDE GUIDE ASSEMBLY. |  |  | 1500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | ENTRY PEELER TABLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | SCRAP TROLLEY |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | SCRAP DOWN TABLE |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | PASSING TABLE ASSEMBLY.#1 |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | PASSING TABLE ASSEMBLY.#2 |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | LOOPER TABLE #1 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | LOOPER TABLE #2 |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING |  | OM DEV | EXIT THREADING TABLE ASSEMBLY. |  |  | 300000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING | BOI | OM DEV | FOUNDATION BOLTS |  |  | 1000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING | BOI | OM DEV | TAPER (LEVELLING) PLATE |  |  | 1000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING | BOI | OM DEV | INTERCONNECTING PIPING |  |  | 2000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | SLITTING | May 2026
2602-BMWIL-SLITTING | ELECTRICAL | OM DEV | ELECTRICAL |  |  | 7000000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | SLITTING | May 2026
2534-BMWIL-TRIMMING | BOI | KUNAL | UNCOILER-COIL CAR ASSEMBLY. |  |  | 750000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2026
2534-BMWIL-TRIMMING |  | KUNAL | UNCOILER-DRAG CHAIN ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | May 2026
2534-BMWIL-TRIMMING |  | KUNAL | UNCOILER-COIL SADDLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2026
2534-BMWIL-TRIMMING |  | KUNAL | UNCOILER-PIT COVER |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | May 2026
2534-BMWIL-TRIMMING | BOI | KUNAL | RECOILER-COIL CAR ASSEMBLY. |  |  | 750000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2026
2534-BMWIL-TRIMMING |  | KUNAL | RECOILER-DRAG CHAIN ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | May 2026
2534-BMWIL-TRIMMING |  | KUNAL | RECOILER-COIL SADDLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | May 2026
2534-BMWIL-TRIMMING |  | KUNAL | RECOILER-PIT COVER |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | May 2026
2534-BMWIL-TRIMMING | BOI | KUNAL | FOUNDATION BOLTS |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2026
2534-BMWIL-TRIMMING | BOI | KUNAL | TAPER (LEVELLING) PLATE |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | May 2026
2534-BMWIL-TRIMMING | BOI | KUNAL | INTERCONNECTING PIPING |  |  | 1000000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | TRIMMING | May 2026
2540-AS PRECISION-ELECTRICAL | ELECTRICAL |  | ELECTRICAL-Lot 1 |  |  | 125100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | ELECTRICAL | May 2026
2529-KHUSHBOO-CCL | BOI | TRIPURARI | UNCOILER COIL CAR ASSY. |  |  | 500000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | UNCOILER DRAG CHAIN ASSY. |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CCL | May 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | UNCOILER COIL SADDLE ASSY. |  |  | 200000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2026
2529-KHUSHBOO-CCL | BOI | TRIPURARI | RECOILER COIL CAR ASSY. |  |  | 500000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CCL | May 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | RECOILER DRAG CHAIN ASSY. |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CCL | May 2026
2529-KHUSHBOO-CCL |  | TRIPURARI | RECOILER COIL SADDLE ASSY. |  |  | 200000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | CCL | May 2026
2544-APL-REWINDING | BOI | KUNAL | UNCOILER-COIL CAR ASSEMBLY. |  |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2544-APL-REWINDING |  | KUNAL | UNCOILER-DRAG CHAIN ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2544-APL-REWINDING |  | KUNAL | UNCOILER-COIL SADDLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2544-APL-REWINDING | BOI | KUNAL | RECOILER-COIL CAR ASSEMBLY. |  |  | 400000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2544-APL-REWINDING |  | KUNAL | RECOILER-DRAG CHAIN ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-05-28 |  | TRUE | FALSE | [5 empty] | APL | May 2026
2544-APL-REWINDING |  | KUNAL | RECOILER-COIL SADDLE ASSEMBLY. |  |  | 100000 | Not Disp. | 2026-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | RECOILER OBBS ASSY. |  | 2000 | 180000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | PEELER TABLE ASSY #1 |  | 2000 | 180000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | PEELER TABLE ASSY #2 |  | 2000 | 180000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | ENTRY SCRAP TROLLEY |  | 2000 | 180000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | ENTRY SCRAP DOWN TABLE |  | 2000 | 180000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | EXIT SCRAP TROLLEY |  | 2000 | 180000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | EXIT SCRAP DOWN TABLE |  | 2000 | 180000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | EXIT THREADING TABLE ASSY. |  | 2000 | 180000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | PASSING TABLES |  | 2000 | 180000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | PINCH CUM LEVELLER ROLL ASSY. |  | 10000 | 900000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | ENTRY SIDE GUIDE ASSY. |  | 5000 | 450000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | EXIT SIDE GUIDE ASSY. |  | 5000 | 450000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#1 |  | 5000 | 450000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#2 |  | 5000 | 450000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | ENTRY PINCH ROLL ASSY.#3 |  | 5000 | 450000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | AIR WIPER ASSY |  | 10000 | 900000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | ELECTRICAL | ADITYA SAINI | ELECTRICAL PACKAGE |  | 50000 | 4500000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | TENSIONER ROLL ASSY |  | 10000 | 900000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | BURR MASHER |  | 4000 | 360000 | Not Disp. | 2026-05-20 |  | FALSE | FALSE | [5 empty] | PICKLING | May 2026
2522-APL-SPM |  | ADITYA SAINI | TOP PLATEFORM |  |  | 500000 | Not Disp. | 2026-04-30 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | HOOD ASSY |  |  | 500000 | Not Disp. | 2026-04-30 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | BOI | ADITYA SAINI | MILL DRIVE |  |  | 2000000 | Not Disp. | 2026-04-30 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2425-MMI-6HI CRM | UNIT-2 | MAYANK | Mill hood assembly |  | 4000 | 344000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2404-GOPANI-4HI SPM | UNIT-2 | ADITYA SHARMA | TOP PLATEFORM |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2404-GOPANI-4HI SPM | UNIT-2 | ADITYA SHARMA | HOOD ASSY |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2414-UTTAM-6HI CRM | UNIT-2 | ADITYA SHARMA | HOOD ASSY |  |  | 1000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2414-UTTAM-6HI CRM | BOI | ADITYA SHARMA | FUME EXHAUST DUCT. |  |  | 2500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2414-UTTAM-6HI CRM | BOI | ADITYA SHARMA | CELLER VENTILATION DUCT |  |  | 600000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2421-APL-CGL | BOI-LL | SAURABH | MIG WELDER ASSY. |  |  | 1500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2518-APL-SPM | BOI | MAYANK | UNCOILER & RECOILER AC MOTORS |  |  | 22000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2518-APL-SPM | BOI-LL | MAYANK | BACKUP CHOCK BEARINGS (CRB + THRUST) |  |  | 8500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2518-APL-SPM | BOI-LL | MAYANK | WORK ROLL CHOCK BEARINGS |  |  | 1000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2518-APL-SPM | UNIT-1 | MAYANK | BACKUP PULLING TROLLEY | FB |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2518-APL-SPM | UNIT-1 | MAYANK | BACKUP STOOL | FB |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2518-APL-SPM | UNIT-3 | MAYANK | DRAG CHAIN @ RECOILER | FB |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2518-APL-SPM | UNIT-3 | MAYANK | COIL SADDLE @ RECOILER | FB |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2518-APL-SPM | BOI-LL | MAYANK | HYDRAULIC POWER PACK & VALVE STANDS |  |  | 17500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE |  |  |  | LC | 12150000 | SPM | Apr 2026
2518-APL-SPM | BOI | MAYANK | SHEARING MACHINE |  |  | 1200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE |  |  |  | PAYMENT | 1058400 | SPM | Apr 2026
2518-APL-SPM | ELECTRICAL | MAYANK | ELECTRICAL |  |  | 1000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2428-BMWIL-CGL |  | TRIPURARI | DRAG CHAIN ASSY. @ UNCOILER |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | COIL SADDLE ASSY. @ UNCOILER |  |  | 400000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL |  | TRIPURARI | DRAG CHAIN ASSY. @ RECOILER |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | COIL SADDLE ASSY. @ RECOILER |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | UNCOILER MANDREL ASSY.#1 |  |  | 3000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | UNCOILER GEAR BOX ASSY.#1 |  |  | 5000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | UNCOILER SNUBBER ROLL ASSY.#1 |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | UNCOILER OBBS ASSY.#1 |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | UNCOILER MANDREL ASSY.#2 |  |  | 3000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | UNCOILER GEAR BOX ASSY.#2 |  |  | 5000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | UNCOILER SNUBBER ROLL ASSY. #2 |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | UNCOILER OBBS ASSY.#2 |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | RECOILER MANDREL ASSY. |  |  | 4000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | RECOILER GEAR BOX ASSY. |  |  | 6000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | RECOILER PUSHER PLATE ASSY. |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY& EXIT SCRAP CAR ASSY. |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | EXIT THREADING TABLE ASSY. |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | BRIDLE ROLL ASSY.#6 |  |  | 3100000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | BRIDLE ROLL ASSY.#7 |  |  | 3100000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | BRIDLE ROLL ASSY.#8 |  |  | 3100000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | BRIDLE ROLL ASSY.#9 |  |  | 3100000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY ACCUMULATOR TOP FRAME |  |  | 5000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY ACCUMULATOR COUNTER WEIGHT ASSEMBLY | FB |  | 1000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | BOI | TRIPURARI | ENTRY ACCUMULATOR CHAIN |  |  | 2000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | EXIT ACCUMULATOR STRUCTURE |  |  | 2000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | EXIT ACCUMULATOR TOP FRAME |  |  | 5000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | EXIT ACCUMULATOR COUNTER WEIGHT ASSEMBLY | FB |  | 1000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | BOI | TRIPURARI | EXIT ACCUMULATOR CHAIN |  |  | 2000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY PINCH ROLL ASSY.#1 |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY PINCH ROLL ASSY.#2 |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY PINCH ROLL ASSY.#3 |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY PINCH ROLL ASSY.#4 |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY PINCH ROLL ASSY.#5 |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | EXIT PINCH ROLL ASSY. #1 |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | EXIT PINCH ROLL ASSY. #2 |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | DEFLECTOR ROLL ASSY.#1 (AFTER BRIDLE ROLL ASSY.#1) |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | DEFLECTOR ROLL ASSY.#2&3 (BEFORE & AFTER ENTRY ACC ASSY.) |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | DEFLECTOR ROLL ASSY.#4 (BEFORE COATING THICKNESS GAUGE) |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | DEFLECTOR ROLL ASSY.#5 (AFTER BRIDLE ROLL ASY.#07) |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | DEFLECTOR ROLL ASSY.#6&7 (BEFORE CHEMICAL COATER) |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | DEFLECTOR ROLL ASSY.#8 (BEFORE BRIDLE ROLL ASY.#08) |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | DEFLECTOR ROLL ASSY.#9 (BEFORE LOGO MARKER) |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | STRIP CLAMP ASSY.3 NOS |  |  | 1500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | BOI | TRIPURARI | FOUNDATION BOLT |  |  | 1000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | ELECTRICAL | TRIPURARI | ELECTRICAL-lot 2 |  |  | 23500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2428-BMWIL-CGL | STRUCTURE | TRIPURARI | Furnace Structure - Columns |  |  | 10000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2427-PROMPT-6HI CRM | ELECTRICAL | MAYANK | ELECTRICAL-Balance |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2427-PROMPT-6HI CRM | BOI | MAYANK | SPARE-All Cables from YD Panel to YD Supplied equipment |  |  | 3000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2427-PROMPT-6HI CRM | BOI | MAYANK | SPARE-Air Receiver tank in YD Scope |  |  | 300000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2427-PROMPT-6HI CRM | UNIT-1 | MAYANK | SPARE - IMR CHOCKS (4 NOS.) |  |  | 1000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2427-PROMPT-6HI CRM | UNIT-1 | MAYANK | SPARE - WORK ROLL CHOCKS (4 NOS.) |  |  | 800000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2427-PROMPT-6HI CRM | BOI-LL | MAYANK | SPARE - BACKUP ROLLS (2 NOS.) |  |  | 9000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE |  |  | 10488000 |  |  | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | RAIL LINE, CLAMP PLATE & BOLT FOR COIL CAR |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | ETR SAFETY CAGE | FB |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | ETR-SNUBBER ROLL ASSY. |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | ETR-OBBS ASSY | FB |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | DTR SAFETY CAGE | FB |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | DTR-OBBS ASSY | FB |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | SCRAP TROLLEY | FB |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | QWRC TROLLEY ASSY | FB |  | 4000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | BACKUP PULLING TROLLEY | FB |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | PEELER TABLE |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | ENTRY TILTING TABLE |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | EXIT TILTING TABLE |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | SCRAP DOWN TABLE | FB |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | IMR CHOCKS (4 NOS.) |  |  | 2992000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | WORK ROLL CHOCKS (4 NOS.) |  |  | 2925000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | TAPER WEDGE POSITION TRANSDUCER ASSY. |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | ROLL FORCE CLY ASSY |  |  | 5000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | BACKUP OUTSIDE TRACK |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | SIDE GUIDE ASSEMBLY |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | DISTRIBUTION HEADERS |  |  | 445000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2511-GAURANG-6HI |  | MAYANK | COOLANT TRAY | FB |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2511-GAURANG-6HI | BOI | MAYANK | TAPER PLATES SET |  |  | 740000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2511-GAURANG-6HI | ELECTRICAL | MAYANK | Electricals-BALANCE |  |  | 1500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2511-GAURANG-6HI |  | MAYANK | POR-MANDREL ASSY,GEARBOX,SNUBBER | FB |  | 7500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2511-GAURANG-6HI |  | MAYANK | ETR-MANDREL ASSY,GEARBOX,PUSHER PLATE |  |  | 9000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | UNCOILER-MANDREL ASSY |  |  | 3000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE |  |  | 1440000 |  |  | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | UNCOILER-GEARBOX ASSY |  |  | 0 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | UNCOILER-SNUBBER ROLL ASSY |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | UNCOILER-O.B.B.S ASSY |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | RECOILER-MANDREL ASSY |  |  | 3000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | RECOILER-GEARBOX ASSY |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | RECOILER-PUSHER PLATE ASSY |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | UNIT-3 | ADITYA SAINI | RECOILER-O.B.B.S ASSY |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | RECOILER-HOLD DOWN ROLL |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | UNIT-3 | ADITYA SAINI | BRIDLE ROLL ASSY.#1 |  |  | 1500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | UNIT-3 | ADITYA SAINI | BRIDLE ROLL ASSY.#2 |  |  | 1500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | BUP CHOCKS-4 NOS |  |  | 1500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | BOI-LL | ADITYA SAINI | BUP BEARINGS |  |  | 3010000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | BACKUP STOOL ASSY |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | WR CHOCKS-4 NOS |  |  | 1000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | BOI-LL | ADITYA SAINI | WR BEARINGS |  |  | 710000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | BACKUP ROLL CLAMP ASSY |  |  | 0 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | BUP HANGING CLAMP |  |  | 0 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | SPINDLE SUPPORT ARM ASSY |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | BACKUP OUTSIDE TRACK |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | ROLL COOLING HEADER |  |  | 100000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | EXIT AIR KNIFE ASSY. |  |  | 100000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | PEELER TABLE ASSY. |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | EXIT THREADING TABLE ASSY. |  |  | 250000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | PASSING TABLE |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | BOI-LL | ADITYA SAINI | HYDRAULIC POWER PACK lOT -2 |  |  | 4000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM | BOI | ADITYA SAINI | FOUNDATION BOLTS |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2522-APL-SPM |  | ADITYA SAINI | BACKUP ROLL CHANGE TROLLY |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | SPM | Apr 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | COIL CAR ASSY. @ UNCOILER |  |  | 2000000 | Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PIT COVER-1A @ RECOILER |  |  | 450000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PIT COVER-1B @ RECOILER |  |  | 450000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | UNCOILER #1 OBBS ASSY. |  |  | 150000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | UNCOILER #2 OBBS ASSY. |  |  | 150000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | RECOILER EXIT OBBS ASSY. |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | RECOILER BELT WRAPPPER ASSY. |  |  | 1290000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PEELER TABLE ASSY.#1 |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PEELER TABLE ASSY.#2 |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#1 (PINCH ROLL#1 & PINCH ROLL#2) |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#2 (D.D. SHEAR & PINCH ROLL#2) |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#3 (D.D. SHEAR & PINCH ROLL#3) |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ENTRY SCRAP DOWN TABLE ASSY#1 |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ENTRY SCRAP DOWN TABLE ASSY#2 |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ENTRY SCRAP TRAY ASSY. |  |  | 150000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ENTRY SCRAP TROLLEY ASSY. |  |  | 150000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PASSING TABLE ASSY#4 (BEFORE PINCH ROLL#4) |  |  | 200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | STRUCTURE | SAURABH | Entry Accumulator Top frame extension & steering Structure |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Entry Accumulator Dead weight guard |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | STRUCTURE | SAURABH | Exit Accumulator Top frame extension Structure |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Exit Accumulator Dead weight guard |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #5 |  |  | 300000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | PORTER BAR @ CLANING SECTION SQZ ROLL REMOVAL |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRUSHING ROLL ASSY.#01-4 ASSY. |  |  | 1200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRUSHING ROLL ASSY.#02-4 ASSY. |  |  | 1200000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | ALKALI CLANING TANK ASSY.#01 |  |  | 1500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | QUENCHING TANK ASSY. |  |  | 1500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | WATER SPRAY UNIT |  |  | 1500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | DIP TYPE CHROMATIC TANK ASSY. |  |  | 1500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | EDGE WIPER Assy with pot |  |  | 500000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | STRUCTURE | SAURABH | FURNACE STRUCTURE |  |  | 20394150 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | FUME EXHAUST SYSTEM FOR CLANING SECTION |  |  | 1000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | STRUCTURE | SAURABH | CAG & COATER STRUCTURE |  |  | 19000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | MOVING TROLLEY |  |  | 3000000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | BACKUP OUTSIDE TRACK |  | 2000 | 179000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | POR-OBBS ASSY | FB | 2000 | 179000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | ETR-OBBS ASSY | FB | 2000 | 179000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | DTR-OBBS ASSY | FB | 3352.5102 | 300049.6653 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | BACKUP STOOL |  | 1532.7256 | 137178.9384 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | BACKUP ROLL PULLING TROLLY | FB | 2000 | 179000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | PEELER TABLE ASSY |  | 2000 | 179000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | CARRY OVER TABLE |  | 2000 | 179000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | TILTING TABLE ASSY. AT ETR |  | 2000 | 179000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | TILTINGTABLE ASSY. AT DTR |  | 2000 | 179000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | BOI-LL | MAYANK | ENTRY SHEAR ASSY |  | 11875 | 1062812.5 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | MAE WEST BLOCK PISTONS (1 SET) |  | 2000 | 179000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | DEFLECTOR ROLL WITH BEARING BLOCKS (1 SET) |  | 2000 | 179000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | ROTARY UNION FOR POR (1 NOS.) |  | 1000 | 89500 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | ROTARY UNION FOR ETR (1 NOS.) - MACO CORPORATION |  | 2000 | 179000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | ROTARY UNION FOR DTR (1 NOS.) - HYDMARK |  | 1000 | 89500 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | HYDRAULIC MOTOR OMT 315 |  | 500 | 44750 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | HYDRAULIC MOTOR OMT 500 |  | 500 | 44000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL SADDLE |  | 4000 | 360000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL SADDLE ASSY. |  | 2000 | 180000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | SINGLE SQUEEZE ROLL ASSY. |  | 43000 | 3870000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | DOUBLE SQUEEZE ROLL ASSY. |  | 19000 | 1710000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | ENTRY SHEAR |  | 17000 | 1530000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | FOUNDATION BOLTS |  | 10000 | 900000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | BOI-LL | ADITYA SAINI | EXIT SHEAR |  | 19000 | 1710000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | BOI-LL | ADITYA SAINI | EPC SYSTEM |  | 10000 | 900000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | BOI-LL | ADITYA SAINI | ACID RECIRCULATION SYSTEM, FUME EXHAUST & SCRUBBER SYSTEM -Lot 3 |  | 10000 | 900000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | BOI-LL | ADITYA SAINI | HOT AIR DRYER |  | 22000 | 1980000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | TEMP. CONTROL VALVES |  | 10000 | 900000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | HEAT EXCHANGERS |  | 19000 | 1710000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE |  |  |  | 80% BALACE AGAINST PI | 1568000 | PICKLING | Apr 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | PNEUMATIC PIPE ,VALVES & FITTINGS |  | 4949 | 445410 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | CCS DUCT |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | EXHAUST DUCT |  |  | 905000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Exit Seal With Vestibule Assembly |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Furnace Gas and Combustion Air Piping |  |  | 2715000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | STRUCTURE | ADITYA SHARMA | Furnace Structure - APR LOT |  |  | 3620000 | Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Handling Rig |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Quench Tank Assembly |  |  | 905000 | Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Threading Needle Assembly |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Pneumatic Shut-Off Valve, FLOW CONTROL VALVE |  |  | 905000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Ball Valve |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Butterfly Damper |  |  | 905000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Gate, Butterfly, Globe Valve |  |  | 905000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Temprature control valve and Steam trap |  |  | 2715000 | Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ENTRY PIT COVER ASSY.#2A |  |  | 905000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ENTRY PIT COVER ASSY.#2B |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | LOCKING ASSEMBLY 2 |  |  | 905000 | Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ENTRY WHEEL GUIDE ASSEMBLY ( BALL SCREW ) |  |  | 905000 | Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE BEFORE ENTRY PINCH ROLL ASSY.#4 |  |  | 181000 | Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE AFTER ENTRY PINCH ROLL ASSY.#4 |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE AFTER SIDE GUIDE ASSY.#3 |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE AFTER STITCHER |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE AFTER SIDE GUIDE ASSY.#4 |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE AFTER BURR MASHER |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE AFTER HOLE DETECTOR#1 |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE BEFORE BRIDLE ROLL ASSY.#1 (BEFORE ENTRY ACC.) |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | HOT AIR DRYER ASSY. (AFTER WATER QUENCH) |  |  | 905000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE #01 AFTER QUECH SQZ ROLL ASSY. |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE #02 AFTER QUECH SQZ ROLL ASSY. |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE AFTER QUENCH |  |  |  | Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE#01 BEFORE DOUBLE STEERING ROLL ASSY.#05 |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE#02 BEFORE DOUBLE STEERING ROLL ASSY.#05 |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE#03 BEFORE DOUBLE STEERING ROLL ASSY.#05 |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE AFTER BRIDLE ROLL ASSY.#6 |  |  |  | Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE#01 BEFORE PICKLING TANK |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE#02 BEFORE PICKLING TANK |  |  |  | Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | HOT AIR DRYER AFTER RINSING TANK |  |  | 905000 | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE AFTER EXIT PINCH ROLL ASSY.#1 |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXIT PIT COVER ASSY.#1A |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXIT PIT COVER ASSY.#1B |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | FRVE PIPES(FRSVE)& FFUME EXHAUST SCRUBBING SYSTEM |  |  | 905000 | Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | BOI | ADITYA SHARMA | MECHANICAL SPARES |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2506-JSW-APL | ELECTRICAL | ADITYA SHARMA | ELECTRICAL SPARES |  |  |  | Not Disp. | 2026-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2026
2404-GOPANI-4HI SPM | BOI | ADITYA SHARMA | SPARE-SPINDLE COUPLING |  |  | 700000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2421-APL-CGL | UNIT-2 | SAURABH | HORIZONTAL ACCUMULATOR ASSY. |  |  | 1000000 | Not Disp. | 2026-03-28 |  | FALSE | FALSE |  | WINCH DRUM READY BY 15-DEC & ALL FABRICATION PENDING |  |  |  | CGL | Mar 2026
2518-APL-SPM | BOI | MAYANK | MILL MOTOR |  |  | 8000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2518-APL-SPM | BOI | MAYANK | COIL CAR @ UNCOILER |  |  | 5000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2518-APL-SPM | BOI | MAYANK | COIL CAR @ RECOILER |  |  | 5000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2518-APL-SPM | BOI | MAYANK | PIPES & FITTINGS |  |  | 7500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2535-JSW-JFE-POR SPARE | UNIT-3 | MAYANK | POR |  |  | 12200000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPARE | Mar 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | BRIDLE ROLL ASSY.#1 |  |  | 4500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | BRIDLE ROLL ASSY.#3 |  |  | 4500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | BRIDLE ROLL ASSY.#4 |  |  | 4500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | BOI | TRIPURARI | ENTRY ACCUMULATOR STRUCTURE |  |  | 2500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ENTRY ACCUMULATOR MOVING FRAME |  |  | 7500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | EXIT ACCUMULATOR FIXED FRAME |  |  | 9500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | EXIT ACCUMULATOR MOVING FRAME |  |  | 7500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | SINGLE STEERING ROLL ASSY. |  |  | 1000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | BOI | TRIPURARI | COATING THK GAUGE WITH SUPPORT ROLLS ASSY. |  |  | 6750000 | Disp. | 2026-03-28 |  | TRUE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | BOI | TRIPURARI | DOUBLE DECKER ENTRY SHEAR ASSY. |  |  | 1000000 | Disp. | 2026-03-28 |  | TRUE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | BOI | TRIPURARI | DELIVERY SHEAR ASSY. |  |  | 1000000 | Disp. | 2026-03-28 |  | TRUE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | BOI | TRIPURARI | TAPER PLATE |  |  | 500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | ELECTRICAL-lot 1 |  |  | 21550000 | Disp. | 2026-03-28 |  | TRUE | FALSE | [5 empty] | CGL | Mar 2026
2420-INDIA STEEL-CCL | UNIT-2 | SAURABH | ELECTRICAL Loose items |  |  | 440000 | Not Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CCL | Mar 2026
2420-INDIA STEEL-CCL | BOI | SAURABH | Orifice Plate AND PITOT TUBE |  |  | 100000 | Not Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CCL | Mar 2026
2420-INDIA STEEL-CCL | BOI | SAURABH | FITTINGS |  |  | 2729800 | Not Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CCL | Mar 2026
2427-PROMPT-6HI CRM | UNIT-1 | MAYANK | ETR-OBBS ASSY |  |  | 100000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CRM | Mar 2026
2427-PROMPT-6HI CRM | UNIT-1 | MAYANK | DTR-OBBS ASSY |  |  | 100000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CRM | Mar 2026
2427-PROMPT-6HI CRM | UNIT-1 | MAYANK | IMR CHOCKS (4 NOS.) |  |  | 1000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2427-PROMPT-6HI CRM | UNIT-1 | MAYANK | SPARE - BACKUP ROLL CHOCKS (4 NOS.) |  |  | 2800000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | CASTING UNDER M/C IN UNIT #3 |  |  |  | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | POR,ETR,DTR-DRAG CHAIN |  |  | 0 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | DRAG CHAIN RECEIVED |  |  |  | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | ELECTRICAL |  |  | 4000000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | DRAG CHAIN RECEIVED |  |  |  | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | MOTOR BASE FRAME FOR DTR |  |  | 3000000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | UNDER M/C IN HOUSE |  |  |  | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | BACKUP STOOL | FB |  | 550000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | AIR OIL LUBRICATION SYSTEM ASSY |  |  | 4970000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  |  | PAYMENT | 3124000 | CRM | Mar 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | DELIVERY SHEAR ASSY |  |  | 742000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | BACKUP ROLL CHOCKS (4 NOS.) |  |  | 8670000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | WORK ROLLS (2 NOS.) |  |  | 1224000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  | 1053400 |  |  | CRM | Mar 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | IMR ROLLS (2 NOS.) |  |  | 1738000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  | 1495920 |  |  | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | BACK UP CLAMP ASSY. |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | IMR SHIFTING ASSY. |  |  | 3000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | WORK ROLL CLAMP ASSY. |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | MILL HOUSING WITH LINER |  |  | 26000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | BED PLATE ASSY. |  |  | 4500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | SHUTTER ASSY |  |  | 500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | TOP SEPARATOR ASSY. |  |  | 500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | TAPER WEDGE ASSY. |  |  | 2000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | MAEWEST BLOCK ASSY. |  |  | 9000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | WORK ROLL & IMR INSIDE TRACK |  |  | 100000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | BACKUP INSIDE TRACK |  |  | 500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | SPINDLE SUPPORT ASSY |  |  | 314000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | ROLL COOLANT HEADER ASSY |  |  | 2100000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | ENTRY AIR WIPER ASSY |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | BACKUP WIPER ASSY |  |  | 537000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | EXIT AIR WIPER ASSY |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | COBBLE GUARD ASSY |  |  | 2825000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | PRESSURE PAD ASSEMBLY |  |  | 1700000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | ENTRY AIR KNIFE ASSY |  |  | 250000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | EXIT AIR KNIFE ASSY |  |  | 250000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | ENTRY PASSING TABLE @ MILL STAND |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | EXIT PASSING TABLE @ MILL STAND |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | ENTRY DEFLECTOR CUM TURN DOWN |  |  | 3500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | ENTRY C FRAME |  |  | 1000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | DELIVERY DEFLECTOR CUM TURN DOWN |  |  | 3500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | EXIT C FRAME |  |  | 1000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | PASSING TABLE #2 (BET. ENTRY DEF. ROLL & ENTRY THK. GAUGE) |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | PASSING TABLE #3 (BET. EXIT THK. GAUGE & EXIT DEF. ROLL ) |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | PASSING TABLE #4 (BET. ENTRY THK. GAUGE & PRESS. BOARD) |  |  | 100000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | PASSING TABLE #5 (BET. EXIT SHEAR & EXIT THK. GAUGE) |  |  | 100000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | PASSING TABLE #6 (BET. EXIT PASSING TABLE & EXIT SHEAR) |  |  | 100000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | PASSING TABLE #7 (BET. EXIT SHEAR & PASSING TABLE#5) |  |  | 100000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | HYDRAULIC & PNEUMATIC PIPES & FITTINGS |  |  | 5000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | HT MOTORS |  |  | 36000000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  |  | LC | 35326800 | CRM | Mar 2026
2511-GAURANG-6HI |  | MAYANK | POR-DRAG CHAIN | FB |  | 100000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2511-GAURANG-6HI |  | MAYANK | ETR-DRAG CHAIN | FB |  | 100000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2511-GAURANG-6HI |  | MAYANK | DTR-DRAG CHAIN | FB |  | 110000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2511-GAURANG-6HI | BOI | MAYANK | HYDRAULIC PIPES,FITTINGS. |  |  | 4000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2511-GAURANG-6HI | BOI | MAYANK | GEAR LUBRICATION SYSTEM ASSY |  |  | 1200000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2511-GAURANG-6HI | UNIT-2 | MAYANK | Electricals |  |  | 58700000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2511-GAURANG-6HI | BOI | MAYANK | WORK ROLL bearing |  |  | 800000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2511-GAURANG-6HI | BOI | MAYANK | IMR ROLL bearing |  |  | 1000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2511-GAURANG-6HI | BOI | MAYANK | BACK UP ROLL bearing |  |  | 6000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2511-GAURANG-6HI | BOI | MAYANK | FUME EXHAUST SYSTEM WITH BLOWER ASSY |  |  | 6150534 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2511-GAURANG-6HI | BOI | MAYANK | COOLANT FILTERATION SYSTEM |  |  | 11500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2511-GAURANG-6HI | BOI | MAYANK | HYDRAULIC POWER PACK & VALVE TABLE ASSY |  |  | 17000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2522-APL-SPM | UNIT-3 | ADITYA SAINI | UNCOILER-DRAG CHAIN ASSY. |  |  | 160000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-3 | ADITYA SAINI | UNCOILER-COIL SADDLE ASSY. |  |  | 320000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-3 | ADITYA SAINI | UNCOILER-COIL CAR PIT COVER |  |  | 160000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-3 | ADITYA SAINI | RECOILER-DRAG CHAINASSY. |  |  | 160000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-3 | ADITYA SAINI | RECOILER-COIL SADDLE ASSY. |  |  | 320000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-3 | ADITYA SAINI | RECOILER-COIL CAR PIT COVER |  |  | 160000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | TOP BACKUP ROLL ASSY. |  |  | 1100000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  | 4144160 |  |  | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | BOTTOM BACKUP ROLL ASSY. |  |  | 1100000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  | 184788 |  |  | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | TOP WORK ROLL ASSY. |  |  | 300000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | BOTTOM WORK ROLL ASSY. |  |  | 300000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | MILL HOUSING WITH LINER |  |  | 3500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | BED PLATE |  |  | 500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | ANTI CRIMP ROLL ASSY |  |  | 500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | ANTI CROSS ROLL ASSY |  |  | 500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | TOP SEPARATOR ASSY. |  |  | 200000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | ENTRY DEFLECTOR ROLL ASSY. |  |  | 1400000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | DELIVERY DEFLECTOR ROLL ASSY. |  |  | 1400000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | BACKUP WIPER |  |  | 300000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | MILL TABLE FOR DEFLECTORL ROLL |  |  | 200000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | ENTRY & EXIT SHEAR MACHINE ASSY. |  |  | 700000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | BACKUP INSIDE TRACK |  |  | 200000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | BOI | ADITYA SAINI | PIPES & FITTINGS |  |  | 1100000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | UNIT-1 | ADITYA SAINI | ROLL FORCE CYLINDER ASSY. |  |  | 1500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2522-APL-SPM | BOI | ADITYA SAINI | HYDRAULIC POWER PACK lOT -1 |  |  | 5000000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | AULOS | 8260000 |  |  | SPM | Mar 2026
2522-APL-SPM | BOI | ADITYA SAINI | TAPER PLATES SET |  |  | 800000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | SPM | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | COIL CAR ASSY. @ RECOILER |  |  | 1000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-3 | SAURABH | UNCOILER #2 WITH SNUBBER ROLL |  |  | 6500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DOUBLE STEERING ROLL ASSY. BEFORE ENTRY ACC ASSY. |  |  | 1600000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ENTRY PINCH ROLL ASSY.#1 |  |  | 250000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ENTRY PINCH ROLL ASSY.#2 |  |  | 250000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ENTRY PINCH ROLL ASSY.#3 |  |  | 250000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ENTRY PINCH ROLL ASSY.#4 |  |  | 250000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | EXIT PINCH ROLL ASSY. #2 |  |  | 300000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #1 |  |  | 300000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | SINGLE SQUEEZE ROLL ASSY.-8 ASSY. |  |  | 1600000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | ECL TANK LOT 1 |  |  | 7500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRUSHING TANK ASSY.#01 |  |  | 2000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRUSHING TANK ASSY.#02 |  |  | 2000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | HOT WATER RINSING TANK ASSY. |  |  | 2300000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | HOLDING TANK ASSY.#1 (COMMON FOR ALKALI TANK #1 & BRUSH TANK#1) |  |  | 2500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | HOLDING TANK ASSY.#2 (COMMON FOR ALKALI TANK #2 & BRUSH TANK#2) |  |  | 2500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | DEGREASING TANK ASSEMBLY |  |  | 1700000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | TENSIOMETER ASSY.#1 BEFORE FURNACE ENTRY |  |  | 1500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | CHEMICAL HANDLING SYSTEM |  |  | 300000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | CPC |  |  | 4400000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  |  | LC | 5111939 | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | EPC |  |  | 900000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | STRUCTURE | SAURABH | FURNACE STRUCTURE-MARCH |  |  | 7545850 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | SEAM WELDER ASSY. |  |  | 11000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | HYDRAULIC VALVE STAND |  |  | 4000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | HYDRAULIC POWERPACK |  |  | 5010000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | HYDRAULIC PIPES & FITTINGS |  |  | 3500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | GRANITE TILES |  |  | 2500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | ACID FLOOR TILES |  |  | 2700000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | GRANITE TILES, SLICATE POWER, SILICATE RESIN FUROCEM POWER, FUROCEM SYRUP |  |  | 2500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | STRUCTURE | SAURABH | CAG & COATER STRUCTURE-MAR |  |  | 5968800 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | SNOUT |  |  | 2500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | HBR WITH ROLL & REF ASSEMBLY |  |  | 9920000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | HBR DRIVE ASSEMBLY |  |  | 4940000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | MOVING PENDANT ASSEMBLY |  |  | 230000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | COOLING UP PASS PENDANT ASSEMBLY-SLOT |  |  | 1820000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | COOLING PENDANT DOWN PASS ASSEMBLY-HOLE |  |  | 650000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Non-Ox Burners |  |  | 2000000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  |  | LC | 1486219 | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Thermocouple & Compensating cable |  |  | 400000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  |  | PI | 321579 | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Pressure & Temperature Transmitters |  |  | 2000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | IR Pyrometers |  |  | 400000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Solenoid Shut-Off Valves |  |  | 400000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | H2 analyzer O2 & Dew Point Analyzer |  |  | 2000000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  |  | LC | 1652000 | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Recuperator For Non-OX Furnace |  |  | 2500000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | HNX Gas Station & Furnace Gas Station |  |  | 4000000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  | 2959086 |  |  | CGL | Mar 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Pot |  |  | 80495000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2514-GAURANG-CGL |  | SAURABH | COIL CAR ASSY. @ UNCOILER |  |  | 4000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2514-GAURANG-CGL |  | SAURABH | AIRKNIFE MOTOR |  |  | 788000 | Disp. | 2026-03-28 |  | TRUE | FALSE | [5 empty] | CGL | Mar 2026
2514-GAURANG-CGL |  | SAURABH | COIL CAR ASSY. @ RECOILER |  |  | 2000000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2514-GAURANG-CGL |  | SAURABH | COATING THK GAUGE WITH SUPPORT ROLLS ASSY. |  |  | 6750000 | Disp. | 2026-03-28 |  | TRUE | FALSE | [5 empty] | CGL | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-2 | MAYANK | COOLANT TRAY |  | 10000 | 895000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | COIL SADDLE @ POR, ETR & DTR |  | 5578.783 | 499301.0744 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | PIT COVER @ POR, ETR & DTR |  | 7075.8563 | 633289.1344 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | UNDER FABRICATION |  |  |  | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | MOTOR BASE FRAME (PINION, ETR & DTR) |  | 30000 | 2685000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | BACKUP CHOCKS - 4 NOS |  | 57940 | 5185630 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | IMR CHOCKS - 4 NOS |  | 16514.6114 | 1478057.717 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | WORK ROLL CHOCKS - 4 NOS |  | 15594.6477 | 1395720.9716 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | ROLL FORCE CLY ASSY |  | 40000 | 3580000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-2 | MAYANK | ELECTRICAL PACKAGE |  | 150000 | 13425000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | SPARE-IMR CHOCKS - 4 NOS |  | 12000 | 1074000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | SPARE-WORK ROLL CHOCKS -4 NOS |  | 8000 | 716000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | INTERCONNECTING PIPING |  | 8000 | 716000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | UNIT-3 | MAYANK | ELECTROMAGNETIC BRAKE FOR ETR & DTR WITH BASE FRAME |  | 20000 | 1790000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  | 1400626 |  |  | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | FUME EXHAUST SYSTEM |  | 56386.25 | 5046569.375 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | AIR OIL LUBRICATION SYSTEM ASSY |  | 44375 | 3971562.5 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  |  | PAYMENT | 3124000 | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | HYDRAULIC PIPES |  | 35000 | 3132500 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | HT MOTORS (PINION, POR, ETR & DTR) |  | 280006 | 25060537 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | CRM | Mar 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | ENTRY DRAG CHAIN ASSY. |  | 9000 | 810000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Mar 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | EXIT DRAG CHAIN ASSY |  | 5000 | 450000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Mar 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | TAPER (LEVELLING) PLATE |  | 10000 | 900000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | READY TO DISPATCH |  |  |  | PICKLING | Mar 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | PICKLING TANK -1,2,3,4& PRE-WASH TANK,5-STAGE RINSING TANK |  | 161209 | 14508810 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | REKHA INDUSTRIES |  |  |  | PICKLING | Mar 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | GRANITE BLOCKS & RUBBER LINING & ACID PROOF TILING |  | 83612 | 7525080 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | REKHA INDUSTRIES |  |  |  | PICKLING | Mar 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | ACID RECIRCULATION SYSTEM, FUME EXHAUST & SCRUBBER SYSTEM -Lot 2 |  | 78430 | 7058700 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Mar 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | OIL SPRAYING SYSTEM |  | 10000 | 900000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | AVCO TECH - (23-02-2026) | 129800 |  |  | PICKLING | Mar 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | HYDRAULIC SYSTEM(POWERPACKS& VALVE STANDS) |  | 91400 | 8226000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  | AULOS |  |  | 7906000 | PICKLING | Mar 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | PNEUMATIC PIPE ,VALVES & FITTINGS |  | 25000 | 2250000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EHS Casing-1 Assembly with Hearth Roll (2 CASING) |  |  | 8145000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Refractory |  |  | 19910000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | CCS Casing-1 Assembly with Hearth roll & Refractory (1 CASING) |  |  | 2715000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | CCS Casing-2 Assembly with Hearth roll & Refractory (3 CASING) |  |  | 8145000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | CCS Casing-3 Assembly with Hearth roll & Refractory (1 CASING) |  |  | 2715000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | CCS Casing-4 Assembly with Hearth roll & Refractory (1 CASING) |  |  | 2715000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | COOLING TUBE |  |  | 28055000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | CCS Ducting |  |  | 3620000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | DILUTION DUCT |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | HS Casing-1 Assembly with Hearth Roll & Refractory (1 CASING) |  |  | 2715000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | HS Casing-2 Assembly with Hearth Roll & Refractory (3 CASING) |  |  | 2715000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | HS Casing-3 Assembly with Hearth Roll & Refractory (3 CASING) |  |  | 2715000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | HS Casing-4 Assembly with Hearth Roll & Refractory (1 CASING) |  |  | 2715000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Furnace Structure - MAR LOT |  |  | 21720000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Quench Tank Assembly |  |  | 3620000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Compensating Cable |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Solenoid Shut-Off Valves |  |  | 1810000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Pressure Gauges |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Orifice Plates |  |  | 3620000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Recuperator For Non-OX Furnace |  |  | 6335000 | Disp. | 2026-03-28 |  | FALSE | FALSE |  |  | 5184000 |  |  | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Fan-3 Nos |  |  | 3620000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Furnace Bellows |  |  | 905000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Portable analyser |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | H2O2 Dew Point Analyzer |  |  | 1810000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Quench Fume Exhaust |  |  | 1810000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Edge wiper |  |  | 905000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SNUBBER WITH BENDING ROLL ASSY.#2 |  |  | 905000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ENTRY PINCH ROLL ASSY.#2 |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | LEVELLER ASSY.#2 |  |  | 9050000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EPC SENSOR FRAME |  |  | 905000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | STITCHER |  |  | 38915000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | HOLE DETECTOR#1 |  |  | 905000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | DOUBLE STEERING ROLL ASSY.#1 (BEFORE ENTRY ACC.) |  |  | 3620000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ENTRY HORIZONTAL ACCUMULATOR-SWING ARM, STRIP SUPPORT |  |  | 2715000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ENTRY HORIZONTAL ACCUMULATOR ASSY. |  |  | 16290000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SINGLE STEERING ROLL ASSY.#3 (INSIDE ENTRY ACC.) |  |  | 3620000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | HOLE DETECTOR#2 |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | DOUBLE STEERING ROLL ASSY.#4 (BEFORE FURNACE) |  |  | 3620000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | STEERING STRUCTURE |  |  | 905000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE AFTER BRIDLE ROLL ASSY.#3 |  |  | 905000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE BEFORE TENSIOMETER ROLL ASSY. |  |  | 1810000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | TENSIOMETER ROLL ASSY. (BEFORE FURNACE) |  |  | 905000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ROLLER TABLE BEFORE FURNACE |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SINGLE SQUEEZE ROLL ASSY.@ QUENCH SECTION |  |  | 1810000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | EDGE BLOW OFF AIR WIPER ASSY. |  |  |  | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | BRIDLE ROLL ASSY.#5 (AFTER FURNACE SECTION) |  |  | 8145000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | DOUBLE STEERING ROLL ASSY.#5 (AFTER FURNACE SECTION) |  |  | 3620000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | PORTER BAR ASSY. (ROLL REMOVAL ARRANGEMENT) |  |  | 905000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | DOUBLE STEERING ROLL ASSY.#6 (AFTER PICKLING) |  |  | 6335000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXIT HORIZONTAL ACCUMULATOR ASSY.-SUPPORT ROLL |  |  | 6335000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | DOUBLE STEERING ROLL ASSY.#9 (BEFORE EXIT SECTION) |  |  | 3620000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | BELT WRAPPER ASSY. |  |  | 1810000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | PIPES & FITTINGS-LOT 1 |  |  | 905000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | FRVE PIPES(FRSVE)& FITTING, FRP GRATING, PVDF PUMP, MOTOR 10HP 2900 RPM IE3 |  |  | 1810000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | FURNACE INTERCONNECTING PIPINGS-Lot 1 |  |  | 4525000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | FURNACE INTERCONNECTING PIPINGS-Lot 2 |  |  | 4525000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | BOI | ADITYA SHARMA | PICKLING STRUCTURE, PLATEFORM & WALKWAYS |  |  | 905000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SUPPORT ROLL ASSY.#1 |  |  | 1810000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SUPPORT ROLL ASSY.#2 |  |  | 1810000 | Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | APL | Mar 2026
2516-APL-5 TANK PICKLING | BOI | ADITYA SAINI | ACID RECIRCULATION SYSTEM, FUME EXHAUST & SCRUBBING SYSTEM-Lot 1 |  |  | 14950000 | Not Disp. | 2026-03-28 |  | TRUE | FALSE | [5 empty] | APL | Mar 2026
2536-JSW-PICKLING REVAMP | BOI |  | PICKLING TANKS |  |  | 24800000 | Not Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | REVAMP | Mar 2026
2541-STELCO-ELECTRICAL | UNIT-2 |  | ELECTRICAL |  |  | 10500000 | Not Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | ELECTRICAL | Mar 2026
2542-STELCO-ELECTRICAL | UNIT-2 |  | ELECTRICAL |  |  | 10500000 | Not Disp. | 2026-03-28 |  | FALSE | FALSE | [5 empty] | ELECTRICAL | Mar 2026
2421-APL-CGL | UNIT-2 | SAURABH | HORIZONTAL ACCUMULATOR ASSY. STRUCTURE |  |  | 0 | Not Disp. | 2026-03-19 |  | FALSE | FALSE | [5 empty] | CGL | Mar 2026
2425-MMI-6HI CRM | BOI | MAYANK | CPC |  | 10000 | 860000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | ADVANCE PAYMENT & LC REQUIRED |  |  |  | CRM | Feb 2026
2425-MMI-6HI CRM | UNIT-1 | MAYANK | IMR CHOCKS (SPARE) - 4 NOS. |  | 6000 | 516000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | UNDER ASSEMBLY |  |  |  | CRM | Feb 2026
2425-MMI-6HI CRM | UNIT-1 | MAYANK | WORK ROLL CHOCKS (SPARE) - 4 NOS. |  | 6000 | 516000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | UNDER ASSEMBLY |  |  |  | CRM | Feb 2026
2425-MMI-6HI CRM | UNIT-1 | MAYANK | WORK ROLL CHOCKS (SPARE) - 4 NOS. |  | 6000 | 516000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | UNDER ASSEMBLY |  |  |  | CRM | Feb 2026
2404-GOPANI-4HI SPM | UNIT-3 | ADITYA SHARMA | EXIT AIR KNIFE ASSY. |  |  | 500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | SPM | Feb 2026
2404-GOPANI-4HI SPM | BOI | ADITYA SHARMA | PIPES & FITTINGS |  |  | 1100000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | SPM | Feb 2026
2414-UTTAM-6HI CRM | UNIT-1 | ADITYA SHARMA | SPARE-BACKUP ROLL CHOCKS-1 set |  |  | 6000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2518-APL-SPM | BOI | MAYANK | GEARBOX LUBRICATION SYSTEM |  |  | 2000000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  |  |  | PAYMENT / LC | 1176000 | SPM | Feb 2026
2518-APL-SPM | BOI | MAYANK | AIR-OIL SYSTEM |  |  | 7500000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | SPM | Feb 2026
2518-APL-SPM | BOI | MAYANK | HIGH PRESSURE ROLL CLEANING SYSTEM (LECHLER) |  |  | 5000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | SPM | Feb 2026
2518-APL-SPM | BOI | MAYANK | FUME EXHAUST SYSTEM |  |  | 10000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | SPM | Feb 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | COIL CAR ASSY. @ UNCOILER |  |  | 3000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2428-BMWIL-CGL | UNIT-2 | TRIPURARI | COIL CAR ASSY. @ RECOILER |  |  | 1500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2428-BMWIL-CGL |  | TRIPURARI | ENTRY ACCUMULATOR FIXED FRAME |  |  | 9500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2420-INDIA STEEL-CCL | BOI | SAURABH | Thermocouple & cable |  |  | 50000 | Not Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CCL | Feb 2026
2420-INDIA STEEL-CCL | BOI | SAURABH | Gas Flow Meter |  |  | 565705 | Not Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CCL | Feb 2026
2420-INDIA STEEL-CCL |  | SAURABH | Structure-Handrails |  |  | 1000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CCL | Feb 2026
2420-INDIA STEEL-CCL |  | SAURABH | Unwinder guard film |  |  | 500000 | Not Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CCL | Feb 2026
2427-PROMPT-6HI CRM | UNIT-1 | MAYANK | SCRAP TROLLEY |  |  | 100000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | FABRICATION PENDING |  |  |  | CRM | Feb 2026
2427-PROMPT-6HI CRM | UNIT-1 | MAYANK | BACKUP ROLL CHOCKS (4 NOS.) |  |  | 2800000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2427-PROMPT-6HI CRM | BOI | MAYANK | GEARED SPINDLE COUPLING (2 NOS.) |  |  | 3000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2427-PROMPT-6HI CRM | BOI | MAYANK | SPARE - BACKUP CHOCK BEARINGS (6 NOS.) |  |  | 2350000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | POR-COIL CAR PIT COVER |  |  | 200000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | UNDER ASSEMBLY |  |  |  | CRM | Feb 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | ETR-COIL CAR PIT COVER |  |  | 350000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | UNDER ASSEMBLY |  |  |  | CRM | Feb 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | DTR-COIL CAR PIT COVER |  |  | 250000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | UNDER ASSEMBLY |  |  |  | CRM | Feb 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | POR-OBBS ASSY |  |  | 1000000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | UNDER FABRICATION |  |  |  | CRM | Feb 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | MOTOR BASE FRAME FOR ETR |  |  | 2500000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | UNDER M/C IN HOUSE |  |  |  | CRM | Feb 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | MOTOR BASE FRAME FOR MILL DRIVE |  |  | 2500000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | UNDER M/C IN HOUSE |  |  |  | CRM | Feb 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | ETR ELECTROMAGNETIC BRAKE WITH BASE FRAME |  |  | 2000000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | LC REQUIRED TO LIFT THE BRAKE | 1517508 |  |  | CRM | Feb 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | DTR ASSY |  |  | 22500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | DTR ELECTROMAGNETIC BRAKE WITH BASE FRAME |  |  | 2000000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | LC REQUIRED TO LIFT THE BRAKE | 1517508 |  |  | CRM | Feb 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | CARRY OVER TABLE |  |  | 1000000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | UNDER ASSEMBLY |  |  |  | CRM | Feb 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | INTERCONNECTING PIPING |  |  | 1275000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | COOLANT PIPES & FITTINGS |  |  | 4000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2511-GAURANG-6HI | BOI | MAYANK | HYDRAULIC PIPES,FITTINGS. |  |  | 5000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2511-GAURANG-6HI |  | MAYANK | AIR OIL LUBRICATION SYSTEM ASSY |  |  | 2000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2511-GAURANG-6HI |  | MAYANK | THICKNESS GUAGE |  |  | 13500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | DRAG CHAIN, FRAME, RAIL LINE @ UNCOILER |  |  | 600000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DRAG CHAIN, FRAME, RAIL LINE @ RECOILER |  |  | 300000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-3 | SAURABH | UNCOILER #1 WITH SNUBBER ROLL |  |  | 6500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-3 | SAURABH | RECOILER WITH PUSHER PLATE |  |  | 7500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRIDLE ROLL ASSY.#1 |  |  | 3500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRIDLE ROLL ASSY.#2 |  |  | 3500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRIDLE ROLL ASSY.#7 |  |  | 3500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRIDLE ROLL ASSY.#8 |  |  | 3500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRIDLE ROLL ASSY.#10 |  |  | 3500000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Exit Accumulator Top frame |  |  | 6325000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DOUBLE STEERING ROLL ASSY. @ CAG, STRIP HEATER, BEFORE EXIT ACC ASSY.-2 ASSY. |  |  | 3000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ENTRY PINCH ROLL ASSY.#5 |  |  | 250000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | EXIT PINCH ROLL ASSY. #1 |  |  | 250000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | VERTICAL CHEMICAL COATER ASSY.-2 ASSY |  |  | 6000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | FURNACE -STRUCTURE,CHEQUERED PLATE |  |  | 4105850 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | FASTNERS |  |  | 200000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ELECTRICAL PANEL LOT 2-FEB |  |  | 40000000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CGL | Feb 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | DRAG CHAIN @ POR, ETR & DTR |  | 7101.675 | 635599.9125 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | SHUTTER ASSY |  | 2000 | 179000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | UNIT-2 | MAYANK | ELECTRICAL PACKAGE |  | 554400 | 49618800 | Not Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | DISTRIBUTION HEADER |  | 5000 | 447500 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | BACKUP CHOCK BEARINGS - 4 NOS |  | 80000 | 7160000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | IMR CHOCK BEARINGS - 4NOS |  | 12000 | 1074000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | WORK ROLL CHOCK BEARINGS - 4 NOS |  | 8000 | 716000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | OIL SPRAYING SYSTEM |  | 5000 | 447500 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | FOUNDATION BOLTS + TAPER PLATES SET |  | 22258.25 | 1992113.375 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | COOLANT FILTERATION SYSTEM |  | 128000 | 11456000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  |  |  | LC | 7769700 | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | HYDRAULIC POWER PACK & VALVE TABLE ASSY |  | 190000 | 17005000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | GEAR LUBRICATION SYSTEM ASSY |  | 15000 | 1342500 | Disp. | 2026-02-28 |  | FALSE | FALSE |  |  |  | PAYMENT / LC | 961200 | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | IMR ROLLS - 2 NOS |  | 17000 | 1521500 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | WORK ROLLS - 2 NOS |  | 10000 | 895000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | HYDRAULIC FITTINGS |  | 35000 | 3132500 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | COOLANT PIPES & FITTINGS |  | 25000 | 2237500 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2501-AL SHAKER-6HI CRM | BOI | MAYANK | PNEUMATIC PIPES & FITTINGS |  | 3750 | 335625 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | CRM | Feb 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | ENTRY COIL CAR ASSY. |  | 66000 | 5953200 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Feb 2026
2502-AL SHAKER-PICKLING | UNIT-2 | ADITYA SAINI | EXIT COIL CAR ASSY. |  | 33000 | 2976600 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Feb 2026
2502-AL SHAKER-PICKLING | BOI | ADITYA SAINI | ACID RECIRCULATION SYSTEM, FUME EXHAUST & SCRUBBER SYSTEM -Lot 1 |  | 216400 | 19400260 | Disp. | 2026-02-28 |  | FALSE | FALSE |  | NAVJEEVAN |  |  | 21004000 | PICKLING | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | DFF Casing-1 Assembly with Hearth Roll & Refractory (8 CASING) |  |  | 79640000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | DFF Casing-2 Assembly with Hearth Roll & Refractory (1 CASING) |  |  | 9955000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXHAUST CASING FOR TUNNEL |  |  | 2715000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Throat Assembly with Hearth Roll & Refractory |  |  | 3620000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | REFRACTORY |  |  | 2715000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Furnace Structure - FEB LOT |  |  | 12670000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Adjustable Gas Control valves |  |  |  | Disp. | 2026-02-28 |  | FALSE | FALSE |  |  | 1193371 |  |  | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Thermocouple |  |  | 3620000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | IR Pyrometers |  |  | 3620000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Low Pressure Switch |  |  | 905000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | FURNACE BLAST GATE VIEW |  |  | 905000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Rotameters |  |  |  | Disp. | 2026-02-28 |  | FALSE | FALSE |  |  | 32155 |  |  | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Fan-7 Nos |  |  | 8145000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  |  | 10915000 |  |  | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | HNX Gas Station |  |  | 6335000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Furnace Bellows |  |  | 7240000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  |  | 4167742.04 |  |  | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Main gas station |  |  | 1810000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL |  | ADITYA SHARMA | RAIL LINE |  |  | 3620000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ENTRY DRAG CHAIN ASSY.#02 |  |  | 905000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | PEELER TABLE ASSY.#2 |  |  | 905000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | NOTCHER |  |  | 9955000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  |  | 5760000 |  |  | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | BRIDLE ROLL ASSY.#1 (BEFORE ENTRY ACC.) |  |  | 10860000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SINGLE STEERING ROLL ASSY.#2 (INSIDE ENTRY ACC.) |  |  | 3620000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | STEERING STRUCTURE |  |  | 905000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | BRIDLE ROLL ASSY.#3 (BEFORE FURNACE) |  |  | 9050000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | BRIDLE ROLL ASSY.#4 (AFTER FURNACE SECTION) |  |  | 9050000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | PICKLING TANK#2 (18 meter) |  |  | 6335000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | PICKLING TANK#3 (18 meter) |  |  | 6335000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | RINSING SECTION |  |  | 12670000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | SQUEEZE ROLL TANK WITH GRANITE |  |  | 11765000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | FITTINGS & ACCESSORIES FOR SCRUBBING SYSTEM |  |  | 1810000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | FUME EXHAUST SCRUBBING SYSTEM |  |  | 905000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SINGLE SQUEEZE ROLL ASSY. (13 Assembly) |  |  | 8145000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXIT HORIZONTAL ACCUMULATOR ASSY. |  |  | 2715000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXIT HORIZONTAL ACCUMULATOR ASSY.-MOVING FRAME |  |  | 4525000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXIT HORIZONTAL ACCUMULATOR ASSY.-STRIP SUPPORT FRAME |  |  | 3620000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXIT HORIZONTAL ACCUMULATOR ASSY.-SWING ARM & STEEL WIRE ROPE |  |  | 6335000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXIT HORIZONTAL ACCUMULATOR ASSY.-SUPPORT ROLL |  |  | 5430000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SINGLE STEERING ROLL ASSY.#7 (INSIDE EXIT ACC.) |  |  | 3620000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SINGLE STEERING ROLL ASSY.#8 (INSIDE EXIT ACC.) |  |  | 3620000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | STEERING SYSTEM & EPC SENSOR ASSY |  |  | 31675000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXIT PINCH ROLL ASSY.#2 |  |  | 2715000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXIT DRAG CHAIN ASSY.#1 |  |  | 905000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | EXIT THREADING TABLE ASSY.#1 |  |  | 905000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | PICKLING STRUCTURE, PLATEFORM & WALKWAYS |  |  | 3620000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SUPPORT ROLL ASSY.#3 |  |  | 905000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SUPPORT ROLL ASSY.#4 |  |  | 905000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SPARE MOTOR |  |  | 2715000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | SPARE -Squeeze roll |  |  | 1810000 | Disp. | 2026-02-28 |  | FALSE | FALSE | [5 empty] | APL | Feb 2026
2506-JSW-APL | BOI | ADITYA SHARMA | HYDRAULIC POWER PACK & VALVE STAND-FEB LOT |  |  | 15385000 | Disp. | 2026-02-28 |  | FALSE | FALSE |  |  | 14000740 |  |  | APL | Feb 2026
2405-JSPL-TRIMMING | BOI | SAURABH | MISCELLANEOUS |  |  | 165000 | Not Disp. | 2026-01-29 |  | FALSE | FALSE |  | Site req fitting and clamp |  |  |  | TRIMMING | Jan 2026
2424-MMI-6HI CRM | UNIT-2 | MAYANK | Mill hood assembly |  | 2325 | 199950 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Jan 2026
2424-MMI-6HI CRM | UNIT-1 | MAYANK | ROTARY UNION FOR TENSION REEL - 1 NO. (SPARE) |  | 0 | 0 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Jan 2026
2424-MMI-6HI CRM | UNIT-1 | MAYANK | WORK ROLL CHOCKS - 8 NOS. (SPARE) |  | 3488 | 312176 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | 4 NOS. DISPATCHED, 4 NOS. UNDER ASSEMBLY TENTATIVE COMPLETION 25-12-2025 |  |  |  | CRM | Jan 2026
2425-MMI-6HI CRM | UNIT-2 | MAYANK | Mill top platform assembly |  | 25000 | 2237500 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CRM | Jan 2026
2425-MMI-6HI CRM | UNIT-1 | MAYANK | SEAL KIT FOR HYDRAULIC CYLINDER - 1 SET |  | 0 | 0 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jan 2026
2425-MMI-6HI CRM | UNIT-1 | MAYANK | HYDRAULIC HOSE PIPE - 12 NOS. |  | 0 | 0 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jan 2026
2425-MMI-6HI CRM | UNIT-1 | MAYANK | BACKUP ROLL CHOCKS (SPARE) - 4 NOS. |  | 110000 | 9460000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | CHOCKS UNDER ASSEMBLY |  |  |  | CRM | Jan 2026
2425-MMI-6HI CRM | UNIT-1 | MAYANK | IMR CHOCKS (SPARE) - 4 NOS. |  | 34000 | 2924000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | CHOCKS UNDER ASSEMBLY |  |  |  | CRM | Jan 2026
2425-MMI-6HI CRM | UNIT-1 | MAYANK | WORK ROLL CHOCKS (SPARE) - 4 NOS. |  | 24000 | 2064000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | CHOCKS UNDER MACHINING, BALANCE ITEMS FULL KIT |  |  |  | CRM | Jan 2026
2404-GOPANI-4HI SPM | BOI | ADITYA SHARMA | BACKUP ROLL -2NOS |  |  | 2200000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | SPM | Jan 2026
2404-GOPANI-4HI SPM | BOI | ADITYA SHARMA | WR ROLL-2NOS |  |  | 600000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | SPM | Jan 2026
2414-UTTAM-6HI CRM | UNIT-2 | ADITYA SHARMA | TOP PLATFORM |  |  | 1000000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CRM | Jan 2026
2414-UTTAM-6HI CRM | UNIT-1 | ADITYA SHARMA | SPARE-WORK ROLL CHOCKS-1set |  |  | 3200000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CRM | Jan 2026
2231-SHYAM-6HI CRM | UNIT-1 | SAURABH | ROTARY UNION ( SPARE ) |  |  | 0 | Not Disp. | 2026-01-28 |  | FALSE | FALSE |  | 4500010179 |  |  |  | CRM | Jan 2026
2305-APL-CGL | BOI | SAURABH | Furnace blanket |  |  | 50000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2305-APL-CGL | BOI | SAURABH | Coating gauge support roll 2 nos |  |  | 50000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2426-VIKAS-PICKLING | BOI | SACHIN | OIL SPRAYING SYSTEM |  |  | 100000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jan 2026
2426-VIKAS-PICKLING | BOI | SACHIN | EPC SYSTEM |  |  | 745000 | Not Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jan 2026
2426-VIKAS-PICKLING | BOI | SACHIN | GRANITE BLOCKS |  |  | 840000 | Not Disp. | 2026-01-28 |  | FALSE | FALSE |  | ready at vendor end |  |  |  | PICKLING | Jan 2026
2426-VIKAS-PICKLING | BOI | SACHIN | HOT AIR DRYER |  |  | 1100000 | Not Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jan 2026
2426-VIKAS-PICKLING | BOI | SACHIN | TEMP. CONTROL VALVES |  |  | 200000 | Not Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jan 2026
2426-VIKAS-PICKLING | BOI | SACHIN | HEAT EXCHANGERS |  |  | 500000 | Not Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Jan 2026
2421-APL-CGL |  | SAURABH | AIR DRYER @ CAG |  |  | 500000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | 5,00,000. |  |  |  | CGL | Jan 2026
2421-APL-CGL | BOI | SAURABH | HYDRAULIC & PNEUMATIC FITTING-Lot 2 |  |  | 500000 | Not Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2421-APL-CGL | BOI | SAURABH | Air Knife Piping Assembly |  |  | 500000 | Not Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2421-APL-CGL | BOI | SAURABH | Solenoid Shut-Off Valves |  |  | 350000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2421-APL-CGL | BOI | SAURABH | Electric Heater |  |  | 2868956 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2421-APL-CGL | BOI | SAURABH | Orifice Plates |  |  | 1150000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2421-APL-CGL | BOI | SAURABH | Pneumatic Shut-Off Valves |  |  | 1117669 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2421-APL-CGL | BOI | SAURABH | Hot Air Control Valve |  |  | 1310461 | Not Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2421-APL-CGL | BOI | SAURABH | Blower Fan-Lot 2 |  |  | 1500000 | Not Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2421-APL-CGL | BOI | SAURABH | FURNACE-HEARTH ROLL CARDEN SHAFT (1 NO.) |  |  | 0 | Not Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2421-APL-CGL |  | SAURABH | - |  |  | 0 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2421-APL-CGL | BOI | SAURABH | Valves & Dampers |  |  | 3500000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2421-APL-CGL | BOI | SAURABH | Flow Control Valve |  |  | 1000000 | Not Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2518-APL-SPM | UNIT-2 | MAYANK | ELECTRICAL |  |  | 4000000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | SPM | Jan 2026
2420-INDIA STEEL-CCL | UNIT-2 | SAURABH | RECOILER SLEEVE LOADER ASSY. |  |  | 615000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CCL | Jan 2026
2420-INDIA STEEL-CCL | BOI | SAURABH | STITCHER ASSY. |  |  | 5200000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | 4500006086, Ready by jan |  |  |  | CCL | Jan 2026
2420-INDIA STEEL-CCL | BOI | SAURABH | Incinerator Jan lot |  |  | 1650000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CCL | Jan 2026
2420-INDIA STEEL-CCL | BOI | SAURABH | Pressure Transmitters |  |  | 400000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | 4500009951, Ready |  |  |  | CCL | Jan 2026
2420-INDIA STEEL-CCL | BOI | SAURABH | Temperature Transmitters |  |  | 765000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | 4500009957, Ready |  |  |  | CCL | Jan 2026
2420-INDIA STEEL-CCL | BOI | SAURABH | Hot Air Control Valve / Damper |  |  | 2040000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | 4500010481-PDC REQ. 17 Dec |  |  |  | CCL | Jan 2026
2427-PROMPT-6HI CRM | UNIT-3 | MAYANK | RAIL LINE, CLAMP PLATE & BOLT FOR COIL CAR & QWRC |  |  | 100000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CRM | Jan 2026
2427-PROMPT-6HI CRM | UNIT-3 | MAYANK | DRAG CHAIN-POR,ETR DTR |  |  | 100000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | DRAG CHAIN RECEIVED, FRAME FABRICATION PENDING |  |  |  | CRM | Jan 2026
2427-PROMPT-6HI CRM | BOI | MAYANK | AIR OIL LUBRICATION SYSTEM ASSY |  |  | 3550000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  |  | 3124000 |  |  | CRM | Jan 2026
2427-PROMPT-6HI CRM |  | MAYANK | WORK ROLL CHOCKS (4 NOS.) |  |  | 800000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | CHOCKS UNDER MACHINING, LINERS PENDING |  |  |  | CRM | Jan 2026
2427-PROMPT-6HI CRM | UNIT-3 | MAYANK | TAPER WEDGE POSITION TRANSDUCER ASSY. |  |  | 0 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | CYL. PENDING |  |  |  | CRM | Jan 2026
2427-PROMPT-6HI CRM | UNIT-3 | MAYANK | ROLL FORCE CYL ASSY |  |  | 2000000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | 1 NOS. RFC PENDING AT HYDMARK |  |  |  | CRM | Jan 2026
2521-BMWIL-6HI CRM | UNIT-2 | MAYANK | ELECTRICAL |  |  | 73000000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CRM | Jan 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | POR-MANDREL ASSY |  |  | 3550000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | FULL KIT, UNDER ASSEMBLY |  |  |  | CRM | Jan 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | POR-GEARBOX ASSY |  |  | 6900000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | FULL KIT, UNDER ASSEMBLY |  |  |  | CRM | Jan 2026
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | POR-SNUBBER ROLL ASSY |  |  | 550000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | FULL KIT, UNDER ASSEMBLY |  |  |  | CRM | Jan 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | THREE ROLL FEEDER |  |  | 4000000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | UNDER ASSEMBLY |  |  |  | CRM | Jan 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | ENTRY SHEAR |  |  | 1400000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jan 2026
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | PASSING TABLE #1 (BET. THREE ROLL FEEDER & ENTRY SHEAR) |  |  |  | Disp. | 2026-01-28 |  | FALSE | FALSE |  | UNDER ASSEMBLY |  |  |  | CRM | Jan 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | BACKUP CHOCK BEARINGS (6 NOS.) |  |  | 5732000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | LC REQUIRED |  |  |  | CRM | Jan 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | WORK ROLL CHOCK BEARINGS (4 NOS.) |  |  | 1045000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | LC REQUIRED |  |  |  | CRM | Jan 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | IMR CHOCKS BEARINGS (4 NOS.) |  |  | 1274000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | LC REQUIRED |  |  |  | CRM | Jan 2026
2521-BMWIL-6HI CRM | BOI | MAYANK | BACKUP ROLLS (2 NOS.) |  |  | 10400000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  |  | 10488000 |  |  | CRM | Jan 2026
2522-APL-SPM | UNIT-2 | ADITYA SAINI | UNCOILER-COIL CAR ASSY. |  |  | 500000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | SPM | Jan 2026
2522-APL-SPM | UNIT-2 | ADITYA SAINI | RECOILER-COIL CAR ASSY. |  |  | 500000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | SPM | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | COIL SADDLE ASSY. @ UNCOILER |  |  | 200000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | COIL SADDLE ASSY. @ RECOILER |  |  | 100000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRIDLE ROLL ASSY.#3 |  |  | 3500000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRIDLE ROLL ASSY.#4 |  |  | 3500000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRIDLE ROLL ASSY.#5 |  |  | 3500000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRIDLE ROLL ASSY.#6 |  |  | 3500000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | BRIDLE ROLL ASSY.#9 |  |  | 3500000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Entry Accumulator Counter weight |  |  | 600000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Entry Acc wire rope |  |  | 200000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Exit Accumulator Counter weight |  |  | 600000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | Exit Accumulator Wire rope |  |  | 200000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DOUBLE STEERING ROLL ASSY. @ CAG, STRIP HEATER, BEFORE EXIT ACC ASSY.-1 ASSY. |  |  | 1500000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #14 |  |  | 300000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #17 |  |  | 300000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE |  | SAURABH | SUPPLY OF ENGINEERING |  |  | 2000000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | BOI | SAURABH | FOUNDATION BOLT - 1 & EXIT ACCUM STRUCTURAL BEAM |  |  | 550000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | ELECTRICAL PANEL LOT 1-JAN |  |  | 15000000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CGL | Jan 2026
2501-AL SHAKER-6HI CRM | UNIT-3 | MAYANK | POR ASSEMBLY WITH SNUBBER |  | 74079.4244 | 6630108.4866 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | CRM | Jan 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | DTR ASSEMBLY WITH PUSHER PLATE |  | 136835.9386 | 12246816.508 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jan 2026
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | THREE ROLL FEEDER ALONG WITH PASSING TABLE |  | 60000 | 5370000 | Disp. | 2026-01-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Entry seal with Tunnel |  |  | 905000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Entry Seal Assembly with Refractory |  |  |  | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Entry Seal Drive Assembly |  |  |  | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Tunnel-1 Assembly with Hearth Roll & Refractory (1 Casing) |  |  | 4525000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Tunnel-2 Assembly with Hearth Roll & Refractory(3 Casing) |  |  | 8145000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Tunnel-3 Assembly with Hearth Roll & Refractory (2 Casing) |  |  | 5430000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Tunnel-4 Assembly with Hearth Roll & Refractory (1 Casing) |  |  | 4525000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Tunnel-5 Assembly with Hearth Roll & Refractory (1 Casing) |  |  | 4525000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | Exhaust Casing Assembly |  |  | 905000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | INNER COOLING TUBE |  |  | 5430000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Furnace Structure - JAN LOT |  |  | 6335000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Temperature Transmitters |  |  | 905000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | BOI | ADITYA SHARMA | Pressure Transmitters |  |  | 905000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | UNCOILER MANDREL ASSY.#2 |  |  | 9050000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | UNCOILER GEARBOX ASSY.#2 |  |  |  | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | ACCUMULATOR STRUCTURE |  |  | 2715000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#01 |  |  | 1810000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | BRIDLE ROLL ASSY.#2 (BEFORE FURNACE) |  |  | 4525000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | PINCH ROLL ASSY. (BEFORE FURNACE) |  |  | 905000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | PINCH ROLL ASSY. (AFTER FURNACE) |  |  | 905000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | BOI | ADITYA SHARMA | PICKLING TANK#1 (18 meter) |  |  | 5430000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | BOI | ADITYA SHARMA | ACID RECIRCULATION SYSTEM |  |  | 7240000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | BOI | ADITYA SHARMA | FUME EXHAUST SCRUBBING SYSTEM FOR ACID TANKS & RINSE TANK |  |  | 6335000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | BRIDLE ROLL ASSY.#7 (AFTER PICKLING) |  |  | 4525000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | BRIDLE ROLL ASSY.#8 (BEFORE EXIT SECTION) |  |  | 5430000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | RECOILER MANDREL ASSY.#1 |  |  | 9955000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | RECOILER GEARBOX ASSY.#1 |  |  |  | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | UNIT-2 | ADITYA SHARMA | RECOILER PUSHER PLATE ASSY.#1 |  |  |  | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL |  | ADITYA SHARMA | SUMP PUMPS |  |  | 2715000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | BOI | ADITYA SHARMA | HYDRAULIC POWER PACK & VALVE STAND-JAN LOT |  |  | 1810000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | BOI | ADITYA SHARMA | FOUNDATION BOLT |  |  | 905000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | BOI | ADITYA SHARMA | TAPER PLATE |  |  | 905000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2506-JSW-APL | BOI | ADITYA SHARMA | ELECTRICAL SPARES-JAN LOT |  |  | 5430000 | Disp. | 2026-01-28 |  | FALSE | FALSE | [5 empty] | APL | Jan 2026
2424-MMI-6HI CRM |  | MAYANK | CPC |  | 10000 | 860000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY FOR DISPATCH FROM EMG, MUMBAI. LC TO BE EXTENDED |  |  |  | CRM | Dec 2025
2424-MMI-6HI CRM |  | MAYANK | AC Motor ETR, DTR, Mill & Pay Off |  | 209302.3256 | 18000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2424-MMI-6HI CRM |  | MAYANK | BACKUP ROLL CHOCKS - 2 NOS. (SPARE) |  | 11627.907 | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CRM | Dec 2025
2424-MMI-6HI CRM |  | MAYANK | WORK ROLL CHOCKS - 4 NOS. (SPARE) |  | 3488 | 312176 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2425-MMI-6HI CRM |  | MAYANK | Hydraulic , pneumatic , MS pipes & fittings |  | 0 | 0 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Dec 2025
2425-MMI-6HI CRM |  | MAYANK | Imr Chocks - 4 nos |  | 34000 | 2924000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | FULL KIT INCLUDING MACHINING |  |  |  | CRM | Dec 2025
2425-MMI-6HI CRM |  | MAYANK | ELECTROMAGNETIC BRAKE - 1 NOS. (FOR ETR) |  | 70000 | 6265000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2425-MMI-6HI CRM |  | MAYANK | Cellar ventilation blower |  | 70000 | 6265000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Dec 2025
2425-MMI-6HI CRM |  | MAYANK | ELECTROMAGNETIC BRAKE - 1 NOS. (FOR ETR) |  | 70000 | 6265000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2425-MMI-6HI CRM |  | MAYANK | Cellar ventilation duct |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE |  | TO BE FABRICATED AT SITE, AS PER DISCUSSION WITH MR. ANIL SHARMA |  |  |  | CRM | Dec 2025
2425-MMI-6HI CRM |  | MAYANK | AC Motor (ETR - 2nos , DTR - 1no , Mill - 2nos & Pay Off - 2nos) |  |  | 6000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2425-MMI-6HI CRM |  | MAYANK | AC Motor (ETR - 2nos , DTR - 1no , Mill - 2nos & Pay Off - 2nos) |  | 517000 | 38400000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | MOTORS ARE UNDER TESTING AND PAINTING |  |  |  | CRM | Dec 2025
2403-GOPANI-4HI CRM |  | MAYANK | SPARE CHOCKS (1 SETS - WR) |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CRM | Dec 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | BACKUP STOOL ASSY |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | SPM | Dec 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | PASSING TABLE |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | SPM | Dec 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | BACKUP OUTSIDE TRACK |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | SPM | Dec 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | ELECTRICAL |  |  | 4000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | SPM | Dec 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | WR CHOCK BEARINGS 4 NOS |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | SPM | Dec 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | SPARE-BACK UP CHOCKS WITHOUT BEARINGS-4 nos |  |  | 1500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Dec 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | SPARE-WORK ROLL CHOCKS WITHOUT BEARINGS-8 nos |  |  | 1500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Dec 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | BACK UP ROLL - 2nos |  |  | 10200000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | Geared spindle |  |  | 6603300 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Shipment By Sea |  |  |  | CRM | Dec 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | CPC |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Payment Required |  |  |  | CRM | Dec 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | SPARE-IMR ROLLS CHOCKS-1 set |  |  | 1600000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2231-SHYAM-6HI CRM |  | SAURABH | ETR DTR Safety cage |  |  | 50000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2231-SHYAM-6HI CRM |  | SAURABH | HYD MOTOR ( SPARE ) |  |  | 25000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | 4500006877 |  |  |  | CRM | Dec 2025
2231-SHYAM-6HI CRM |  | SAURABH | CELLAR VENTILATION DUCT |  |  | 150000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2231-SHYAM-6HI CRM |  | SAURABH | WR chocks - 4 nos (1 SET) spares |  |  | 260000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2405-JSPL-TRIMMING |  | SAURABH | PIT COVER @ UNCOILER |  |  | 400000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2025
2405-JSPL-TRIMMING |  | SAURABH | PIT COVER @ RECOILER |  |  | 400000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2025
2405-JSPL-TRIMMING |  | SAURABH | EPC |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Dispatch on 24 dec |  |  |  | TRIMMING | Dec 2025
2405-JSPL-TRIMMING |  | SAURABH | CPC |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Dispatch on 24 dec |  |  |  | TRIMMING | Dec 2025
2405-JSPL-TRIMMING |  | SAURABH | RAIL LINE & DRAG CHAIN 2 Meter |  |  | 465000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2025
2405-JSPL-TRIMMING |  | SAURABH | CPC & EPC FRAMES |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Dec 2025
2305-APL-CGL |  | SAURABH | TENSION LEVELLER ASSY. |  |  | 13600000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Material ready at China, LC Open by 27 oct |  |  |  | CGL | Dec 2025
2305-APL-CGL |  | SAURABH | VALVE 5 nos |  |  | 50000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2305-APL-CGL |  | SAURABH | Degreasing Heat exchanger |  |  | 50000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2305-APL-CGL |  | SAURABH | Threading pipe 2 nos |  |  | 50000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2305-APL-CGL |  | SAURABH | Down Chute Structure |  |  | 50000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Ready by 7 nov, material will send by 28 oct |  |  |  | CGL | Dec 2025
2305-APL-CGL |  | SAURABH | Heat exchanger |  |  | 5000000 | Not Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2412-HI TECH-SPARE |  | MAYANK | SPARE |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | SPARE | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | ENTRY COIL CAR ASSY. |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | ENTRY DRAG CHAIN ASSY. |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | ENTRY COIL SADDLE |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | EXIT COIL CAR ASSY. |  |  | 1500000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | EXIT DRAG CHAIN ASSY |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | EXIT COIL SADDLE ASSY. |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | UNCOILER MANDREL ASSY (STEPPED CONE TYPE)#1, GEAR BOX |  |  | 4000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | SNUBBER WITH BENDING ROLL ASSY.#1 |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | RECOILER MANDREL,GEARBOX, PUSHER PLATE ASSY. |  |  | 7000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | RECOILER OBBS ASSY. |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | HOLD DOWN ROLL ASSY. |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | PEELER TABLE ASSY |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | EXIT THREADING TABLE ASSY. |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | PASSING TABLE # 1 |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | PASSING TABLE # 2 |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | PASSING TABLE # 3 |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | PASSING TABLE # 4 |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | PASSING TABLE # 5 |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | PASSING TABLE # 6 |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | PASSING TABLE # 7 |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | ENTRY SHEAR |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | EXIT SHEAR |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | EXIT PINCH CUM DEFLECTOR ROLL ASSY. |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | PINCH CUM LEVELLER ROLL ASSY. |  |  | 3500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | ENTRY SIDE GUIDE ASSY. |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | EXIT SIDE GUIDE ASSY. |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | BURR MASHER ROLL ASSY |  |  | 1200000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | TENSIONER ROLL ASSY |  |  | 1200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | AIR WIPER ASSY |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | SUPPORT ROLL ASSY |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | FOUNDATION BOLTS |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | TAPER (LEVELLING) PLATE |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | ACID RECIRCULATION SYSTEM, FUME EXHAUST & SCRUBBER SYSTEM LOT 2 |  |  | 2200000 | Not Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | HYDRAULIC SYSTEM(VALVE STANDS) |  |  | 3000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | HYDRAULIC SYSTEM(POWERPACKS) |  |  | 3000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | HYDRAULIC PIPE ,VALVES & FITTINGS |  |  | 1700000 | Not Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2426-VIKAS-PICKLING |  | SACHIN | PNEUMATIC PIPE ,VALVES & FITTINGS |  |  | 1000000 | Not Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Dec 2025
2421-APL-CGL |  | SAURABH | Exhaust Ducting-Lot 2 |  |  | 400000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2421-APL-CGL |  | SAURABH | TENSIOMETER ASSEMBLY |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2421-APL-CGL |  | SAURABH | QUENCHING TANK ROLLS |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2518-APL-SPM |  | MAYANK | ELECTRICAL |  |  | 40000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | SPM | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | EXIT THREADING TABLE ASSY. |  |  | 600000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Ready in oct |  |  |  | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | DEGREASING TANK ASSY |  |  | 2100000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | BRUSHING TANK ASSY. |  |  | 2100000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | GA OF HOT RINSING TANK ASSY. |  |  | 2100000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | PRIME QUENCHING TANK ASSY. |  |  | 2100000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Navjeevan Ready by 27 dec |  |  |  | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | FINISH QUENCHING TANK ASSY. |  |  | 2100000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Navjeevan Ready by 27 dec |  |  |  | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | FINISH COATER 'A' ASSY. |  |  | 4500000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | FINISH COATER 'B' ASSY. |  |  | 4510000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | Incinerator Burner Gas train |  |  | 350000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | Incinerator Dec lot |  |  | 1500000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | Refractory |  |  | 2000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | 4500009960, Ready |  |  |  | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | Ducting |  |  | 2815000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | 4500009140 |  |  |  | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | Bellow |  |  | 1060000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | 4500010491, Ready 14 Dec |  |  |  | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | Interconecting Piping & Fittings |  |  | 432000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | Oven Structure- Beams 20 ton |  |  | 2000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Ready by 12 nov |  |  |  | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | Oven Structure-Staircases |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | Oven Structure-Chequered plates |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Under painting |  |  |  | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | Oven Structure- Beams 14 ton |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | dispatch on 10 dec from amane |  |  |  | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | UTILITY-ETP |  |  | 900000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | 4500009051 ready payment |  |  |  | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | UTILITY-RO |  |  | 600000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | 4500009050 ready payment |  |  |  | CCL | Dec 2025
2420-INDIA STEEL-CCL |  | SAURABH | UTILITY-PUMP |  |  | 600000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CCL | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | PIT COVER-POR,ETR,DTR |  |  | 100000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | UNDER FABRICATION |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | POR-OBBS ASSY |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | ETR-SNUBBER ROLL ASSY. |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | COOLANT TRAY |  |  | 100000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | BACKUP PULLING TROLLEY |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | ENTRY TILTING TABLE |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | EXIT TILTING TABLE |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | DELIVERY SHEAR ASSY |  |  | 100000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | BACKUP ROLLS (2 NOS.) |  |  | 9000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | IN TRANSIT FROM NHAVA SHEVA TO YDG |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | BACK UP CLAMP ASSY. |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | IMR SHIFTING ASSY. & SPINDLE SUPPORT |  |  | 100000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | HYD. CYL. PENDING |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | WORK ROLL CLAMP ASSY. |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | MILL HOUSING WITH LINER |  |  | 8250000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | MILL HOUSING WITH LINER |  |  | 8250000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | BED PLATE ASSY. |  |  | 2000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | SHUTTER ASSY |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | TOP SEPARATOR ASSY. |  |  | 0 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | TAPER WEDGE ASSY. |  |  | 500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | MAEWEST BLOCK ASSY. |  |  | 2400000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | WORK ROLL & IMR INSIDE TRACK |  |  | 100000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | BACKUP INSIDE TRACK |  |  | 100000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | BACKUP OUTSIDE TRACK |  |  | 100000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | ENTRY AIR WIPER ASSY |  |  | 0 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | BACKUP WIPER ASSY |  |  | 380000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | EXIT AIR WIPER ASSY |  |  | 0 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | COBBLE GUARD ASSY |  |  | 1750000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | ENTRY SIDE GUIDE CUM PRESSURE PAD ASSY |  |  | 1598000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | ENTRY AIR KNIFE ASSY |  |  | 0 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | EXIT AIR KNIFE ASSY |  |  | 0 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | ENTRY PASSING TABLE @ MILL STAND |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | EXIT PASSING TABLE @ MILL STAND |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | THICKNESS GAUGE (2 NOS.) |  |  | 6000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | ENTRY DEFLECTOR CUM TURN DOWN |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | ENTRY C FRAME |  |  | 100000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | DELIVERY DEFLECTOR CUM TURN DOWN |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | EXIT C FRAME |  |  | 100000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | PASSING TABLE #2 (BET. ENTRY DEF. ROLL & ENTRY THK. GAUGE) |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | PASSING TABLE #3 (BET. EXIT THK. GAUGE & EXIT DEF. ROLL ) |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | PASSING TABLE #4 (BET. ENTRY THK. GAUGE & PRESS. BOARD) |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | PASSING TABLE #5 (BET. EXIT SHEAR & EXIT THK. GAUGE) |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | PASSING TABLE #6 (BET. EXIT PASSING TABLE & EXIT SHEAR) |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | PASSING TABLE #7 (BET. EXIT SHEAR & PASSING TABLE#5) |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2427-PROMPT-6HI CRM |  | MAYANK | HT MOTORS |  |  | 32800000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | LC REQUIRED |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | COIL CAR @ PAY OFF REEL |  |  | 1250000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | POR-COIL SADDLE |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | FABRICATION COMPLETE |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | ETR-COIL CAR |  |  | 1250000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | ETR-COIL SADDLE |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | FABRICATION COMPLETE |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | DTR-COIL CAR |  |  | 1250000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM | UNIT-3 | MAYANK | DTR-COIL SADDLE |  |  | 200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | FABRICATION COMPLETE |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM | UNIT-1 | MAYANK | ETR ASSEMBLY |  |  | 22500000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | COOLANT TRAY |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | GEAR LUBRICATION SYSTEM ASSY |  |  | 1320000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY AT SPAN |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | MILL DRIVE |  |  | 7200000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | GEARED SPINDLE COUPLING (2 NOS.) |  |  | 7452000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | STORED IN WAREHOUSE AT MUMBAI PORT |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | FUME EXHAUST SYSTEM WITH BLOWER ASSY |  |  | 7350000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY AT VAPCON |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | ROLL COOLANT TANK |  |  | 2650000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY AT SPAN |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | COOLANT FILTERATION SYSTEM |  |  | 10000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY AT SPAN |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | HYDRAULIC SUSTEM - VALVE STANDS |  |  | 9000000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY AT BOSCH REXROTH |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | HYDRAULIC SYSTEM - POWER PACKS |  |  | 5500000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY AT BOSCH REXROTH |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | THICKNESS GAUGE (2 NOS.) |  |  | 14846000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY AT IMS MACO |  |  |  | CRM | Dec 2025
2521-BMWIL-6HI CRM |  | MAYANK | FOUNDATION BOLTS + TAPER PLATES SET |  |  | 1000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2522-APL-SPM |  | ADITYA SAINI | ELECTRICAL |  |  | 5000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | SPM | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Entry Accumulator Fix frame |  |  | 3000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Entry Accumulator Top frame |  |  | 6325000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Entry Accumulator Dead weight |  |  | 1400000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | BOI | SAURABH | Entry Accumulator Duplex chain |  |  | 1600000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Exit Accumulator Fix frame |  |  | 4950000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Exit Accumulator Moving frame |  |  | 4975000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Exit Accumulator Fastners |  |  | 50000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Exit Accumulator Dead weight |  |  | 1400000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | BOI | SAURABH | Exit Accumulator Duplex chain |  |  | 1600000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | SINGLE STEERING ROLL ASSY.-2 ASSY. |  |  | 2000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #2 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #3 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #4 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #6 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #7 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #8 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #9 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #10 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #11 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #12 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #13 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #15 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | DEFLECTOR ROLL FRAME ASSY #16 |  |  | 300000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | BOI | SAURABH | DOUBLE DECKER ENTRY SHEAR ASSY. |  |  | 1340000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | BOI | SAURABH | DELIVERY SHEAR ASSY. |  |  | 750000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | BOI | SAURABH | FOUNDATION BOLT - 1 |  |  | 1213000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | BOI | SAURABH | WELDING ELECTRODE CONSUMABLE |  |  | 50000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2527-AECPL-GI/GL LINE | BOI | SAURABH | TAPER PLATE |  |  | 400000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CGL | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | COIL CAR @ POR, ETR & DTR |  | 99000 | 8860500 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | IMR SHIFTING ALONG WITH SPINDLE SUPPORT |  | 40000 | 3580000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | MILL HOUSING WITH WORK ROLL CLAMP, BACKUP CLAMP & LINERS |  | 220000 | 19690000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | BED PLATE ASSY. |  | 50000 | 4475000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | TOP SEPARATOR ASSY. |  | 5000 | 447500 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | TAPER WEDGE ASSY |  | 35000 | 3132500 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | MAEWEST BLOCK ASSY. |  | 120000 | 10740000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | WORK ROLL INSIDE TRACK |  | 2000 | 179000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | BACKUP INSIDE TRACK |  | 2000 | 179000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | ENTRY MILL TABLE WITH DEFLECTOR CUM TURN DOWN ROLL ASSEMBLY |  | 50000 | 4475000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | EXIT MILL TABLE WITH DEFLECTOR CUM TURN DOWN ROLL ASSEMBLY |  | 50000 | 4475000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | ENTRY C FRAME |  | 2053.2426 | 183765.2139 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | EXIT C FRAME |  | 2053.2426 | 183765.2139 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | ETR ASSEMBLY WITH PUSHER PLATE |  | 160000 | 14320000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | PINION GEARBOX ASSEMBLY |  | 75000 | 6712500 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | ROLL COOLANT HEADER ASSY |  | 20000 | 1790000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | ENTRY & EXIT AIR WIPER ASSY |  | 10000 | 895000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | BACKUP ROLL WIPER ASSY |  | 10000 | 895000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | COBBLE GUARD ASSY |  | 30000 | 2685000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | PRESSURE PAD WITH SIDE GUIDE |  | 50000 | 4475000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | ENTRY & EXIT AIR KNIFE ASSY |  | 10000 | 895000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | ENTRY PASSING TABLE @ MILL STAND |  | 5000 | 447500 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | UNIT-1 | MAYANK | EXIT PASSING TABLE @ MILL STAND |  | 3000 | 268500 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | BOI | MAYANK | DELIVERY SHEAR ASSY |  | 6875 | 615312.5 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | CRM | Dec 2025
2501-AL SHAKER-6HI CRM | BOI | MAYANK | GEARED SPINDLE (1 WORKING SET+1 SPARE) |  | 120000 | 10560000 | Disp. | 2025-12-28 |  | FALSE | FALSE |  | READY AT NHAVA SHEVA PORT |  |  |  | CRM | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | Furnace Structure - DEC LOT |  |  | 7240000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | Non Ox Burners |  |  | 6767500 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | Post Combustion Burner |  |  | 6817500 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | Ignition Transformers |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | Ignition Cable |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | Ratio Regulator |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | UV Sensors |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | UV Flame Switches |  |  |  | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | Electric Wall Heater |  |  | 19910000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | ENTRY COIL SADDLE ASSY.#2A (V SHAPED- PAD) |  |  | 1007000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | SIDE GUIDE ASSY.#2 |  |  | 1508333 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | ENTRY SHEAR ASSY. WITH KICK OUT ROLL#2 |  |  | 3620000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | ENTRY SCRAP CAR ASSY.#2 |  |  | 905000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | ENTRY SCRAP DOWN TABLE ASSY.#2 |  |  | 135300 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | SIDE GUIDE ASSY.#3 |  |  | 1508333 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | SIDE GUIDE ASSY.#4 |  |  | 1508334 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | SCRAP DOWN TABLE ASSY. (BEFORE FURNACE) |  |  | 581000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | SCRAP CAR ASSY.#3 (BEFORE FURNACE) |  |  | 905000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | SHEAR ASSY. (BEFORE FURNACE) |  |  | 1810000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | SHEAR ASSY. (AFTER FURNACE) |  |  | 1810000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | SCRAP CAR ASSY.#4 (AFTER FURNACE) |  |  | 905000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | SCRAP DOWN TABLE ASSY. (AFTER FURNACE) |  |  | 581000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#02 (BEFORE SHOT BLASTING) |  |  | 2000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#03 (BEFORE SHOT BLASTING) |  |  | 2000000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | DEFLECTOR ROLL ASSY.#04 (BEFORE PICKLING) |  |  | 2335000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#6 (AFTER SHOT BLASTING) |  |  | 4525000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | EXIT SHEAR ASSY. |  |  | 1810000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | EXIT SCRAP CAR ASSY. |  |  | 905000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | EXIT SCRAP DOWN TABLE ASSY |  |  | 135300 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | EXIT COIL SADDLE ASSY.#1A (V SHAPED- PAD) |  |  | 1007000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | EXIT COIL SADDLE ASSY. #1B (COIL WEIGHING SYSTEM) |  |  | 1553000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | FOUNDATION BOLT |  |  | 905000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | TAPER PLATE |  |  | 430400 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | ELECTRICAL (DEC LOT) |  |  | 31675000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2506-JSW-APL |  | ADITYA SHARMA | HEAT EXCHANGER |  |  | 3620000 | Disp. | 2025-12-28 |  | FALSE | FALSE | [5 empty] | APL | Dec 2025
2424-MMI-6HI CRM |  | MAYANK | Interconnecting Pipings |  | 5000 | 0 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Nov 2025
2424-MMI-6HI CRM |  | MAYANK | Distribution headers |  | 5000 | 0 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Nov 2025
2424-MMI-6HI CRM |  | MAYANK | Electricals(Balance) |  | 5000 | 430000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Nov 2025
2424-MMI-6HI CRM |  | MAYANK | SEAL KIT FOR HYDRAULIC CYLINDER - 1 SET (SPARE) |  | 0 | 0 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Nov 2025
2425-MMI-6HI CRM |  | MAYANK | Fume exhaust ducts |  | 0 | 0 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | TO BE FABRICATED AT SITE, AS PER DISCUSSION WITH MR. ANIL SHARMA |  |  |  | CRM | Nov 2025
2425-MMI-6HI CRM |  | MAYANK | Tension reel assembly (SPARE) |  | 130000 | 11180000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Nov 2025
2403-GOPANI-4HI CRM |  | MAYANK | Top Platform |  |  | 200000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Nov 2025
2403-GOPANI-4HI CRM |  | MAYANK | Hood Assembly |  |  | 600000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Nov 2025
2403-GOPANI-4HI CRM |  | MAYANK | SPARE CHOCKS (1 SET-BUP) |  |  | 2000000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Nov 2025
2403-GOPANI-4HI CRM |  | MAYANK | Cellar Ventilation System |  |  | 500000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Nov 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | AC MOTOR -1 Motor |  |  | 13285000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CRM | Nov 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | WORK ROLL - 2nos |  |  | 1220000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CRM | Nov 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | IMR ROLL - 2nos |  |  | 1730000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CRM | Nov 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | SPARE-WORK ROLL CHOCKS-2 set |  |  | 3200000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | 1 Set Dispatched |  |  |  | CRM | Nov 2025
2231-SHYAM-6HI CRM |  | SAURABH | Shear blades ( SPARE ) |  |  |  | Disp. | 2025-11-28 |  | FALSE | FALSE |  | 4500010191 |  |  |  | CRM | Nov 2025
2405-JSPL-TRIMMING |  | SAURABH | BELT WRAPPER |  |  | 1100000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | Ready |  |  |  | TRIMMING | Nov 2025
2405-JSPL-TRIMMING |  | SAURABH | HYDRAULIC POWER PACK & VALVE STAND |  |  | 4000000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | Dispatched on 15 Nov |  |  |  | TRIMMING | Nov 2025
2405-JSPL-TRIMMING |  | SAURABH | UNCOILER & RECOILER OBBS |  |  | 1000000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Nov 2025
2305-APL-CGL |  | SAURABH | GAS LEACKAGE DETECTOR 2 NOS |  |  | 200000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | 4500008091, |  |  |  | CGL | Nov 2025
2305-APL-CGL |  | SAURABH | SPM Blower |  |  | 100000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | In house |  |  |  | CGL | Nov 2025
2305-APL-CGL |  | SAURABH | SPM Blower piping |  |  | 200000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | 4500010538, |  |  |  | CGL | Nov 2025
2305-APL-CGL |  | SAURABH | TENSIOMETER |  |  | 100000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | 1 Roll pending, receive by 29 oct |  |  |  | CGL | Nov 2025
2305-APL-CGL |  | SAURABH | Air Knife blower fitting |  |  | 50000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | 4500010538 |  |  |  | CGL | Nov 2025
2305-APL-CGL |  | SAURABH | Maco Rotary union |  |  | 50000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | In transit |  |  |  | CGL | Nov 2025
2503-AFRICAN STEEL-SPARE |  |  | SPARE |  |  | 2340250 | Not Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | SPARE | Nov 2025
2421-APL-CGL |  | SAURABH | RECOILER ASSY WITH PUSHPERPLATE ASSY |  |  | 5700000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2025
2421-APL-CGL |  | SAURABH | STEERING CUM TURN UP ROLL ASSY. |  |  | 1100000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2025
2421-APL-CGL |  | SAURABH | DOUBLE STEERING ROLL ASSY BEFORE HOZ. ACC ASSY. |  |  | 800000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2025
2421-APL-CGL |  | SAURABH | SEAM WELDER ASSY. |  |  | 10000000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2025
2421-APL-CGL |  | SAURABH | Exhaust Ducting-Lot 1 |  |  | 1300000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2025
2421-APL-CGL |  | SAURABH | Blower Fan-Lot 1 |  |  | 1800000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2025
2523-JSW BAWAL |  | SACHIN TB | COATER REVAMP |  |  | 3800000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | SPARE | Nov 2025
2420-INDIA STEEL-CCL |  | SAURABH | UNCOILER 1 ASSY |  |  | 3950000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | Ready in NOV, Fullkit |  |  |  | CCL | Nov 2025
2420-INDIA STEEL-CCL |  | SAURABH | UNCOILER 2 ASSY |  |  | 4050000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CCL | Nov 2025
2420-INDIA STEEL-CCL |  | SAURABH | RECOILER WITH PUSHER PLATE |  |  | 4500000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | Ready in nov |  |  |  | CCL | Nov 2025
2420-INDIA STEEL-CCL |  | SAURABH | RECOILER BELT WRAPPER ASSY. |  |  | 1000000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CCL | Nov 2025
2420-INDIA STEEL-CCL |  | SAURABH | BRIDLE ROLL ASSY.#1 |  |  | 3200000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CCL | Nov 2025
2420-INDIA STEEL-CCL |  | SAURABH | BRIDLE ROLL ASSY.#5 |  |  | 2005025 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | 2 Frame spectec by 13, machining anil engg complate by 13 |  |  |  | CCL | Nov 2025
2420-INDIA STEEL-CCL |  | SAURABH | SINGLE STEERING ROLL ASSY.#5 (BEFORE FINISH COATER) |  |  | 500000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CCL | Nov 2025
2420-INDIA STEEL-CCL |  | SAURABH | PRIME SQUEEZE ROLL CUM STEERING ASSY.#4 |  |  | 1500000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CCL | Nov 2025
2420-INDIA STEEL-CCL |  | SAURABH | FINISH SQUEEZE ROLL CUM STEERING ASSY.#6 |  |  | 1500000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CCL | Nov 2025
2420-INDIA STEEL-CCL |  | SAURABH | CHEMICAL COATER ASSY. |  |  | 4700000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CCL | Nov 2025
2420-INDIA STEEL-CCL |  | SAURABH | PRIME COATER ASSY. |  |  | 4800000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CCL | Nov 2025
2427-PROMPT-6HI CRM |  | MAYANK | ENTRY SHEAR |  |  | 500000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | PAINT PENDING |  |  |  | CRM | Nov 2025
2427-PROMPT-6HI CRM |  | MAYANK | GEAR LUBRICATION SYSTEM ASSY |  |  | 1200000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | READY FOR DISPATCH, PAYMENT REQUIRED |  |  |  | CRM | Nov 2025
2427-PROMPT-6HI CRM |  | MAYANK | WORK ROLLS (2 NOS.) |  |  | 1224000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Nov 2025
2427-PROMPT-6HI CRM |  | MAYANK | IMR ROLLS (2 NOS.) |  |  | 1738000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Nov 2025
2427-PROMPT-6HI CRM |  | MAYANK | INTERCONNECTING PIPING |  |  | 1275000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Nov 2025
2427-PROMPT-6HI CRM |  | MAYANK | DISTRIBUTION HEADERS |  |  | 445000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Nov 2025
2427-PROMPT-6HI CRM |  | MAYANK | CELLER VENTILATION SYSTEM WITH BLOWER ASSY |  |  | 800000 | Disp. | 2025-11-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Nov 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Entry Accumulator Moving frame |  |  | 3000000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Entry Accumulator Structure |  |  | 2000000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2025
2527-AECPL-GI/GL LINE | UNIT-2 | SAURABH | Exit Accumulator Structure |  |  | 2000000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | CGL | Nov 2025
2506-JSW-APL |  | ADITYA SHARMA | Furnace Structure - NOV LOT |  |  | 4015000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2025
2506-JSW-APL |  | ADITYA SHARMA | ENTRY COIL SADDLE ASSY.#2B (CRADLE ROLL) |  |  | 457000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2025
2506-JSW-APL |  | ADITYA SHARMA | ENTRY COIL CAR ASSY.#2 |  |  | 1357500 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2025
2506-JSW-APL |  | ADITYA SHARMA | ENTRY OBBS ASSY.#2 |  |  | 676500 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2025
2506-JSW-APL |  | ADITYA SHARMA | ENTRY PINCH ROLL ASSY.#4 |  |  | 417000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2025
2506-JSW-APL |  | ADITYA SHARMA | BURR MASHER |  |  | 696500 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2025
2506-JSW-APL |  | ADITYA SHARMA | EXIT PINCH ROLL ASSY.#1 |  |  | 696500 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2025
2506-JSW-APL |  | ADITYA SHARMA | EXIT COIL CAR ASSY. #1 |  |  | 1357500 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2025
2506-JSW-APL |  | ADITYA SHARMA | EXIT OBBS ASSY.#1 |  |  | 676500 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2025
2506-JSW-APL |  | ADITYA SHARMA | ELECTRICAL (NOV LOT) |  |  | 29865000 | Disp. | 2025-11-28 |  | FALSE | FALSE | [5 empty] | APL | Nov 2025
2207-JTL-6HI CRM |  | ADITYA SHARMA | Fume exhaust duct |  |  | 850000 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | CRM | Oct 2025
2207-JTL-6HI CRM |  | ADITYA SHARMA | Cellar Ventilation duct |  |  | 500000 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | CRM | Oct 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | WR CHOCKS -4 NOS |  |  | 1200000 | Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | SPM | Oct 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | AC MOTOR -2 Motor |  |  | 16670000 | Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | CRM | Oct 2025
2231-SHYAM-6HI CRM |  | SAURABH | Mill Hood |  |  | 0 | Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | CRM | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | COIL CAR ASSY.@ UNCOILER |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | DRAG CHAIN ASSY.@ UNCOILER |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | SADDLE ASSY.#1 @ UNCOILER |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | SADDLE ASSY.#2 @ UNCOILER |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | PIT COVER @ UNCOILER |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | COIL CAR ASSY. @ RECOILER |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | DRAG CHAIN ASSY. @ RECOILER |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | SADDLE ASSY.#1 (LOAD CELL) @ RECOILER |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | SADDLE ASSY.#2 @ RECOILER |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | SADDLE ASSY.#3 @ RECOILER |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | PIT COVER @ RECOILER |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | UNCOILER ASSY. |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | RECOILER ASSY. |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | TABLE |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | PINCH CUM DEFLECTOR ROLL ASSY |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | DEBURRING ROLL ASSY. |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | EPC |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | CPC |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | SHEAR ASSY. |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | SIDE GUIDE ASSY. |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | TENSIONER ASSY. |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | TRIMMER HEAD ASSY. |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | SCRAP BAILER ASSY. |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | PRESSURE PAD ASSY. |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | ELECTRICAL CONTROL ROOM |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | FOUNDATION BOLTS |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | TAPER PLATES |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | HYDRAULIC POWER PACK & VALVE STAND |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2406-JSPL-TRIMMING |  | SAURABH | HYDRAULIC & PNEUMATIC FITTING |  |  | 0 | Not Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | EPC |  |  | 750000 | Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | CPC |  |  | 750000 | Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Oct 2025
2305-APL-CGL |  | SAURABH | GLOW HEATER |  |  |  | Disp. | 2025-10-28 |  | FALSE | FALSE |  | Watt heater 94400 |  |  |  | CGL | Oct 2025
2305-APL-CGL |  | SAURABH | VALVE |  |  | 100000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | DELVAL 4874 |  |  |  | CGL | Oct 2025
2305-APL-CGL |  | SAURABH | VALVE |  |  | 100000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | READY AIRA AUTOMATION ( 2128162 PDC REQ ) 5011 |  |  |  | CGL | Oct 2025
2421-APL-CGL |  | SAURABH | POT EQUIPMENT SINK ROLL AND DEFLECTOR ASSY |  |  | 4800000 | Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | CGL | Oct 2025
2420-INDIA STEEL-CCL |  | SAURABH | UNCOILER DRAG CHAIN ASSY. |  |  | 1000000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | Ready for dispatch |  |  |  | CCL | Oct 2025
2420-INDIA STEEL-CCL |  | SAURABH | RECOILER DRAG CHAIN ASSY. |  |  | 500000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | Ready for dispatch |  |  |  | CCL | Oct 2025
2420-INDIA STEEL-CCL |  | SAURABH | UNCOILER OBBS ASSY 2 NOS |  |  | 500000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | Ready in oct |  |  |  | CCL | Oct 2025
2420-INDIA STEEL-CCL |  | SAURABH | DOUBLE DECKER SHEAR ASSY. |  |  | 2202325 | Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2025
2420-INDIA STEEL-CCL |  | SAURABH | EXIT SHEAR ASSY. |  |  | 1707250 | Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2025
2420-INDIA STEEL-CCL |  | SAURABH | ELECTRICAL Oct Lot |  |  | 4500000 | Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | CCL | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | COIL CAR @ PAY OFF REEL |  |  | 1250000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | ETR-COIL CAR |  |  | 1250000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | DTR-COIL CAR |  |  | 1250000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | POR-MANDREL ASSY |  |  | 3550000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | POR-GEARBOX ASSY |  |  | 6900000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | POR-SNUBBER ROLL ASSY |  |  | 550000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | ETR ELECTROMAGNETIC BRAKE WITH BASE FRAME |  |  |  | Disp. | 2025-10-28 |  | FALSE | FALSE |  | DISPATCHED FROM REXROTH |  |  |  | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | DTR ELECTROMAGNETIC BRAKE WITH BASE FRAME |  |  |  | Disp. | 2025-10-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | BACKUP STOOL |  |  | 1600000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | SCRAP DOWN TABLE |  |  | 500000 | Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | HYDRAULIC SYSTEM - VALVE STANDS |  |  | 9000000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | DISPATCHED FROM REXROTH, YD INVOICE PENDING |  |  |  | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | HYDRAULIC SYSTEM - POWER PACKS |  |  | 5500000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | DISPATCHED FROM REXROTH, YD INVOICE PENDING |  |  |  | CRM | Oct 2025
2427-PROMPT-6HI CRM |  | MAYANK | HYDRAULIC PIPES & FITTINGS |  |  | 6336000 | Disp. | 2025-10-28 |  | FALSE | FALSE |  | Partially dispatched |  |  |  | CRM | Oct 2025
2506-JSW-APL |  | ADITYA SHARMA | Furnace Structure - OCT LOT |  |  | 7110000 | Disp. | 2025-10-28 |  | FALSE | FALSE | [5 empty] | APL | Oct 2025
2425-MMI-6HI CRM |  | MAYANK | Back up roll chocks - 4 nos |  | 111000 | 9546000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | WR chocks - 4nos |  | 24000 | 2064000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Pay off reel assembly only (SPARE) |  | 120000 | 10320000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Bed Plate |  | 40000 | 3440000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Mill Housing with Liners |  | 378750 | 32572500 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Maewest Blocks |  | 120000 | 10320000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Taper wedge assembly |  | 25000 | 2150000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | IMR shifting assembly |  | 30000 | 2580000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Roll cooling headers with (spare 30 nozzles) + (coolant hose pipe - 12nos) |  | 15000 | 1290000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Air wiping headers |  | 12000 | 1032000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Cobble Guard Assembly |  | 27000 | 2322000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Pressure board assembly |  | 14000 | 1204000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Side guide assembly |  | 20000 | 1720000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Back up wiper assembly |  | 4000 | 344000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Interconnecting Pipings |  | 12000 | 1032000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Distribution headers |  | 11000 | 946000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Shearing Machine Mill exit side |  | 10000 | 860000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Entry table assembly along with thickness gauge C Frame |  | 40000 | 3440000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Exit table assembly along with thickness gauge C frame |  | 40000 | 3440000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Deflector roll with turn down roll assembly assembly with spare hydl. Motor |  | 40000 | 3440000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Balance Electrical (Loose suply) |  | 100000 | 8600000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Roll force cylinder |  | 55000 | 4730000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Sep 2025
2425-MMI-6HI CRM |  | MAYANK | Thickness gauge |  | 160000 | 13760000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | DISPATCH BY 19-09-2025 FROM IMS MACO, KOLKATA |  |  |  | CRM | Sep 2025
2207-JTL-6HI CRM |  | ADITYA SHARMA | Hydraulic System |  |  | 3500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2403-GOPANI-4HI CRM |  | MAYANK | Hydraulic & pneumatic pipe & fitting-Part 2 |  |  | 1000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2403-GOPANI-4HI CRM |  | MAYANK | SPARE CHOCKS (1 SETS - WR) |  |  | 1000000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CRM | Sep 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | BACKUP CHOCKS -4 NOS |  |  | 1500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | SPM | Sep 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | BACKUP CHOCK BEARINGS 4 NOS |  |  | 1500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | SPM | Sep 2025
2407-APL-PICKLING |  | SACHIN | HORIZONTAL ACCUMULATOR ASSY |  |  | 400000 | Not Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2025
2407-APL-PICKLING |  | SACHIN | EPC SENSOR -BOI |  |  | 300000 | Not Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2025
2407-APL-PICKLING |  | SACHIN | CPC ASSY.#1 SENSOR -BOI |  |  | 250000 | Not Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2025
2407-APL-PICKLING |  | SACHIN | CPC ASSY.#2 SENSOR -BOI |  |  | 250000 | Not Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2025
2407-APL-PICKLING |  | SACHIN | TEMP. CONTROL VALVE |  |  | 400000 | Not Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | AC MOTOR -1 Motor |  |  | 2755000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Ready by 30th Sept |  |  |  | CRM | Sep 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | MILL HOUSING |  |  | 20000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | BED PLATE ASSY. |  |  | 2000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ROLL FORCE CLY ASSY |  |  | 4140000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ENTRY SIDE GUIDE CUM PRESSURE PAD ASSY |  |  | 2380000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | HYDRAULIC POWER PACK & VALVE TABLE ASSY |  |  | 13600000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | Electricals-Misc. |  |  | 5000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2231-SHYAM-6HI CRM |  | SAURABH | Roll force cylinder ( SPARE ) |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2231-SHYAM-6HI CRM |  | SAURABH | Moog Valve AGC ELECTRICAL ( SPARE ) |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2405-JSPL-TRIMMING |  | SAURABH | HYDRAULIC & PNEUMATIC FITTING LOT 1 |  |  | 500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Sep 2025
2305-APL-CGL |  | SAURABH | Solenoid shut-off valves |  |  | 100000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | PYRON PO-354023 |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | Exhaust Ducting assembly |  |  | 250000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | VARENYAN PO-722656 |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | Flow Switch |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | IFM PO-338247 |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | Orifice Flow meter |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | ESA MANUFACTURING |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | Pressure Gauges |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | TEMPSENS PO-72500 |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | Pressure Transmitter.& Differential pressure transmitter |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | VIZEN PO- 784346 |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | Temperature Transmitter |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | VIZEN PO-630474 |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | PYROMETER |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | TEMPSENS PO- 354000 |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | Thermpcouple and cables |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | TEMPSENS PO-422664 |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | LOW PRESSURE SWITCH |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Niyara automation 79910 |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | LRB MATRESS & CLADDING SHEET |  |  | 308944 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Ready at RK trader |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | H2/O2 & Dew point ANALYSER |  |  | 100000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Ready at Halcyon |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | FURNACE-INTER CONNECTING PIPINGS |  |  | 100000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | HARYANA 9206, BHART 9325, SHIBDASS 9304 , SS PIPE ????? |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | VALVE |  |  | 100000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | PYRON ENGG 2476 |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | Furnace water and N2 Station - 14 |  |  | 300000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | CPC & EPC ASSY. |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY, In transit reach by August end, dispatch in sept,payment 2421 adjust |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | Module Air piping 1, 2 Pilot burner 1,2,3,Gas valve train - 13 |  |  | 100000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | HUSKEY PUMP & AGITATOR |  |  | 200000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Ready payment required FEC 342318 |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | Quenching tank rolls |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | POT--Pot equipment ROLLS |  |  | 5300000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | FOR HSS ONLY, REACH IN OCT |  |  |  | CGL | Sep 2025
2305-APL-CGL |  | SAURABH | POT--Air knife blower |  |  | 5800000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | IN TRANSIT, HSS DONE, ON PORT BY 31 OCT |  |  |  | CGL | Sep 2025
2426-VIKAS-PICKLING |  | SACHIN | PRE-WASH TANK , PICKLING TANK -1,2 |  |  | 2800000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | ready at vendor end |  |  |  | PICKLING | Sep 2025
2426-VIKAS-PICKLING |  | SACHIN | GRANITE BLOCKS & RUBBER LINING |  |  | 5660000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | ready at vendor end |  |  |  | PICKLING | Sep 2025
2426-VIKAS-PICKLING |  | SACHIN | PICKLING TANK -3 - |  |  | 1400000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | ready at vendor end |  |  |  | PICKLING | Sep 2025
2426-VIKAS-PICKLING |  | SACHIN | PICKLING TANK - 5-STAGE RINSING TANK |  |  | 2800000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | ready at vendor end |  |  |  | PICKLING | Sep 2025
2426-VIKAS-PICKLING |  | SACHIN | ACID RECIRCULATION SYSTEM, FUME EXHAUST & SCRUBBER SYSTEM LOT 1 |  |  | 10800000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | ready at vendor end |  |  |  | PICKLING | Sep 2025
2507-JSW-BAWAL-SPARE |  | ADITYA SAINI | SPARE |  |  | 9200000 | Not Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | SPARE | Sep 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#6 (B/W ENTRY TUNNEL & BRIDLE ROLL ASSY#4) |  |  | 150000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#7 |  |  | 200000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY OF DISPATCH |  |  |  | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#4 |  |  | 2100000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR TOP FRAME |  |  | 5000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | LIFTING FORK, SLING PULLEY BLOCK, RAIL SECTION |  |  | 2500000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY OF DISPATCH |  |  |  | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | SUPPORT ROLL ASSY. LOT-2 |  |  | 500000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY OF DISPATCH |  |  |  | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | DOUBLE STEERING ROLL ASSY.#1 @ ENTRY ACC ASSY. |  |  | 800000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | DOUBLE STEERING ROLL ASSY.#2 @ CAG |  |  | 800000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | DEGREASING TANK ASSY #1 |  |  | 1200000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Vehicle to be placed at Navjeevan on 28th Sept |  |  |  | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | BRUSHING TANK ASSY #1 |  |  | 1100000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Vehicle to be placed at Navjeevan on 28th Sept |  |  |  | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | HOT WATER RINSING TANK |  |  | 1200000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Vehicle to be placed at Navjeevan on 28th Sept |  |  |  | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | QUENCHING TANK ASSY. |  |  | 2100000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Vehicle to be placed at Navjeevan on 28th Sept |  |  |  | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | WATER SPRAY UNIT |  |  | 1600000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Vehicle to be placed at Navjeevan on 28th Sept |  |  |  | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | HOT AIR DRYER ASSY.@ CLEANING SECTION |  |  | 1000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | HOT AIR DRYER @ TOC |  |  | 1000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | CHEMICAL COATER ASSY. 1 & 2 |  |  | 6500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | EPC ASSY. |  |  | 700000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | CPC |  |  | 5500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | ELECTRICAL PACKAGE |  |  | 23100000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | HYDRAULIC POWER PACK & VALVE STAND |  |  | 7300000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | HYDRAULIC & PNEUMATIC FITTING-Lot 1 |  |  | 1000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Threading Needle Assembly |  |  | 700000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Furnace Gas and Combustion Air Piping |  |  | 1900000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Furnace interconnecting Piping |  |  | 2600000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Pipes & Fittings for Water station and N2 Station |  |  | 500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | JCF Ducting |  |  | 700000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Throat Assembly |  |  | 3500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Throat Refractory |  |  | 0 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Hearth Roll Drive Assembly |  |  | 0 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Floating Support Assembly |  |  | 0 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | RTF |  |  | 5500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Hearth Roll Drive Assembly |  |  | 0 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | RTF Refractory |  |  | 0 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | SF |  |  | 2000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Hearth Roll Drive Assembly |  |  | 0 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | SF Refractory |  |  | 0 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Floating Support Assembly |  |  | 300000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | HBR Assembly |  |  | 8300000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | HBR Hearth Roll Drive Assy |  |  | 100000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | HBR Refractory Assy |  |  | 1900000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Maintenance Door Assy |  |  | 100000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Maintenance Door Assy |  |  | 100000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | CERAMIC ZINC POT |  |  | 19500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | AIR KNIFE |  |  | 6000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | EDGE BAFFLE |  |  | 2600000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | ZINC PUMP |  |  | 700000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | DROSSER |  |  | 1200000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | AIR KNIFE BLOWER |  |  | 6000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | AIR KNIFE BLOWER MOTOR |  |  | 700000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Pot cellar Ventilation Supply Ducting |  |  | 400000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Pot cellar Ventilation Exhaust Ducting |  |  | 400000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Moving Pendant ducting |  |  | 200000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Up Pass cooling pendant ducting |  |  | 300000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Down Pass cooling pendant ducting |  |  | 250000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Pressure transmitter & Temperature Transmitters |  |  | 1179000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Glow Heater |  |  | 80000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Low Pressure Switch |  |  | 70000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Pressure Gauges |  |  | 65000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Rotameters |  |  | 18200 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Blower Fan-Lot 1 |  |  | 2000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2421-APL-CGL |  | SAURABH | Furnace Bellows |  |  | 985000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CGL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | PEELER TABLE ASSY.#1 |  |  | 450000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Full kit |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | PEELER TABLE ASSY.#2 |  |  | 450000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Full kit |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#12 |  |  | 100000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | BRIDLE ROLL ASSY.#2 |  |  | 2800000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | machining anil engg complate by 13 |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | BRIDLE ROLL ASSY.#3 |  |  | 3300000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | In assy |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | BRIDLE ROLL ASSY.#4 |  |  | 2913349 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | machining anil engg complate by 13 |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | ENTRY ACCUMULATOR COUNTER WEIGHT |  |  | 1905528 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | EXIT ACCUMULATOR STRUCTURE |  |  | 2809197 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | 809197 value will dispatch in OCT |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | EXIT ACCUMULATOR TOP PLATFORM |  |  | 7404661 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Full kit, chequred plate in house available |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | EXIT ACCUMULATOR COUNTER WEIGHT |  |  | 1905528 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | ENTRY PINCH ROLL ASSY.#1 |  |  | 949295 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | ENTRY PINCH ROLL ASSY.#2&3 |  |  | 932270 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | ENTRY PINCH ROLL ASSY.#4 |  |  | 942825 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | DEBURRING ROLL ASSY. |  |  | 593498 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | EXIT PINCH ROLL ASSY. |  |  | 871532 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | EXIT PINCH CUM DEFLECTOR ROLL ASSY. |  |  | 830417 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | SUPPORT ROLL ASSY.#5 |  |  | 100000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | SINGLE SQUEEZE ROLL ASSY. |  |  | 2525000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | BRUSHING ROLL ASSY.#1 |  |  | 435000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | BRUSHING ROLL ASSY.#2 |  |  | 435000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | Blower Fan |  |  | 5450000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | EVG 6 fan ready, 6 ready by 22, LC Required |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | Oven Burner |  |  | 3520000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | ESA Ready by 29 sept |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | Incinerator Burner |  |  | 1900000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | ESA Ready by 29 sept Except gas valve station - 15 oct |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | Prime Oven-Plenum Assembly |  |  | 1500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | Prime Oven-Burner Chamber |  |  | 1800000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | SPEC DISPATCHED |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | Finish Oven-Plenum Assembly |  |  | 1500000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | VERA ready by 16 sept |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | Finish Oven-Burner Chamber |  |  | 1770000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | SPEC DISPATCHED |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | Cladding & LRB mattress |  |  | 2125000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Ready by 26 sept |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | Oven Structure - Columns |  |  | 10000000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | ready for dispatch, pi submit |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | Oven Structure- Beams sept lot |  |  | 3000000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | In process, Material will also dispatch in oct |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | CPC SENSOR ASSY.#1,2,3,4,5,6,7 & EPC |  |  | 8400000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Ready for dispatch at mumbai, payment req |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | VALVE STAND |  |  | 3000000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Ready by 29 Aug, All material received at aulos |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | HYDRAULIC POWER PACK |  |  | 7500000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Ready by 28 sept |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | HYDRAULIC & PNEUETIC FITTINGS Sept Lot |  |  | 6000000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | under ordering by 12 sept |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | UTILITY-COOLING TOWER |  |  | 1600000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Ready by 15 sept, payment req |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | UTILITY-RECIEVER TANK |  |  | 300000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Ready by 15 sept, payment req |  |  |  | CCL | Sep 2025
2420-INDIA STEEL-CCL |  | SAURABH | ELECTRICAL Sept Lot |  |  | 14000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CCL | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | POR-COIL SADDLE |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | ETR-COIL SADDLE |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | DTR-COIL SADDLE |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | MOTOR BASE FRAME FOR ETR |  |  | 2400000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | UNDER MACHINING |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | MOTOR BASE FRAME FOR DTR |  |  | 2400000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | UNDER MACHINING |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | MOTOR BASE FRAME FOR MILL DRIVE |  |  | 2400000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | UNDER MACHINING |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | ETR MANDREL ASSEMBLY |  |  | 5600000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | ROTARY UNION FROM MACO |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | ETR-GEARBOX ASSY |  |  | 9400000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | ETR-PUSHER PLATE ASSY. |  |  | 550000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | DTR-MANDREL ASSY |  |  | 5350000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | DTR-GEARBOX ASSY |  |  | 9450000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | DTR-PUSHER PLATE ASSY. |  |  | 550000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | THREE ROLL FEEDER |  |  | 1600000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | QWRC TROLLEY ASSY |  |  | 7000000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | QWRC SAFETY CAGE |  |  | 500000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | FAB. ONGOING |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | PEELER TABLE |  |  | 181000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | CARRY OVER TABLE |  |  | 730000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | PASSING TABLE #1 (BET. THREE ROLL FEEDER & ENTRY SHEAR) |  |  | 200000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | BACKUP CHOCK BEARINGS (6 NOS.) |  |  | 6032000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | WORK ROLL CHOCK BEARINGS (4 NOS.) |  |  | 1045000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | IMR CHOCKS BEARINGS (4 NOS.) |  |  | 1274000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | ROLL COOLANT HEADER ASSY |  |  | 900000 | Disp. | 2025-09-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | FUME EXHAUST SYSTEM WITH BLOWER ASSY |  |  | 5500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | ROLL COOLANT TANK |  |  | 4500000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | COOLANT FILTERATION SYSTEM |  |  | 10000000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2427-PROMPT-6HI CRM |  | MAYANK | PNEUMATIC PIPES & FITTINGS |  |  |  | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | CRM | Sep 2025
2506-JSW-APL |  | ADITYA SHARMA | Furnace Structure - SEP LOT |  |  | 9469000 | Disp. | 2025-09-28 |  | FALSE | FALSE | [5 empty] | APL | Sep 2025
2424-MMI-6HI CRM |  | MAYANK | Mill top platform assembly |  | 5000 | 1290000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | AS PER DISCUSSION WITH TRIPATHI SIR, SIZE AND QUANTITY OF PLATES TO BE SENT TO THE SITE, HOWEVER, DETAILS OF THE PLATES WILL BE GIVEN IN JUNE 2025 |  |  |  | CRM | Aug 2025
2424-MMI-6HI CRM |  | MAYANK | Coolant Sump System (For CRM Without Cellar) |  | 19348.8372 | 1664000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2424-MMI-6HI CRM |  | MAYANK | Fume exhaust ducts |  | 0 | 0 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | DUCTING IS BEING FABRICATED AT SITE |  |  |  | CRM | Aug 2025
2424-MMI-6HI CRM |  | MAYANK | IMR CHOCKS - 4 NOS. (SPARE) |  |  | 1000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Aug 2025
2424-MMI-6HI CRM |  | MAYANK | IMR CHOCKS - 4 NOS. (SPARE) |  | 11627.907 | 1000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Aug 2025
2425-MMI-6HI CRM |  | MAYANK | OBBS Assembly for etr & DTR |  | 12000 | 1032000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2425-MMI-6HI CRM |  | MAYANK | COIL CAR RAILS & PIT COVER |  | 5000 | 430000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2425-MMI-6HI CRM |  | MAYANK | Hydraulic , pneumatic , MS pipes & fittings |  | 12000 | 1032000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2425-MMI-6HI CRM |  | MAYANK | QWRC |  | 90000 | 7740000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2425-MMI-6HI CRM |  | MAYANK | Hydraulic System ( Power pack & Valve tables) + hydl filter - 2 set as spare |  | 160000 | 13760000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Aug 2025
2425-MMI-6HI CRM |  | MAYANK | WORK ROLL bearing - 4nos |  | 12000 | 1032000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Aug 2025
2425-MMI-6HI CRM |  | MAYANK | IMR ROLL bearing - 4nos |  | 18000 | 1548000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Aug 2025
2425-MMI-6HI CRM |  | MAYANK | BACK UP ROLL bearing - 4nos |  | 130000 | 11180000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | Aug 2025
2207-JTL-6HI CRM |  | ADITYA SHARMA | WORK ROLLS |  |  | 1060000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2207-JTL-6HI CRM |  | ADITYA SHARMA | IMR ROLLS |  |  | 1000000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#1 |  |  | 1500000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | BRIDLE ROLL ASSY.#2 |  |  | 1500000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | ANTI CRIMP ROLL ASSY |  |  | 250000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | ANTI CROSS ROLL ASSY |  |  | 250000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | BACKUP ROLL CLAMP ASSY |  |  | 0 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | WORK ROLL CLAMP ASSY |  |  |  | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | MILL HOUSING AND LINERS ASSY. |  |  | 7000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | MAEWEST BLOCK ASSY |  |  | 2000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | BED PLATE |  |  | 2000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | SPINDLE COUPLING |  |  | 700000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | SPINDLE SUPPORT ARM ASSY |  |  |  | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | TOP SEPARATOR ASSY. |  |  | 0 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | ROLL FORCE CYLINDER ASSY. |  |  | 2000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | TAPER WEDGE ASSY |  |  | 1000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | EXIT SHEAR MACHINE ASSY. |  |  | 1000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | THICKNESS GAUGE SUPPORT |  |  | 4000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | HYDRAULIC POWER PACK & VALVE TABLE |  |  | 7000000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | AIR OIL LUBRICATION SYSTEM ASSY |  |  | 1500000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | BOI |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | BACKUP INSIDE TRACK |  |  | 200000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | BACKUP ROLL CHANGE TROLLY |  |  | 400000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | WORK ROLL INSIDE TRACK |  |  | 200000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | QWRC TROLLEY |  |  | 1500000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Aug 2025
2407-APL-PICKLING |  | SACHIN | HOT AIR DRYER ASSY BOI |  |  | 400000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | F/up with Ajay Mishra |  |  |  | APL | Aug 2025
2407-APL-PICKLING |  | SACHIN | ACID RECIRCULATION SYSTEM |  |  | 400000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Shifted to august for commissioning |  |  |  | APL | Aug 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ETR-COIL WEIGHING SYSTEM |  |  | 600000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | DTR-COIL WEIGHING SYSTEM |  |  | 600000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | DTR-MANDREL ASSY,GEARBOX,PUSHER PLATE |  |  | 11500000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | THICKNESS GUAGE |  |  | 12000000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | wr chocks - 4nos |  |  | 1600000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | FUME EXHAUST SYSTEM WITH BLOWER ASSY |  |  | 5150534 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | COOLANT FILTERATION SYSTEM |  |  | 11500000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | FOUNDATION BOLTS |  |  | 929166 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | SPARE-IMR ROLLS CHOCKS-1set |  |  | 1600000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2231-SHYAM-6HI CRM |  | SAURABH | Fume exhaust ducts |  |  | 500000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2231-SHYAM-6HI CRM |  | SAURABH | CPC |  |  | 300000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Ready at Mumbai. LC Required |  |  |  | CRM | Aug 2025
2231-SHYAM-6HI CRM |  | SAURABH | Agitator & Heat exchanger |  |  |  | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2231-SHYAM-6HI CRM |  | SAURABH | Meawest piston ( SPARE ) |  |  |  | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Ready for dipatch at dudhola |  |  |  | CRM | Aug 2025
2231-SHYAM-6HI CRM |  | SAURABH | WR chocks - 4 nos (1 SET) spares |  |  | 200000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2405-JSPL-TRIMMING |  | SAURABH | ELECTRICAL |  |  | 3500000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2025
2301-CIM-6HI CRM |  | MAYANK | IMR & WR BEARINGS (SPARE - NEW ORDER) |  |  | 2342928 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | UNCOILER-UNCOILER MANDREL,GEARBOX,SNUBBER |  |  | 6450000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | RECOILER-MANDREL, GEARBOX PUSHER PLATE |  |  | 7450000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | EXIT-PINCH CUM DEFLECTOR ROLL ASSY |  |  | 400000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | SHEAR ASSY. |  |  | 600000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | TRIMMER HEAD ASSY. |  |  | 2300000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | SCRAP BAILER ASSY. |  |  | 700000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | HYDRAULIC FITTING |  |  | 350000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | PNEUMATIC FITTING |  |  | 350000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Aug 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | EPC |  |  | 700000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | At mumbai |  |  |  | TRIMMING | Aug 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | CPC |  |  | 700000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | At mumbai |  |  |  | TRIMMING | Aug 2025
2305-APL-CGL |  | SAURABH | DFF ASSEMBLY |  |  | 300000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | 4 casing refractory in progress, Ready by 10 Aug |  |  |  | CGL | Aug 2025
2305-APL-CGL |  | SAURABH | HBR DRIVE ASSY |  |  | 250000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Dispatched 26 aug |  |  |  | CGL | Aug 2025
2305-APL-CGL |  | SAURABH | ASSEMBLY OF TUNNEL |  |  | 700000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | 3 tunnel casing Ready, refractory pending, ready by 20 aug |  |  |  | CGL | Aug 2025
2305-APL-CGL |  | SAURABH | MIG WELDER ASSY. |  |  | 1430000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | In transit, Will reach port by 30 JULY |  |  |  | CGL | Aug 2025
2305-APL-CGL |  | SAURABH | Gas station with flow meter and filter |  |  | 500000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Ready, Payment required ECLIPSE |  |  |  | CGL | Aug 2025
2305-APL-CGL |  | SAURABH | POT--Air knife and Edge baffle assembly |  |  | 10557000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | In transit, reach by 10 aug on port |  |  |  | CGL | Aug 2025
2305-APL-CGL |  | SAURABH | SPM ROLLS |  |  | 1000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Roll at shah forged, dispatch in August |  |  |  | CGL | Aug 2025
2426-VIKAS-PICKLING |  | SACHIN | SINGLE SQUEEZE ROLL ASSY. (12 Assy) |  |  | 7000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Aug 2025
2426-VIKAS-PICKLING |  | SACHIN | DOUBLE SQUEEZE ROLL ASSY.(2 ASSY) |  |  | 3000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | PICKLING | Aug 2025
2426-VIKAS-PICKLING |  | SACHIN | ELECTRICAL PACKAGE |  |  | 5000000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | PICKLING | Aug 2025
2421-APL-CGL |  | SAURABH | UNCOILER ASSY # 1 WITH SNUBBER ROLL ASSY |  |  | 3100000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | UNCOILER #1-ENTRY OBBS ASSY |  |  | 100000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | UNCOILER ASSY # 2 WITH SNUBBER ROLL ASSY |  |  | 3100000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | UNCOILER #2 ENTRY OBBS ASSY |  |  | 100000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#6 |  |  | 2100000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#7 |  |  | 2100000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR WIRE ROPE |  |  | 500000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | D.D ENTRY SHEAR ASSY. |  |  | 600000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | DELIVERY SHEAR ASSY. |  |  | 300000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#5 |  |  | 300000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#7 |  |  | 400000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | SINGLE STEERING ROLL ASSY. @ ENTRY ACC ASSY. |  |  | 800000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Entry Seal Assembly |  |  | 800000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Entry Seal Refractory |  |  | 100000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Entry Seal Drive Assembly |  |  | 100000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | UNDER ASSY |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Tunnel-1 Assembly |  |  | 900000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | UNDER ASSY |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Water Cooled Hearth Roll Drive Assembly |  |  | 100000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | UNDER ASSY |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Tunnel-3 Assembly |  |  | 800000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | UNDER ASSY |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Tunnel-1 Refractory |  |  | 1000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | UNDER ASSY |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Tunnel-3 Refractory |  |  | 800000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | UNDER ASSY |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Water Cooled Hearth Roll Drive Assembly |  |  | 100000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Water Cooled Hearth Roll Drive Assembly |  |  | 100000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Down chute Assy. |  |  | 1200000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Moving Pendant Assembly |  |  | 300000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Moving Trolley |  |  | 1500000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | READY AT VENDOR END,PAYMENT REQUIRED |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Cooling pendant assembly |  |  | 400000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Down pass Cooling pendant assembly |  |  | 400000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Non Ox Burners |  |  | 2000000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Adjustable Gas Control valves |  |  | 368360 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | JCF Heat Exchanger |  |  | 1800000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Required |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Flow Sensor |  |  | 176400 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Thermocouple & Compensating Cable |  |  | 273910 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | IR Pyrometers |  |  | 300000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | H2 analyzer, Dew Point Analyzer,O2 Analyzer |  |  | 1500000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Recuperator For Non-OX Furnace |  |  | 1800000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | HNX Gas Station |  |  | 1500000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Payment Done |  |  |  | CGL | Aug 2025
2421-APL-CGL |  | SAURABH | Main gas station |  |  | 1056000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CGL | Aug 2025
2508-MMI-SPARE |  | SACHIN | SPARE |  |  | 8800000 | Not Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | SPARE | Aug 2025
2012-APL-SPARES |  | ADITYA SAINI | SPARE |  |  | 11275100 | Not Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | SPARE | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | UNCOILER COIL CAR ASSY. |  |  | 2500000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | RECOILER COIL CAR ASSY. |  |  | 1200000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | ENTRY ACCUMULATOR STRUCTURE |  |  | 2809197 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | ENTRY ACCUMULATOR TOP PLATFORM |  |  | 4404661 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Key indent |  |  |  | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | ENTRY ACCUMULATOR CHAIN |  |  | 1500000 | Disp. | 2025-08-28 |  | FALSE | FALSE |  | Full kit |  |  |  | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | EXIT ACCUMULATOR CHAIN |  |  | 1500000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | SINGLE STEERING ROLL ASSY.#1,2,3,7 |  |  | 3500000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | AIR KNIFE ASSEMBLY |  |  | 460000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | CHEMICAL DRYER ASSEMBLY |  |  | 1150000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | AIR COOLING SECTION ASSEMBLY @ PRIME QUENCH TANK |  |  | 600000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | AIR COOLING SECTION ASSEMBLY @ FINISH QUENCH TANK |  |  | 600000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | Primary Heat Exchanger |  |  | 6350000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | Prime Oven Assembly (Trim, Frame,Door, Duct) |  |  | 2830000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | Prime Oven-Panel Assembly |  |  | 1275000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | Finish Oven Assembly (Trim, Frame,Door, Duct) |  |  | 2850000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | Finish Oven-Panel Assembly |  |  | 1275000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | FOUNDATION BOLT |  |  | 1100000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2420-INDIA STEEL-CCL |  | SAURABH | UTILITY-COMPRESSOR & DRYER |  |  | 2500000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CCL | Aug 2025
2427-PROMPT-6HI CRM |  | MAYANK | ELECTRICAL |  |  | 65000000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2427-PROMPT-6HI CRM |  | MAYANK | MILL DRIVE |  |  | 7200000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2427-PROMPT-6HI CRM |  | MAYANK | FOUNDATION BOLTS + TAPER PLATES SET |  |  | 2506000 | Disp. | 2025-08-28 |  | FALSE | FALSE | [5 empty] | CRM | Aug 2025
2424-MMI-6HI CRM |  | MAYANK | DRIVE SPINDLE COUPLING - 1 SET (SPARE) |  | 5813.9535 | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2425-MMI-6HI CRM |  | MAYANK | Electrical Package (MCC Panel, Control Desk, AGC System, PLC & Automation ) |  | 650000 | 55900000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2425-MMI-6HI CRM |  | MAYANK | Fume Exhaust system |  | 66000 | 5676000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | READY AT VAPCON. DISPATCH CLEARANCE & PDC REQUIRED |  |  |  | CRM | Jul 2025
2425-MMI-6HI CRM |  | MAYANK | Roll Coolant Filteration System Part 2 |  | 60000 | 5160000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2425-MMI-6HI CRM |  | MAYANK | Geared spindle couplings - 2 set |  | 80000 | 6880000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | AT MUMBAI PORT |  |  |  | CRM | Jul 2025
2425-MMI-6HI CRM |  | MAYANK | WORK ROLL - 2nos |  | 10000 | 860000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | READY AT BAO STEEL |  |  |  | CRM | Jul 2025
2425-MMI-6HI CRM |  | MAYANK | BACK UP ROLL - 2nos |  | 100000 | 8600000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | UNDER FINISH MACHINING & ASSEMBLY OF INNER RACE AT BAO STEEL |  |  |  | CRM | Jul 2025
2425-MMI-6HI CRM |  | MAYANK | IMR ROLL - 2nos |  | 17000 | 1462000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | READY AT BAO STEEL |  |  |  | CRM | Jul 2025
2403-GOPANI-4HI CRM |  | MAYANK | Fume Exhaust System |  |  | 3000000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | READY AT VAPCON. PDC AND DISPATCH CLEARANCE REQUIRED |  |  |  | CRM | Jul 2025
2403-GOPANI-4HI CRM |  | MAYANK | Electrical |  |  | 32500000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | CRM | Jul 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | UNCOILER-COIL CAR PIT COVER |  |  | 200000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jul 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | RECOILER-COIL CAR PIT COVER |  |  | 200000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jul 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | UNCOILER-MANDREL, GEARBOX, SNUBBER ASSY |  |  | 5000000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jul 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | RECOILER-MANDREL, MANDREL, PUSHER PLATE ASSY |  |  | 5000000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jul 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | PEELER TABLE ASSY. |  |  | 200000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jul 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | EXIT THREADING TABLE ASSY. |  |  | 200000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jul 2025
2407-APL-PICKLING |  | SACHIN | UNCOILER #2 |  |  | 1400000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | APL | Jul 2025
2407-APL-PICKLING |  | SACHIN | OILING SPRAYING SYSTEM BOI |  |  | 108000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | APL | Jul 2025
2407-APL-PICKLING |  | SACHIN | HYDRAULIC & PNEUMATIC FITTINGS |  | 2000000 | 500000 | Not Disp. | 2025-07-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | APL | Jul 2025
2407-APL-PICKLING |  | SACHIN | REKHA 5 TON GRANITE + SEALANT |  |  | 1000000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | APL | Jul 2025
2407-APL-PICKLING |  | SACHIN | PRESSURE REDUCING STATION WITH CRS |  |  | 1030000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | APL | Jul 2025
2407-APL-PICKLING |  | SACHIN | HEAT EXCHANGER ( 4 NOS.) |  |  | 1260000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | APL | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | POR-OBBS ASSY |  |  | 200000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ENTRY TILTING TABLE ASSY |  |  | 250000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | EXIT TILTING TABLE ASSY |  |  | 250000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | BACKUP STOOL ASSY. |  |  | 300000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | HYDRAULIC PIPES,FITTINGS. |  |  | 2100000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | BACKUP ROLL PULLING TROLLY |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | POR-MANDREL ASSY,GEARBOX,SNUBBER |  |  | 8000000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ETR-MANDREL ASSY,GEARBOX,PUSHER PLATE |  |  | 11500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ETR-OBBS ASSY |  |  | 300000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | DTR-OBBS ASSY |  |  | 300000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | DELIVERY SHEAR ASSY |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | Back up roll chocks - 4 nos |  |  | 6000000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | Imr Chocks - 4 nos |  |  | 1600000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | WORK ROLL bearing |  |  | 878856 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | IMR ROLL bearing |  |  | 1080584 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | BACK UP ROLL bearing |  |  | 7260560 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | IMR SHIFTING ASSY. |  |  | 1800000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | SPINDLE SUPPORT ASSY |  |  | 1500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | MAEWEST BLOCK ASSY. |  |  | 5800000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ENTRY DEFLECTOR CUM TURN DOWN |  |  | 800000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ENTRY C FRAME |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | DELIVERY DEFLECTOR CUM TURN DOWN |  |  | 800000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | EXIT C FRAME |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | PINION GEAR BOX |  |  | 4000000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | TOP SEPARATOR ASSY. |  |  | 100000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | SHUTTER ASSY |  |  | 300000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | TAPER WEDGE ASSY |  |  | 2582000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ROLL COOLANT HEADER ASSY |  |  | 900000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ENTRY AIR WIPER ASSY |  |  | 200000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | BACKUP WIPER ASSY |  |  | 380000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | EXIT AIR WIPER ASSY |  |  | 200000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | COBBLE GUARD ASSY |  |  | 1750000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ENTRY AIR KNIFE ASSY |  |  | 200000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | EXIT AIR KNIFE ASSY |  |  | 200000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ENTRY PASSING TABLE @ MILL STAND |  |  | 187500 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | EXIT PASSING TABLE @ MILL STAND |  |  | 187500 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | INTER CONNECTING PIPING |  |  | 400000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | DISTRIBUTION HEADERS |  |  | 615000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | CELLER VENTILATION SYSTEM WITH BLOWER ASSY |  |  | 860000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | FOUNDATION BOLTS |  |  | 400000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | BACKUP INSIDE TRACK |  |  | 100000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | BACKUP OUTSIDE TRACK |  |  | 100000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | WORK ROLL & IMR INSIDE TRACK |  |  | 100000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2231-SHYAM-6HI CRM |  | SAURABH | Hydraulic System-Power Pack |  |  | 7400000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Ready by 22 July. LC Required |  |  |  | CRM | Jul 2025
2231-SHYAM-6HI CRM |  | SAURABH | BUP chocks - 4 nos (1 SET) spares |  |  | 1600000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Ready by 24 July |  |  |  | CRM | Jul 2025
2231-SHYAM-6HI CRM |  | SAURABH | IMR Chocks - 4 nos (1 SET) spares |  |  | 600000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2405-JSPL-TRIMMING |  | SAURABH | SADDLE ASSY.#1 (LOAD CELL) @ RECOILER |  |  | 300000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2405-JSPL-TRIMMING |  | SAURABH | UNCOILER ASSY. |  |  | 9500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2405-JSPL-TRIMMING |  | SAURABH | RECOILER ASSY. |  |  | 10500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2405-JSPL-TRIMMING |  | SAURABH | TABLE-2 |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2405-JSPL-TRIMMING |  | SAURABH | TRIMMER HEAD ASSY. |  |  | 3000000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2301-CIM-6HI CRM |  | MAYANK | STEAM HEATING ARRANGEMENT FOR COOLANT FILTRATION SYSTEM |  |  | 1500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2301-CIM-6HI CRM |  | MAYANK | SPARE SPINDLE COUPLING |  | 40000 | 3440000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CRM | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | UNCOILER-COIL CAR ASSY. |  |  | 600000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | UNCOILER-PIT COVER |  |  | 100000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | RECOILER-COIL CAR ASSY. |  |  | 600000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | RECOILER-PIT COVER |  |  | 100000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | UNCOILER-ENTRY OBBS ASSY |  |  | 600000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | RECOILER-EXIT OBBS ASSY |  |  | 600000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | PEELER TABLE ASSY. |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | SCRAP DOWN TABLE ASSY. |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE & SUIT ASSY. |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | THREADING TABLE ASSY. |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | SCRAP TROLLEY ASSY. |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | ENTRY-PINCH CUM DEFLECTOR ROLL ASSY |  |  | 800000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | DEBURRING ROLL ASSY. |  |  | 1000000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | SIDE GUIDE ASSY. |  |  | 1000000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | TENSIONER ASSY. |  |  | 1000000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | ELECTRICAL |  |  | 3500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | UNCOILER MANDREL ASSY. |  |  | 1000000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | This Week |  |  |  | TRIMMING | Jul 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | UNCOILER GEAR BOX ASSY. |  |  | 3000000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | This Week |  |  |  | TRIMMING | Jul 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | UNCOILER SNUBBER ROLL ASSY. |  |  | 1000000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | This Week |  |  |  | TRIMMING | Jul 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | RECOILER MANDREL ASSY. |  |  | 2000000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | This Week |  |  |  | TRIMMING | Jul 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | RECOILER GEAR BOX ASSY. |  |  | 4000000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | This Week |  |  |  | TRIMMING | Jul 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | RECOILER PUSHER PLATE ASSY. |  |  | 1000000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | This Week |  |  |  | TRIMMING | Jul 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | SCRAP BAILER ASSY. |  |  | 1000000 | Not Disp. | 2025-07-28 |  | FALSE | FALSE |  | 2025-07-22 |  |  |  | TRIMMING | Jul 2025
2401-AART-TRIMMER |  | ADITYA SAINI | HYD. POWER PACK |  |  | 0 | Not Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jul 2025
2504-BMWIL-SPARES |  | ADITYA SHARMA | CARTRIDGE |  |  | 700000 | Not Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | SPARE | Jul 2025
2305-APL-CGL |  | SAURABH | PINION STAND GEARBOX |  |  | 390942 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Dispatch with RTF CASING 1, Ready by 24 july, |  |  |  | CGL | Jul 2025
2305-APL-CGL |  | SAURABH | CAG & Furnace Structure with staircase |  |  | 0 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2025
2305-APL-CGL |  | SAURABH | DFF burners with Accessories |  |  | 600000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | IN House received from ESA manufacturing, dispatch on 23 july |  |  |  | CGL | Jul 2025
2305-APL-CGL |  | SAURABH | Rotameter |  |  | 0 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | In house received from fitzer, dispatch on 23 july |  |  |  | CGL | Jul 2025
2305-APL-CGL |  | SAURABH | JCF ASSEMBLY |  |  | 200000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Ready, dispatch on 23 july |  |  |  | CGL | Jul 2025
2305-APL-CGL |  | SAURABH | SCH ASSEMBLY |  |  | 200000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Ready for dispatch, Dispatch by 23/24 july |  |  |  | CGL | Jul 2025
2305-APL-CGL |  | SAURABH | RTF / SF Casing |  |  | 400000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | Casing #1 dispatch by 24 july, casing #4 ready by 26 july |  |  |  | CGL | Jul 2025
2305-APL-CGL |  | SAURABH | STEERING CUM TURN UP ROLL ASSY. |  |  | 100000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2025
2305-APL-CGL |  | SAURABH | SPM 45 KW Motor |  |  |  | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2025
2221-TPI REVAMP |  | MAYANK | BRAKES & MOTOR FRAME |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | REVAMP | Jul 2025
2421-APL-CGL |  | SAURABH | UNCOILER-DRAG CHAIN ASSY. |  |  | 300000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | DARGCHAIN FRAME STAND PENDING |  |  |  | CGL | Jul 2025
2421-APL-CGL |  | SAURABH | RECOILER-DRAG CHAIN ASSY. |  |  | 300000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | DARGCHAIN FRAME STAND PENDING |  |  |  | CGL | Jul 2025
2421-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#3 |  |  | 2100000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | ,FAB M/C PENDING |  |  |  | CGL | Jul 2025
2421-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#5 |  |  | 2100000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | FULL KIT BY 10-JULY |  |  |  | CGL | Jul 2025
2421-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR CHAIN |  |  | 1200000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2025
2421-APL-CGL |  | SAURABH | SINGLE STEERING ROLL ASSY. |  |  | 400000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | FAB PENDING , ROLL PENDING , M/C ITEMS PENDING |  |  |  | CGL | Jul 2025
2421-APL-CGL |  | SAURABH | COATING THK GAUGE ASSY. |  |  | 5000000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | ORDERING DONE TO JASCH, FOLLOW UP REQ |  |  |  | CGL | Jul 2025
2421-APL-CGL |  | SAURABH | FOUNDATION BOLT |  |  | 500000 | Disp. | 2025-07-28 |  | FALSE | FALSE |  | READY BY 25-JUNE |  |  |  | CGL | Jul 2025
2421-APL-CGL |  | SAURABH | TAPER PLATE |  |  | 1000000 | Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | CGL | Jul 2025
2508-MMI-SPARE |  | SACHIN | SPARE |  |  | 10000000 | Not Disp. | 2025-07-28 |  | FALSE | FALSE | [5 empty] | SPARE | Jul 2025
2424-MMI-6HI CRM |  | MAYANK | Back up roll chocks - 4 nos |  | 23280 | 2000000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2424-MMI-6HI CRM |  | MAYANK | WORK ROLL - 2nos |  | 8820 | 800000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | VESSEL FOR UGANDA BOOKED FROM CHINA FOR 26TH JUNE 2025 |  |  |  | CRM | Jun 2025
2424-MMI-6HI CRM |  | MAYANK | BACK UP ROLL - 2nos |  | 102900 | 7900000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | VESSEL FOR UGANDA BOOKED FROM CHINA FOR 26TH JUNE 2025 |  |  |  | CRM | Jun 2025
2424-MMI-6HI CRM |  | MAYANK | IMR ROLL - 2nos |  | 14280 | 1462000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | VESSEL FOR UGANDA BOOKED FROM CHINA FOR 26TH JUNE 2025 |  |  |  | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | OBBS @ POR |  | 6000 | 516000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | DRAG CHAIN |  | 5000 | 430000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | FULL KIT |  |  |  | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | Coil saddles |  | 5000 | 430000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | Carry over tables, Threading tables , peeler tables and other feeding tables |  | 50000 | 4300000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | Back up Pulling trolley |  | 15000 | 1290000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | Back up stool assembly |  | 15000 | 1290000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | Three Feeder roll assembly |  | 40000 | 3440000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | Shearing machine Mill entry side |  | 15000 | 1290000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | Base frames for Motors |  | 30000 | 2580000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | Pay off reel assembly with , Snubber Roll assembly - |  | 105000 | 9030000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | ETR assembly along along with spare rotary union |  | 175000 | 15050000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jun 2025
2425-MMI-6HI CRM |  | MAYANK | DTR Assembly |  | 175000 | 15050000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | READY |  |  |  | CRM | Jun 2025
2403-GOPANI-4HI CRM |  | MAYANK | Back up bearing |  |  | 4000000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2403-GOPANI-4HI CRM |  | MAYANK | Back up roll chock |  |  | 3000000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | UNCOILER-COIL CAR ASSY. |  |  | 1000000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jun 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | UNCOILER-DRAG CHAIN ASSY. |  |  | 200000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jun 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | UNCOILER-COIL SADDLE ASSY. |  |  | 100000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jun 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | RECOILER-COIL CAR ASSY. |  |  | 1000000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jun 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | RECOILER-DRAG CHAINASSY. |  |  | 200000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jun 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | RECOILER-COIL SADDLE ASSY. |  |  | 100000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jun 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | MILL DRIVE |  |  | 2000000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jun 2025
2404-GOPANI-4HI SPM |  | ADITYA SHARMA | FOUNDATION BOLTS + TAPER PLATES SET |  |  | 1000000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | SPM | Jun 2025
2407-APL-PICKLING |  | SACHIN | UNCOILER #1 |  |  | 1500000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | APL | Jun 2025
2407-APL-PICKLING |  | SACHIN | RECOILER MANDREL ASSY. |  |  | 1000000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | APL | Jun 2025
2407-APL-PICKLING |  | SACHIN | RECOILER GEAR BOX ASSY. |  |  | 500000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | APL | Jun 2025
2407-APL-PICKLING |  | SACHIN | PUSHER PLATE ASSY. |  |  | 500000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | APL | Jun 2025
2407-APL-PICKLING |  | SACHIN | SHEAR & WELDER SYSTEM BOI |  |  | 2880000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | APL | Jun 2025
2407-APL-PICKLING |  | SACHIN | RLA BOI |  |  | 9218000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | APL | Jun 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | POR-COIL CAR |  |  | 1000000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ETR-COIL CAR |  |  | 1000000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ETR-DRAG CHAIN |  |  | 100000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | DTR-COIL CAR |  |  | 1000000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | DTR-DRAG CHAIN |  |  | 110000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | PEELER TABLE ASSY |  |  | 250000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | CARRY OVER TABLE WITH ENTRY SHEAR |  |  | 500000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | Electricals, such As AC Drive Panels |  |  | 40000000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | MCC Panel, Control Desk, AGC System, PLC & Automation |  |  | 4800000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2231-SHYAM-6HI CRM |  | SAURABH | BUP TOP Chocks |  |  | 4000000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | DISPATCHED |  |  |  | CRM | Jun 2025
2231-SHYAM-6HI CRM |  | SAURABH | Air oil System SS Pipes |  |  | 0 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2231-SHYAM-6HI CRM |  | SAURABH | Shear Pin coupling |  |  | 0 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | DISPATCHED |  |  |  | CRM | Jun 2025
2231-SHYAM-6HI CRM |  | SAURABH | Belt wrapper |  |  | 0 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CRM | Jun 2025
2231-SHYAM-6HI CRM |  | SAURABH | BACK UP ROLL - 1nos |  |  | 5000000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Dispatch on 9 june from china, High sea sale |  |  |  | CRM | Jun 2025
2231-SHYAM-6HI CRM |  | SAURABH | IMR ROLL - 2nos |  |  | 1800000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Dispatch on 9 june from china, High sea sale |  |  |  | CRM | Jun 2025
2231-SHYAM-6HI CRM |  | SAURABH | WORK ROLL - 2nos |  |  | 1200000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Dispatch on 9 june from china, High sea sale |  |  |  | CRM | Jun 2025
2231-SHYAM-6HI CRM |  | SAURABH | IMR Chocks - 4 nos (1 SET) spares |  |  | 1200000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | DISPATCHED |  |  |  | CRM | Jun 2025
2231-SHYAM-6HI CRM |  | SAURABH | WR chocks - 4 nos (1 SET) spares |  |  | 800000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Chocks 1Set - Under machining |  |  |  | CRM | Jun 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | HYDRAULIC POWER PACK |  |  | 3500000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Jun 2025
2305-APL-CGL |  | SAURABH | PIPES & FITTINGS |  |  |  | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2305-APL-CGL |  | SAURABH | SEAMLESS PIPES |  |  | 400000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2305-APL-CGL |  | SAURABH | HBR ASSY WITH HEARTH ROLL ASSY |  |  | 400000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Casing ready at new plant, Drive send to P 2421 |  |  |  | CGL | Jun 2025
2305-APL-CGL |  | SAURABH | HBR ROLLS |  |  | 400000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2305-APL-CGL |  | SAURABH | ENTRY SEAL FOR FURNACE ASSY., TUNNEL - 1 FOR FURNACE ASSY. & THROAT FOR FURNACE ASSY |  |  | 680000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2305-APL-CGL |  | SAURABH | BLOWER FANS(JCF, CAG, COMBUSTION & EXHAUST) |  |  | 1200000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2305-APL-CGL |  | SAURABH | GAS STATION WITH FLOW METER AND FILTER |  |  | 100000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | LC Required, Eclipse combustion (honeywell) PO-10,56,500 |  |  |  | CGL | Jun 2025
2305-APL-CGL |  | SAURABH | HYDRAULIC POWER PACK |  |  | 0 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Ready by 30 June, 3640000 invoice done by aulos for valve stand |  |  |  | CGL | Jun 2025
2305-APL-CGL |  | SAURABH | HBR DOWN CHUTE |  |  | 1159000 | Disp. | 2025-06-28 |  | FALSE | FALSE |  | Payment required, Dynaxcel |  |  |  | CGL | Jun 2025
2305-APL-CGL |  | SAURABH | Furnace Gas and Combustion Air Piping |  |  | 310000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2305-APL-CGL |  | SAURABH | POT--Pot cellar ventilation supply and exhaust ducting |  |  | 1240000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2421-APL-CGL |  | SAURABH | PEELER TABLE ASSY.#1 |  |  | 150000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2421-APL-CGL |  | SAURABH | PEELER TABLE ASSY.#2 |  |  | 150000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2421-APL-CGL |  | SAURABH | EXIT THREADING TABLE ASSY. |  |  | 100000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2421-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#1 |  |  | 2500000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2421-APL-CGL |  | SAURABH | BRIDLE ROLL ASSY.#2 |  |  | 2100000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2421-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR DEAD WEIGHT & WIRE ROPE-Part 1 |  |  | 300000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2421-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR COUNTER WEIGHT ASSY |  |  | 1000000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2421-APL-CGL |  | SAURABH | BRUSHING ROLL ASSY.#1 |  |  | 275000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2421-APL-CGL |  | SAURABH | BRUSHING ROLL ASSY.#2 |  |  | 275000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2421-APL-CGL |  | SAURABH | TURN DOWN ROLL ASSY. |  |  | 600000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2421-APL-CGL |  | SAURABH | LEVELLER ASSY. |  |  | 1600000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CGL | Jun 2025
2420-INDIA STEEL-CCL |  | SAURABH | EXIT ACCUMULATOR FIX FRAME |  |  | 3000000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2025
2420-INDIA STEEL-CCL |  | SAURABH | EXIT ACCUMULATOR MOVING FRAME |  |  | 2200000 | Disp. | 2025-06-28 |  | FALSE | FALSE | [5 empty] | CCL | Jun 2025
2424-MMI-6HI CRM |  | MAYANK | OBBS Assembly for etr & DTR |  | 0 | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2424-MMI-6HI CRM |  | MAYANK | Coil Car rails , drag chain, pit covers |  | 0 | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2424-MMI-6HI CRM |  | MAYANK | Carry over tables, Threading tables , peeler tables and other feeding tables |  | 6977 | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2424-MMI-6HI CRM |  | MAYANK | Base frames for Motors (Mill Drive) |  | 0 | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2424-MMI-6HI CRM |  | MAYANK | Roll force cylinder |  | 18350 | 1500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2424-MMI-6HI CRM |  | MAYANK | Pay off reel assembly with , Snubber Roll assembly |  | 20000 | 1710000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2424-MMI-6HI CRM |  | MAYANK | Shearing machine Mill entry side |  | 10000 | 900000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2424-MMI-6HI CRM |  | MAYANK | Fume Exhaust system |  | 53500 | 4500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2424-MMI-6HI CRM |  | MAYANK | Hydraulic System ( Power pack & Valve tables) + hydl filter - 2 set as spare |  | 151130 | 12921615 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2207-JTL-6HI CRM |  | ADITYA SHARMA | WORK ROLL CHOCKS |  |  | 800000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | May 2025
2403-GOPANI-4HI CRM |  | MAYANK | Entry shearing machine |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2403-GOPANI-4HI CRM |  | MAYANK | Work Roll bearing |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2403-GOPANI-4HI CRM |  | MAYANK | Work roll chock |  |  | 1900000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2403-GOPANI-4HI CRM |  | MAYANK | Hydraulic system |  |  | 5000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2403-GOPANI-4HI CRM |  | MAYANK | ETR Assembly |  |  | 8400000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2403-GOPANI-4HI CRM |  | MAYANK | Geared spindle |  |  | 4000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2403-GOPANI-4HI CRM |  | MAYANK | DTR Assembly |  |  | 8400000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2407-APL-PICKLING |  | SACHIN | UNCOILER-ENTRY DRAG CHAIN ASSY. 2 ASSY |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2025
2407-APL-PICKLING |  | SACHIN | RECOILER-EXIT DRAG CHAIN ASSY |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2025
2407-APL-PICKLING |  | SACHIN | EXIT SHEAR BOI |  |  | 800000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2025
2407-APL-PICKLING |  | SACHIN | PICKLING TANK 3,4 |  |  | 2000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2025
2407-APL-PICKLING |  | SACHIN | RINSING AND OVER HEAD TANKS |  |  | 2200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2025
2407-APL-PICKLING |  | SACHIN | RUBBER LINING WITH GRANITE BLOCKS |  |  | 1500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2025
2407-APL-PICKLING |  | SACHIN | FUME EXHAUST AND SCRUBBING SYSTEM & REKHA SEALANT |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2025
2407-APL-PICKLING |  | SACHIN | HYDRAULIC & PNEUMATIC FITTINGS |  |  | 1500000 | Not Disp. | 2025-05-28 |  | FALSE | FALSE |  | Unbilled |  |  |  | APL | May 2025
2407-APL-PICKLING |  | SACHIN | HYDRAULIC VALVE STAND |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2025
2407-APL-PICKLING |  | SACHIN | HYDRAULIC POWER PACK |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2025
2407-APL-PICKLING |  | SACHIN | ELECTRICAL PACKAGE |  |  | 3000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | APL | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | POR-DRAG CHAIN |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | POR-COIL SADDLE |  |  | 50000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | POR-COIL CAR PIT COVER |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ETR-COIL SADDLE |  |  | 50000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | ETR-COIL CAR PIT COVER |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | DTR-COIL SADDLE |  |  | 50000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | DTR-COIL CAR PIT COVER |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | THREE ROLL FEEDER |  |  | 2000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | QWRC TROLLEY ASSY |  |  | 4740000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | COOLANT TRAY |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | HYDRAULIC PIPES,FITTINGS. |  |  | 2000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | AIR OIL LUBRICATION SYSTEM ASSY |  |  | 865000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Payment Required |  |  |  | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | GEAR LUBRICATION SYSTEM ASSY |  |  | 1200000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Payment Required |  |  |  | CRM | May 2025
2414-UTTAM-6HI CRM |  | ADITYA SHARMA | TAPER PLATES SET |  |  | 740000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | Hydraulic System-Valve Stand |  |  | 6000000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | DISPATCH ON 31 MAY FROM REXROTH |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | Backup outside track |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | QWRC Rail line |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Machining pending |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | QWRC Drag chain frame |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 21 may |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | POR ETR DTR Drag chain frame |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 21 may |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | TAPER WEDGE Position Transducer with Mounting plate |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 21 may |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | Exit air wiper frame with hyd cylinder |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 21 may |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | ETR DTR Spacer and motor bolts |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 21 may |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | VACO Seal kit |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Received |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | Air oil system cartidges mill fill |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | RECEIVED, DISPATCH AFTER ALL CHOCKS DISPATCH |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | Entry Shear |  |  | 300000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | BUP BOTTOM Chocks |  |  | 4000000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY FOR DISPATCH BY 31 MAY |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | IMR Chock |  |  | 1600000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | WR Chock |  |  | 1200000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | ETR DTR Brake |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Payment required - 28,28,575 |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | Drag Chain - POR ETR DTR |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Received |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | Top platform Assy |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY BY 3O MAY, PAINT PENDING |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | BACK UP ROLL bearing - 2nos |  |  | 3700000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | At delhi MSONS |  |  |  | CRM | May 2025
2231-SHYAM-6HI CRM |  | SAURABH | WORK ROLL bearing - 4nos |  |  | 700000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | At delhi MSONS |  |  |  | CRM | May 2025
2405-JSPL-TRIMMING |  | SAURABH | COIL CAR ASSY.@ UNCOILER |  |  | 2000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2405-JSPL-TRIMMING |  | SAURABH | DRAG CHAIN ASSY.@ UNCOILER |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2405-JSPL-TRIMMING |  | SAURABH | COIL CAR ASSY. @ RECOILER |  |  | 2000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2405-JSPL-TRIMMING |  | SAURABH | DRAG CHAIN ASSY. @ RECOILER |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2405-JSPL-TRIMMING |  | SAURABH | TABLE-1 |  |  | 2000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2405-JSPL-TRIMMING |  | SAURABH | PINCH CUM DEFLECTOR ROLL ASSY |  |  | 2000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2405-JSPL-TRIMMING |  | SAURABH | DEBURRING ROLL ASSY. |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2405-JSPL-TRIMMING |  | SAURABH | SIDE GUIDE ASSY. |  |  | 1500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2405-JSPL-TRIMMING |  | SAURABH | TENSIONER ASSY. |  |  | 1500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2405-JSPL-TRIMMING |  | SAURABH | SCRAP BAILER ASSY. |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2405-JSPL-TRIMMING |  | SAURABH | PRESSURE PAD ASSY. |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | UNCOILER-DRAG CHAIN ASSY. |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | UNCOILER-SADDLE ASSY. |  |  | 150000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | RECOILER-DRAG CHAIN ASSY. |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | RECOILER-SADDLE ASSY. |  |  | 150000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE ASSY.#1 |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE ASSY.#2 |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE ASSY.#3 |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE ASSY.#4 |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE ASSY.#5 |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE ASSY.#6 |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2415-UTTAM-TRIMMING |  | ADITYA SAINI | FOUNDATION BOLTS & TAPER PLATES |  |  | 300000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | COIL CAR ASSY. @ UNCOILER |  |  | 750000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | AC MOTOR FROM ABB MOTORS PENDING |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | DRAG CHAIN ASSY. @ UNCOILER |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | PIT COVER @ UNC |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | COIL CAR ASSY.@ RECOILER |  |  | 750000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | AC MOTOR FROM ABB MOTORS PENDING |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | DRAG CHAIN ASSY.@ RECOILER |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | PIT COVER @ RECOILER |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | UNCOILER ENTRY OBBS ASSY |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | ASSY ON GOING |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | RECOILER EXIT OBBS ASSY |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | PEELER TABLE ASSY. |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | ENTRY PINCH CUM DEFLECTOR ROLL ASSY |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | HOUSING MACHING INPROCESS AT DEEPAK FOLLOW UP REQUIRED |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | EXIT PINCH CUM DEFLECTOR ROLL ASSY |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | HOUSING MACHING INPROCESS AT DEEPAK FOLLOW UP REQUIRED |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | DEBURRING ROLL ASSY. |  |  | 1200000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | HOUSING MACHING INPROCESS AT BHAGWATI FOLLOW UP REQUIRED |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | ENTRY SHEAR ASSY. |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | MATERIAL RECEIVED (READY FOR DISPATCHED) |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | EXIT SHEAR ASSY. |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | MATERIAL RECEIVED (READY FOR DISPATCHED) |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | TENSIONER ASSY. |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | HOUSING MACHING INPROCESS AT DEEPAK FOLLOW UP REQUIRED |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | TRIMMER HEAD ASSY. |  |  | 2800000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY BY 25 MAY 25 |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | HYDRAULIC PIPE & FITTINGS |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | MATERIAL READY FOR DISPATCHED |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | PNEUMATIC PIPE & FITTINGS |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | MATERIAL READY FOR DISPATCHED |  |  |  | TRIMMING | May 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | ELECTRICAL |  |  | 3300000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | WILL BE DISPATCH BY 25 MAY 25 |  |  |  | TRIMMING | May 2025
2305-APL-CGL |  | SAURABH | JCF Heat exchanger |  |  | 2143000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | Billing value to be confirm |  |  |  | CGL | May 2025
2305-APL-CGL |  | SAURABH | Threading Needle Assembly |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2305-APL-CGL |  | SAURABH | ELECTRIC BUNDLE ROD HEATER |  |  | 30000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2305-APL-CGL |  | SAURABH | QUENCHING TANK ASSY. |  |  | 800000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2305-APL-CGL |  | SAURABH | WATER SPRAY UNIT |  |  | 800000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2305-APL-CGL |  | SAURABH | ELECTRICAL |  |  | 3000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2305-APL-CGL |  | SAURABH | D.D ENTRY SHEAR ASSY. |  |  | 1325000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2305-APL-CGL |  | SAURABH | DELIVERY SHEAR ASSY. |  |  | 675000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | DEGREASING TANK ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | BRUSHING TANK ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | HOT WATER RINSING TANK ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | QUENCHING TANK ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | SINGLE SQUEEZE ROLL ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | DOUBLE SQUEEZE ROLL ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | BRUSHING ROLL ASSY.#1 |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | BRUSHING ROLL ASSY.#2 |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | EPC SENSOR ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | CPC SENSOR ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | DEFLECTOR ROLL ASSY.#1 |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | PASSING TABLE ASSY#1 |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | PASSING TABLE ASSY#2 |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | TURN UP ROLL ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | TURN DOWN ROLL ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | DOUBLE STEERING ROLL ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | BRIDLE ROLL ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | CHEMICAL COATER ASSY. |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | FOUNDATION BOLT |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | TAPER PLATE |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | ELECTRICAL |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | HYDRAULIC POWER PACK & VALVE STAND |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | ADITYA SAINI | PIPES & FITTINGS |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Exhaust Ducting ( FURNACE) |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Insulation and claddings sheet |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Threading Needle Assembly |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Furnace Gas and Combustion Air Piping |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Furnace N2 & HNX Piping |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Furnace Emergency N2 station |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Furnace interconnecting Piping |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Furnace Water Station |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Entry Seal & Tunnel Assy |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | DFF Assembly |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Throat Assembly |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | RTF Assembly |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | SF Assembly |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Calm Zone Assembly |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | HBR Assembly |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Down Chute Assy |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Non Ox Burners and acessories |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Adjustable Gas Control valves |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Flow Switches |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Thermocouple |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Temperature Transmitters |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Compensating Cable |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | IR Pyrometers |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Pressure Transmitters |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Solenoid Shut-Off Valves |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | H2, O2 and Dew Point analyzer (HALCYON) |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Electric Heater |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Glow Heater |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Pressure Gauges |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Orifice Plates |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Rotameters |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Pneumatic Shut-Off Valves |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Hot Air Control Valve |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Blower Fan |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE |  | 7 Fans Ready ( payment required ) |  |  |  | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Radiant Tubes |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Recuperator For Non-OX Furnace |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE |  | Material ready Payment required |  |  |  | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | HNX Gas Station |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Furnace Bellows |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Butterfly Valve |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Ball Valve |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Gate Valve |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Globe Valve |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Flow Control Valve |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Pressure Control Valve |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Main gas station |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | HNX Heater |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | Miscellaneous |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | MAIN POT & PMP POT |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | AIR KNIFE & EDGE BAFFLE WITH DROSSER AND ZINC PUMP |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE |  | Advance payment required |  |  |  | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | AIR KNIFE BLOWER (CONTINENTAL ,FRANCE) |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | AIR KNIFE BLOWER MOTOR (ABB ) |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | POT EQUIPMENT SINK ROLL AND DEFLECTOR ASSY |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | AIR KNIFE PIPING |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | POT CELLAR SUPPLY DUCTING |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 25-05-2025 ( payment required ) |  |  |  | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | POT CELLAR EXHAUST DUCTING |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 25-05-2025 ( payment required ) |  |  |  | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | MOVING PENDANT DUCTING |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 25-05-2025 ( payment required ) |  |  |  | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | MOVING PENDANT ASSEMBLY |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 25-05-2025 ( payment required ) |  |  |  | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | MOVING TROLLEY ASSEMBLY |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | DOWN PASS PENDANT |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 25-05-2025 ( payment required ) |  |  |  | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | DOWN PASS PENDANT DUCTING |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 25-05-2025 ( payment required ) |  |  |  | CGL | May 2025
2422-AECPL-CGL |  | SACHIN | AIR DRYER @ CHEMICAL COATER |  |  | 0 | Not Disp. | 2025-05-28 |  | FALSE | FALSE |  | Ready by 25-05-2025 ( payment required ) |  |  |  | CGL | May 2025
2421-APL-CGL |  | SAURABH | UNCOILER-COIL CAR ASSY. |  |  | 1450000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | GLOBAL UNDER ASSY |  |  |  | CGL | May 2025
2421-APL-CGL |  | SAURABH | RECOILER-COIL CAR ASSY. |  |  | 750000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | GLOBAL UNDER ASSY |  |  |  | CGL | May 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#1 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#2 |  |  | 50000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#3 |  |  | 50000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#4 |  |  | 50000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#5 |  |  | 50000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | SCRAP DOWN TABLE ASSY#1 |  |  | 50000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | SCRAP DOWN TABLE ASSY#2 |  |  | 50000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | SCRAP TRAY ASSY |  |  | 50000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | SCRAP TROLLEY ASSY. |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#8 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#9 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#10 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#11 |  |  | 150000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | PASSING TABLE ASSY#12 |  |  | 50000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#1,2,3 |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | MOTOR PENDING FROM GUPTA 4500004700, PINCH ROLL GEARBOX WILL CHANGE BY GK, CARDON SHAFT REC NOT OK, TO BE SEND TO JAYPEE |  |  |  | CGL | May 2025
2421-APL-CGL |  | SAURABH | BASE FRAME FOR ENTRY PINCH ROLL ASSY.#1 |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | BASE FRAME FOR ENTRY PINCH ROLL ASSY.#2 & 3 |  |  | 0 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | ENTRY PINCH ROLL ASSY.#4 |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | MOTOR PENDING FROM GUPTA 4500004700, PINCH ROLL GEARBOX WILL CHANGE BY GK, CARDON SHAFT REC NOT OK, TO BE SEND TO JAYPEE |  |  |  | CGL | May 2025
2421-APL-CGL |  | SAURABH | DEBURRING ROLL ASSY. |  |  | 400000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | EXIT PINCH ROLL ASSY. |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | EXIT PINCH CUM DEFLECTOR ROLL ASSY. |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | DOUBLE DECKER DEFLECTOR ROLL ASSY.#1 |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CGL | May 2025
2421-APL-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#2 |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | DEFLECTOR ROLL ASSY.#3,4 |  |  | 400000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2421-APL-CGL |  | SAURABH | SUPPORT ROLL ASSY. LOT-1 |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | ROLL ORDERED, REMAINING TO BE ORDER |  |  |  | CGL | May 2025
2421-APL-CGL |  | SAURABH | SINGLE SQUEEZE ROLL ASSY. |  |  | 1300000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | HOUSING RECEIED REMAINING TO BE CHECK IN EXCEL SHEET |  |  |  | CGL | May 2025
2421-APL-CGL |  | SAURABH | VERTICAL DOUBLE SQUEEZE ROLL ASSY. |  |  | 700000 | Disp. | 2025-05-28 |  | FALSE | FALSE |  | HOUSING RECEIED REMAINING TO BE CHECK IN EXCEL SHEET |  |  |  | CGL | May 2025
2421-APL-CGL |  | SAURABH | HBR Drive Assembly |  |  | 2500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CGL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | UNCOILER COIL SADDLE ASSY. |  |  | 1000000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | RECOILER COIL SADDLE ASSY. |  |  | 500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#1 |  |  | 115000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#2 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#3 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#4 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#5 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#6 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#7 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#8 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#9 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#10 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#11 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | PASSING TABLE ASSY#12 |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | INSPECTION TABLE |  |  | 100000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | ENTRY ACCUMULATOR FIX FRAME |  |  | 3500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | ENTRY ACCUMULATOR MOVING FRAME |  |  | 2500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | DOUBLE DECKER DEFLECTOR ROLL ASSY.#1 |  |  | 400000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | DEFLECTOR ROLL ASSY.#2 |  |  | 258044 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | DEFLECTOR ROLL ASSY.#3 |  |  | 254972 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | DEFLECTOR ROLL ASSY.#4 |  |  | 261847 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | DEFLECTOR ROLL ASSY.#5 |  |  | 257705 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | DEFLECTOR ROLL ASSY.#6 |  |  | 257705 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | DEFLECTOR ROLL ASSY.#7 |  |  | 257705 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | SUPPORT ROLL ASSY.#1 |  |  | 441596 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | SUPPORT ROLL ASSY.#2 |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | SUPPORT ROLL ASSY.#3 |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | SUPPORT ROLL ASSY.#4 |  |  | 465000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | SUPPORT ROLL ASSY.#5 |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | TAPER PLATE |  |  | 200000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2420-INDIA STEEL-CCL |  | SAURABH | SUPPLY OF ENGINEERING |  |  | 13500000 | Disp. | 2025-05-28 |  | FALSE | FALSE | [5 empty] | CCL | May 2025
2424-MMI-6HI CRM |  | MAYANK | WORK ROLL CHOCKS - 4 NOS. (SPARE) |  | 4660 | 400000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2424-MMI-6HI CRM |  | MAYANK | QWRC |  | 17500 | 1500000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2424-MMI-6HI CRM |  | MAYANK | WORK ROLL bearing - 4nos |  | 12000 | 1032000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2424-MMI-6HI CRM |  | MAYANK | IMR ROLL bearing - 4nos |  | 18000 | 1548000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2424-MMI-6HI CRM |  | MAYANK | DTR Assembly |  | 175000 | 5000000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2425-MMI-6HI CRM |  | MAYANK | Foundation Bolts , Taper plate |  | 19000 | 1634000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2425-MMI-6HI CRM |  | MAYANK | Coil car - 3nos |  | 48000 | 4128000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2425-MMI-6HI CRM |  | MAYANK | Hydraulic , pneumatic , MS pipes & fittings |  | 30000 | 2580000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2425-MMI-6HI CRM |  | MAYANK | AIR OIL SYSTEM |  | 16000 | 1376000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2425-MMI-6HI CRM |  | MAYANK | Pinion Gear Box Assembly - 1nos (1 NOS. SPARE) |  | 40000 | 3440000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2403-GOPANI-4HI CRM |  | MAYANK | Pay off reel with snubber roll |  |  | 4500000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2403-GOPANI-4HI CRM |  | MAYANK | Delivery shearing machine |  |  | 200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2403-GOPANI-4HI CRM |  | MAYANK | Hydraulic system |  |  | 5000000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2403-GOPANI-4HI CRM |  | MAYANK | Hydraulic & pneumatic pipe & fitting-Part 1 |  |  | 3000000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2403-GOPANI-4HI CRM |  | MAYANK | thickness gauge |  |  | 6500000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2403-GOPANI-4HI CRM |  | MAYANK | QWRC |  |  | 3000000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2407-APL-PICKLING |  | SACHIN | PINCH CUM LEVELLER ROLL ASSY. 2 ASSY |  |  | 1200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2025
2407-APL-PICKLING |  | SACHIN | EXIT SIDE GUIDE ASSY. |  |  | 200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2025
2407-APL-PICKLING |  | SACHIN | BRIDLE ROLL ASSY #3 |  |  | 2000000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2025
2407-APL-PICKLING |  | SACHIN | DOUBLE STEERING ROLL ASSY |  |  | 1200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | APL | Apr 2025
2231-SHYAM-6HI CRM |  | SAURABH | POR Assy |  |  | 4500000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2231-SHYAM-6HI CRM |  | SAURABH | ETR OBBS |  |  | 300000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2231-SHYAM-6HI CRM |  | SAURABH | DTR OBBS |  |  | 300000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2231-SHYAM-6HI CRM |  | SAURABH | ETR Extension shaft |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2231-SHYAM-6HI CRM |  | SAURABH | DTR Extension shaft |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2231-SHYAM-6HI CRM |  | SAURABH | Threading Tables |  |  | 200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2231-SHYAM-6HI CRM |  | SAURABH | Peeler tables |  |  | 200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2231-SHYAM-6HI CRM |  | SAURABH | BACK UP ROLL - 1nos |  |  | 5000000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CRM | Apr 2025
2405-JSPL-TRIMMING |  | SAURABH | SADDLE ASSY.#1 @ UNCOILER |  |  | 200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2405-JSPL-TRIMMING |  | SAURABH | SADDLE ASSY.#2 @ UNCOILER |  |  | 200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2405-JSPL-TRIMMING |  | SAURABH | SADDLE ASSY.#2 @ RECOILER |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2405-JSPL-TRIMMING |  | SAURABH | SADDLE ASSY.#3 @ RECOILER |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2405-JSPL-TRIMMING |  | SAURABH | SHEAR ASSY. |  |  | 1500000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2405-JSPL-TRIMMING |  | SAURABH | FOUNDATION BOLTS |  |  | 300000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2405-JSPL-TRIMMING |  | SAURABH | TAPER PLATES |  |  | 300000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | SCRAP DOWN TABLE ASSY. |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE & SCRAP SUIT |  |  | 200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | THREADING TABLE ASSY. |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | SCRAP TROLLEY ASSY. |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE #1 |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE #2 |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE #3 |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE #4 |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE #5 |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | PASSING TABLE #6 |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | SIDE GUIDE ASSY. |  |  | 1500000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | FOUNDATION BOLTS |  |  | 500000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2239-SHYAM-TRIMMING |  | ADITYA SAINI | TAPER & FLAT PLATES |  |  | 500000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | TRIMMING | Apr 2025
2305-APL-CGL |  | SAURABH | JCF Ducting assembly |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE |  | Payment required |  |  |  | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | Adjustable Gas control valves |  |  | 200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | BRUSHING ROLL ASSY.#1 |  |  | 2000000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | BRUSHING ROLL ASSY.#2 |  |  | 2000000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | ASSEMBLY OF THROAT |  |  | 200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | DEGREASING TANK ASSY #1 |  |  | 800000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | BRUSHING TANK ASSY #1 |  |  | 800000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | HOT WATER RINSING TANK |  |  | 800000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | AIR DRYER @ CAG |  |  | 200000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | CHEMICAL COATER ASSY. |  |  | 3000000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | HYDRAULIC & PNEUMATIC SYSTEM [VALVE STANDS] |  |  | 3000000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | HOT AIR DRYER ASSY. |  |  | 600000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | HOT AIR DRYER @ TOC |  |  | 600000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2305-APL-CGL |  | SAURABH | HNX GAS STATION |  |  | 1723000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2421-APL-CGL |  | SAURABH | UNCOILER-COIL SADDLE ASSY. |  |  | 200000 | Disp. | 2025-04-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CGL | Apr 2025
2421-APL-CGL |  | SAURABH | RECOILER-COIL SADDLE ASSY. |  |  | 100000 | Disp. | 2025-04-28 |  | FALSE | FALSE |  | READY FOR DISPATCH |  |  |  | CGL | Apr 2025
2421-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR MOVING FRAME ASSY |  |  | 3400000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2421-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR FIX FRAME ASSY |  |  | 3700000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2421-APL-CGL |  | SAURABH | ENTRY ACCUMULATOR STRUCTURE |  |  | 2000000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | CGL | Apr 2025
2221-TPI REVAMP |  | MAYANK | DTR |  |  | 3500000 | Disp. | 2025-04-28 |  | FALSE | FALSE | [5 empty] | REVAMP | Apr 2025